## 00 Summary
IH35-TMS MASTER TRACKER — v29
Generated 2026-06-17 13:50 CST from live repo + GitHub reconciliation
Metric | v24 snapshot (2026-06-08) | LIVE now
main HEAD | 7490803c3 (#794) | 49638a7a
Highest merged PR | #813 | #923
Total merged PRs (GitHub) | 749 | 871
Merged since #813 | — | 92 (#814→#923 range; 18 nums closed-unmerged/open)
Repo facts (what's in the tree now): 448 migrations · 591 verify scripts · 455 backend route files · 426 frontend routes · 234 block-ready manifests.
Old tracker got these wrong (listed pending — actually DONE): AI-1b closed-period ledger write-lock (posting-engine.service.ts:169-176→PERIOD_LOCKED); BLOCK-19 audit hash-chain (202606111051_w1a_event_log_immutable.sql, #869); AI-3b financial probes (verify-accounting-*+verify-bank-recon-*, #816); P0 FUEL/DISPATCH sub-nav (#817/#818/#833); Wave-0 #794–#813 all merged.
Why PR numbers jump: GitHub uses one global counter across PRs and issues; gaps = closed-unmerged PRs, issues, or still-open PRs. In #814–#923: 92 merged, 18 gaps (#821, #830, #832, #835, #836, #837, #839, #841, #845, #848, #850, #852, #858, #876, #895, #903, #911, #912).
REFRESH 2026-06-17
main HEAD | 49638a7a (v28) | 25c84d5c
Merged PRs (record) | #480..#1014 | #480..#1132 (600 pulled)
.block-ready construction blocks | 294 | 294
shipped (branch merged) | — | 224
PENDING (no merged branch) | — | 70
PRs merged last 48h | — | 80
Live prod build | — | 596e85c (deactivate fix)

## 01 All Tasks
ALL TASKS — complete sequential reconciled record
# renumbered 1..N · duplicates flagged · generated 2026-06-15
# | Phase / Section | Task ID / PR | Task Name | Orig Status | Reconciled Status | Merge Date | Merge Time | Est Min | Dup? | Notes / Evidence
▼ Phase 1 — Foundation
1 | Phase 1 — Foundation | P1-ALL | Identity + auth + 2FA, audit log, outbox, multi-tenant org, … | DONE | DONE |  |  |  |  | Closed pre-May 8 at commit 999a114
▼ Phase 2 — Core Operations
2 | Phase 2 — Core Operations | P2-ALL | Catalogs, maint v1, fuel v1, banking shell, factoring views,… | DONE | DONE |  |  |  |  | Closed pre-May 8
▼ Phase 3 — Screen Rebuilds
3 | Phase 3 — Screen Rebuilds | T11.5 | Dispatch rebuild + gates | DONE | DONE |  |  |  |  | List-table, Driver Status column, Book Load modal
4 | Phase 3 — Screen Rebuilds | T11.5.1 | Dispatch follow-up (authorization gates) | DONE | DONE |  |  |  |  | WF-044 advisory, WF-050 hard block, WF-038 HOS
5 | Phase 3 — Screen Rebuilds | T11.6 | Maintenance rebuild | DONE | DONE |  |  |  |  | 5-button action row + 8 sub-tabs
6 | Phase 3 — Screen Rebuilds | T11.6.1 | Maintenance follow-up A (WO Format V2) | DONE | DONE |  |  |  |  | V5 vendor invoice suffix, parts inventory
7 | Phase 3 — Screen Rebuilds | T11.6.2 | Maintenance follow-up B (Arriving Soon) | DONE | DONE |  |  |  |  | PM due priority queue
8 | Phase 3 — Screen Rebuilds | T11.7 | Settlement screen | DONE | DONE |  |  |  |  | Presettlement → final → voided; void requires Owner
9 | Phase 3 — Screen Rebuilds | T11.8 | Fuel planner | DONE | DONE |  |  |  |  | Loves daily price upload, recommendation vs actual
10 | Phase 3 — Screen Rebuilds | T11.9 | Banking rebuild | DONE | DONE |  |  |  |  | 6 account tiles, BOA/IBC/Faro/escrow
11 | Phase 3 — Screen Rebuilds | T11.10 | Safety + liabilities | DONE | DONE
12 | Phase 3 — Screen Rebuilds | T11.11 | Cash advance | DONE | DONE
13 | Phase 3 — Screen Rebuilds | T11.12 | Factoring detail | DONE | DONE
14 | Phase 3 — Screen Rebuilds | T11.13 | Form 425C | DONE | DONE |  |  |  |  | Monthly Operating Report for Ch.11
15 | Phase 3 — Screen Rebuilds | T11.14 | Lists hub | DONE | DONE
16 | Phase 3 — Screen Rebuilds | T11.16 | Reports module foundation | DONE | DONE
17 | Phase 3 — Screen Rebuilds | T11.17 | Universal cost box base | DONE | DONE
18 | Phase 3 — Screen Rebuilds | T11.17.1A | Cost box variant A | DONE | DONE
19 | Phase 3 — Screen Rebuilds | T11.17.1B | Cost box variant B | DONE | DONE
20 | Phase 3 — Screen Rebuilds | T11.17.2 | Cost box rollup | DONE | DONE
21 | Phase 3 — Screen Rebuilds | T11.17.3 | Drivers detail expansion | DONE | DONE
22 | Phase 3 — Screen Rebuilds | T11.17.5 | Customers detail expansion | DONE | DONE
23 | Phase 3 — Screen Rebuilds | T11.17.6 | Final detail polish | DONE | DONE
24 | Phase 3 — Screen Rebuilds | T11.18 | Forms standardization | DONE | DONE |  |  |  |  | Closed at ac31b3a
25 | Phase 3 — Screen Rebuilds | T6 | PC*MILER integration | CANCELLED | CANCELLED |  |  |  |  | Cancelled. Routing engine decision pending
▼ Phase 4 — Driver PWA
26 | Phase 4 — Driver PWA | T11.15.1 | PWA shell (4-tab nav, i18n EN+ES, icons, PendingSyncBar) | DONE | DONE |  |  |  |  | commit ddb228e
27 | Phase 4 — Driver PWA | T11.15.2 | Today/LoadDetail/StopAction/Acceptance + WF-051 geofence + s… | DONE | DONE |  |  |  |  | commit 0415e3d (WF-051 shipped at 25-mile; spec is 250 FEET — corrected via CAP-3 PR #213)
28 | Phase 4 — Driver PWA | T11.15.3 | DVIR (49 CFR §392.7), HOS, Earnings G23, IncidentReport WF-0… | DONE | DONE |  |  |  |  | commit 34c5f4b
29 | Phase 4 — Driver PWA | T11.15.4 | Backend reapply (REVERTED) | DONE | DONE |  |  |  |  | 37c78a7 → REVERTED 8d6b7f0
30 | Phase 4 — Driver PWA | T11.15.5 | Backend reapply + PWA cleanup | DONE | DONE |  |  |  |  | commit a067a40
31 | Phase 4 — Driver PWA | T11.15.6 | Drivers-only role gate + multi-credential login | DONE | DONE |  |  |  |  | commit 8e8959f
32 | Phase 4 — Driver PWA | T11.15.7 | Real email provider | PENDING | PENDING |  |  |  |  | BLOCKS T11.16.3
33 | Phase 4 — Driver PWA | T11.15.8 | Orphan-report office UI (45 driver identities + 5 mdata.driv… | PENDING | PENDING
▼ Phase 4 — Office Polish
34 | Phase 4 — Office Polish | T11.16.1 | Reports backend wiring (5 real + 3 stub + 18 cadences) | DONE | DONE |  |  |  |  | commit ed05dd9
35 | Phase 4 — Office Polish | T11.16.2 | Report runner UI + CSV export | DONE | DONE |  |  |  |  | commit 6ffbdb7
36 | Phase 4 — Office Polish | T11.16.3 | Email cron worker (needs T11.15.7) | PENDING | PENDING
37 | Phase 4 — Office Polish | T11.17.7 | Customer detail backend (Contacts/Billing/Lanes + 0059) | DONE | DONE |  |  |  |  | commit 77d00d7
38 | Phase 4 — Office Polish | T11.18-HOME | Office HOME page real data | DONE | DONE
39 | Phase 4 — Office Polish | T11.19 | HOME page polish (after T11.18) | PENDING | DONE |  |  |  |  | / matched merged PR by Task-ID
▼ Phase 4 — Accounting (T11.20)
40 | Phase 4 — Accounting (T11.… | T11.20.1 | Schema (5 tables + view + 2 triggers + RLS) | DONE | DONE |  |  |  |  | commit 49ed8d1 / migration 0060
41 | Phase 4 — Accounting (T11.… | T11.20.2 | Invoice generation flow | DONE | DONE |  |  |  |  | commit 4bf9e57
42 | Phase 4 — Accounting (T11.… | T11.20.3 | Payment recording | DONE | DONE |  |  |  |  | commit 4cc8721
43 | Phase 4 — Accounting (T11.… | T11.20.4 | AR aging real numbers | DONE | DONE |  |  |  |  | commit e009196
44 | Phase 4 — Accounting (T11.… | T11.20.5 | Factoring tracking | DONE | DONE |  |  |  |  | commit 2fcb3eb / migration 0061
45 | Phase 4 — Accounting (T11.… | T11.20.6.1 | QBO master-data read-only mirror Phase 1 | DONE | DONE |  |  |  |  | DIR-B 2026-05-13, migration 0142
46 | Phase 4 — Accounting (T11.… | T11.20.6.2 | QBO write-back umbrella (all 6 cuts CLOSED) | DONE | DONE |  |  |  |  | All 6 cuts merged: customers/vendors/items/accounts/invoices/bills
47 | Phase 4 — Accounting (T11.… | T11.20.6.2.1 | QBO write-back customers | DONE | DONE |  |  |  |  | PR #192 (merge 9013268). Cut 1
48 | Phase 4 — Accounting (T11.… | T11.20.6.2.2 | QBO write-back vendors | DONE | DONE |  |  |  |  | PR #194 (merge a54dac3). Cut 2
49 | Phase 4 — Accounting (T11.… | T11.20.6.2.3 | QBO write-back items/products | DONE | DONE |  |  |  |  | PR #195 (merge 08c3d10). Cut 3
50 | Phase 4 — Accounting (T11.… | T11.20.6.2.4 | QBO write-back accounts (chart of accounts) | DONE | DONE |  |  |  |  | PR #197 (merge baca2f4). Cut 4
51 | Phase 4 — Accounting (T11.… | T11.20.6.2.5 | QBO write-back invoices | DONE | DONE |  |  |  |  | PR #199. Cut 5 with mdata.qbo_invoices migration
52 | Phase 4 — Accounting (T11.… | T11.20.6.2.6 | QBO write-back bills | DONE | DONE |  |  |  |  | PR #201 (merge b006f01). Cut 6 — closes T11.20.6.2 with mdata.qbo_bills migration
▼ Phase 4 — Catalog
53 | Phase 4 — Catalog | T11.21.0 | Catalog seed data migration 0062 (~555 rows) | DONE | DONE |  |  |  |  | commit 6b6abe6
54 | Phase 4 — Catalog | T11.21.2A | Safety catalogs (3 catalogs, legacy schemas) | DONE | DONE |  |  |  |  | commit 264b24e
55 | Phase 4 — Catalog | T11.21.3A | Dispatch catalogs (4 catalogs, factory pattern) | DONE | DONE |  |  |  |  | commit c2ff851
56 | Phase 4 — Catalog | T11.21.4A | Driver catalogs (4 catalogs) | PENDING | DONE |  |  |  |  | Next up / matched merged PR by Task-ID
57 | Phase 4 — Catalog | T11.21.5A | Maintenance catalogs (8 catalogs) | DONE | DONE
58 | Phase 4 — Catalog | T11.21.6A | Fuel catalogs (7 catalogs) | PENDING | PENDING
59 | Phase 4 — Catalog | T11.21.7A | Accounting catalogs (5+ catalogs) | PENDING | PENDING
60 | Phase 4 — Catalog | T11.21.8A | Fleet catalogs (6 catalogs) | PENDING | PENDING
▼ Phase 4 — Cleanup
61 | Phase 4 — Cleanup | Cleanup-1 | 0041 idempotency + render preDeployCommand + 0051/0052 view … | DONE | DONE |  |  |  |  | commit d811d88
62 | Phase 4 — Cleanup | Cleanup-2 | 5 UX bug fixes | DONE | DONE |  |  |  |  | commit 351136e (distinct from Dispatch-4 CLEANUP-2 PR #321)
63 | Phase 4 — Cleanup | Cleanup-3 | Permanent grants migration 0065 + developer doc | IN FLIGHT | DONE |  |  |  |  | / matched merged PR by Task-ID
64 | Phase 4 — Cleanup | Cleanup-hub | Lists hub domain map regression fix + wire new catalogs | DONE | DONE
65 | Phase 4 — Cleanup | Cleanup-hyphen | Table CODE column hyphen rendering CSS fix | PENDING | PENDING
66 | Phase 4 — Cleanup | Cleanup-list-err… | List pages surface 500/error states | PENDING | PENDING
67 | Phase 4 — Cleanup | Cleanup-attentio… | Today's Attention List → real data | DONE | DONE |  |  |  |  | PR #179 (A2-1). verify-home-attention-tenant-scope.mjs CI guard
68 | Phase 4 — Cleanup | Cleanup-fleet-sn… | Fleet Snapshot card scope to operating company | DONE | DONE |  |  |  | samePR#179→#67 | PR #179 (A2-1). verify-fleet-snapshot-tenant-scope.mjs CI guard
69 | Phase 4 — Cleanup | Cleanup-tests | Backend test infrastructure (0 tests vs 50+ endpoints) | PENDING | PENDING |  |  |  |  | Pre-existing failing suites surfaced 2026-05-23
70 | Phase 4 — Cleanup | Cleanup-orphans | Triage 45 + 5 orphan identities/drivers | PENDING | PENDING
71 | Phase 4 — Cleanup | Cleanup-phone | Jorge phone off-by-one | PENDING | PENDING
72 | Phase 4 — Cleanup | Audit Action 1 | FMCSA verify with real MC# | PENDING | PENDING
73 | Phase 4 — Cleanup | Cleanup-legal-do… | Legal + Docs + Users tenant-scope; Help confirmed frontend-o… | DONE | DONE |  |  |  |  | PR #184 (A1-3). 3 CI guards
▼ Phase 4 — Hotfixes
74 | Phase 4 — Hotfixes | P4-HOTFIX-156 | QBO sync health column-mismatch fix (Bug A read + Bug B writ… | DONE | DONE |  |  |  |  | PR #156 (merge 1dc50a9). Both bugs fixed. Diagnosis doc at 42fd172
▼ Phase 4 — Cycles
75 | Phase 4 — Cycles | Cycle3-Wizard | Book Load V4 wizard | DONE | DONE |  |  |  |  | commit eaf4403, migration 0140
76 | Phase 4 — Cycles | Cycle3-PDFs | 3 monochrome PDF rendering routes | DONE | DONE |  |  |  |  | commits 2e2112f + 7f425207
77 | Phase 4 — Cycles | DIR-A / P6-T1117… | driver_finance.driver_bills proper table separation + RLS | DONE | DONE |  |  |  |  | commit 6af0eae, migration 0141
78 | Phase 4 — Cycles | DIR-B / P6-T1117… | QBO master-data mirror Phase 1 (read-only) | DONE | DONE |  |  |  |  | PR #26, migration 0142
79 | Phase 4 — Cycles | DIR-C / P6-T1117… | Form validation pattern sweep | DONE | DONE |  |  |  |  | commits 5e73c64 + b2c0d72
80 | Phase 4 — Cycles | DIR-D / P6-T1117… | Lists routing + 40 concrete catalog routes + segment tabs | DONE | DONE |  |  |  |  | commit 90b6bdd
81 | Phase 4 — Cycles | DIR-E / P6-T1117… | Load-bookended settlement + expense-to-load + QBO sync obser… | DONE | DONE |  |  |  | samePR#26→#78 | PR #26, migrations 0143+0144
82 | Phase 4 — Cycles | DIR-F / P6-T1117… | Responsive shell + ESC modal + SaveDropdown + Users invite (… | DONE | DONE |  |  |  |  | PR #25 → 7b54bd2
83 | Phase 4 — Cycles | DIR-G / P6-T1117… | DIR-F follow-up: 6 remaining modals + responsive sweep + tes… | IN FLIGHT | SUPERSEDED |  |  |  |  | DIR-G modals/responsive delivered via #462 (nested-modal), #398/#437 (A15 modal audit) — no standalone DIR-G PR
84 | Phase 4 — Cycles | DIR-H / P6-T1117… | Work Order PDFs + mandatory validation + R2 photo + vendor b… | DISPATCHED | SUPERSEDED |  |  |  |  | DIR-H WO-PDF/validation/AP-bill delivered via #262 (WO PDF path), #272 (WO modal), #312 (WO→AP) — no standalone DIR-H PR
85 | Phase 4 — Cycles | DIR-I | Customer email templates + invoice PDF auto-delivery | ON DECK | ON DECK |  |  |  |  | still pending — no merged PR (DIR-I)
86 | Phase 4 — Cycles | DIR-J | OCR parsing of rate confirmation PDFs | ON DECK | ON DECK |  |  |  |  | still pending — no merged PR (DIR-J)
87 | Phase 4 — Cycles | DIR-K | Server-side PDF generation via puppeteer | ON DECK | ON DECK |  |  |  |  | still pending — no merged PR (DIR-K)
88 | Phase 4 — Cycles | DIR-M | Backup/DR plan doc for Ch.11 DIP | ON DECK | ON DECK |  |  |  |  | still pending — no merged PR (DIR-M)
▼ Data Sovereignty (P1)
89 | Data Sovereignty (P1) | DS-1 | Verify QBO mirror (T11.20.6.1) data integrity | SUPERSEDED | SUPERSEDED |  |  |  |  | Superseded 2026-05-21. See DS Remediation
90 | Data Sovereignty (P1) | DS-2 | QBO mirror reconciliation report | SUPERSEDED | SUPERSEDED |  |  |  |  | Superseded 2026-05-21
91 | Data Sovereignty (P1) | DS-3 | Insert integrations.samsara_config row for IH 35 Transportat… | SUPERSEDED | SUPERSEDED |  |  |  |  | Superseded 2026-05-21
92 | Data Sovereignty (P1) | DS-4 | Samsara vehicle import (units T120-T177 or T178) | SUPERSEDED | SUPERSEDED |  |  |  |  | Done via DS-REM-17 (PR #187)
93 | Data Sovereignty (P1) | DS-5 | Samsara driver import | SUPERSEDED | SUPERSEDED |  |  |  | samePR#187→#92 | Done via DS-REM-17 (PR #187)
94 | Data Sovereignty (P1) | DS-7 | Verify production indicator changes to green | SUPERSEDED | SUPERSEDED |  |  |  |  | Superseded 2026-05-21
▼ Architecture
95 | Architecture | ARCH-1 | ih35-db (old software) reactivation | DONE | DONE |  |  |  |  | Service srv-d7chi5rbc2fs73euhivg. Resumed 2026-05-20
96 | Architecture | ARCH-2 | Read ih35-db repo for Samsara reference code | NOT STARTED | NOT STARTED |  |  |  |  | Document what to port vs redesign
97 | Architecture | ARCH-4 | Identify Samsara features in blueprint vs new from 2026-05-2… | NOT STARTED | NOT STARTED |  |  |  |  | Read docs/specs/IH35_MASTER_BLUEPRINT_v3_FULL.md
▼ Samsara Capabilities
98 | Samsara Capabilities | CAP-1 | Real-time GPS tracking on every active load | DONE | DONE |  |  |  |  | PR #234
99 | Samsara Capabilities | CAP-2 | Auto-create geofences on dispatch (pickup + delivery + fuel) | DONE | DONE |  |  |  |  | PR #218. Consumes CAP-GEOFENCE-FOUNDATION (#207)
100 | Samsara Capabilities | CAP-3 | 250-foot arrival prompt (driver alert to check in) | DONE | DONE |  |  |  | samePR#213→#27 | PR #213. Consumes CAP-9 pairing
101 | Samsara Capabilities | CAP-4 | Auto-status switching on vehicle movement | DONE | DONE |  |  |  |  | PR #223. Suggest-only
102 | Samsara Capabilities | CAP-5 | Dispatch board on-track / behind / delayed pills | DONE | DONE |  |  |  |  | PR #215
103 | Samsara Capabilities | CAP-6 | HOS-driven fuel stop calculation in fuel planner | DONE | DONE |  |  |  |  | PR #220
104 | Samsara Capabilities | CAP-7 | Maintenance prediction from live odometer | DONE | DONE |  |  |  |  | PR #221
105 | Samsara Capabilities | CAP-8 | Engine diagnostic fault → auto work order creation | DONE | DONE |  |  |  |  | PR #229. 7-day dedup
106 | Samsara Capabilities | CAP-9 | Vehicle-driver pairing-at-time-of-event tracking | DONE | DONE |  |  |  |  | PR #210. Foundation for CAP-3/5/13
107 | Samsara Capabilities | CAP-10 | Driver scoring page in safety module | DONE | DONE |  |  |  |  | PR #230
108 | Samsara Capabilities | CAP-11 | Dashcam integration (in-cab + road-facing) | DONE | DONE |  |  |  |  | PR #231. RBAC-restricted
109 | Samsara Capabilities | CAP-12 | DVIR integrated into safety (49 CFR §392.7) | DONE | DONE |  |  |  |  | T11.15.3 at 34c5f4b
110 | Samsara Capabilities | CAP-13 | DOT inspection station geofence dwell tracking | DONE | DONE |  |  |  |  | PR #224 + #207 foundation
111 | Samsara Capabilities | CAP-15 | Samsara driver ↔ QBO vendor mapping integrity | DONE | DONE |  |  |  |  | PR #189 (detection) + #193 (resolution, e5d01c0)
112 | Samsara Capabilities | CAP-HOS-FOUNDATI… | HOS duty status events + FMCSA clock service | DONE | DONE |  |  |  |  | PR #204
113 | Samsara Capabilities | CAP-GEOFENCE-FOU… | Generic geofencing infrastructure | DONE | DONE |  |  |  |  | PR #207
114 | Samsara Capabilities | CAP-16 | Geofence breach alerts | DONE | DONE |  |  |  |  | PR #243
115 | Samsara Capabilities | CAP-AGGREGATE | Driver day-summary card | DONE | DONE |  |  |  |  | PR #235
116 | Samsara Capabilities | CAP-HEATMAP | Position heatmap layer on dispatch map | DONE | DONE |  |  |  |  | PR #236
117 | Samsara Capabilities | CAP-FUEL-CARD | Match fuel-card transactions to GPS at fuel stop | DONE | DONE |  |  |  |  | PR #237
▼ Phase 5A
118 | Phase 5A | P5-T1.1 | Banking Schema (4 tables + RLS) | DONE | DONE |  |  |  |  | commit 071b245
▼ Phase 5B
119 | Phase 5B | P5-T1.3 | Plaid Frontend Link + Daily Cron | PENDING | DONE |  |  |  |  | / matched merged PR by Task-ID
▼ Phase 5C
120 | Phase 5C | P5-T2 | Reconciliation Workspace UI | PENDING | DONE |  |  |  |  | / matched merged PR by Task-ID
121 | Phase 5C | P5-T3 | QBO Sync state machine (queue + retry + Class auto-derive) | DONE | DONE |  |  |  |  | PR #191 (4002c41)
122 | Phase 5C | P5-T5 | Driver settlement auto-pay | DONE | DONE |  |  |  |  | DIR-E foundation done · PR #483 · merged + LIVE 2026-06-04
▼ Phase 5D
123 | Phase 5D | P5-T6 | Banking Transfer between accounts | PENDING | DONE |  |  |  |  | Jorge G11 / matched merged PR by Task-ID
124 | Phase 5D | P5-T7 | Record Credit Card Payment | PENDING | DONE |  |  |  |  | Jorge G11 / matched merged PR by Task-ID
125 | Phase 5D | P5-T8 | Bills-with-balance dropdown for AP payment | DONE | DONE |  |  |  |  | Jorge G12 · PR #484 · merged + LIVE 2026-06-04
126 | Phase 5D | P5-T9 | Bill payment sub-rows for partial payments | PENDING | DONE |  |  |  |  | Jorge G12 / matched merged PR by Task-ID
127 | Phase 5D | P5-T11 | Manual JE 2-step modal | PENDING | DONE |  |  |  | DUP→#118 | / matched merged PR by Task-ID
▼ Phase 5E
128 | Phase 5E | P5-T12 | Auto-deduct on load abandonment | PENDING | DONE |  |  |  |  | Jorge G8 / matched merged PR by Task-ID
129 | Phase 5E | P5-T13 | Settlement disputes workflow | PENDING | DONE |  |  |  | DUP→#119 | Jorge G38 / matched merged PR by Task-ID
130 | Phase 5E | P5-T14 | Team drivers + 50/50 split | PENDING | DONE |  |  |  |  | Jorge G40 / matched merged PR by Task-ID
131 | Phase 5E | P5-T16 | Severe Repair / OOS estimate generation | PENDING | DONE |  |  |  |  | Jorge G20 / matched merged PR by Task-ID
▼ Phase 5F
132 | Phase 5F | P5-T17 | Roadservice as 3rd R&M bucket | PENDING | DONE |  |  |  |  | Jorge G10 / matched merged PR by Task-ID
133 | Phase 5F | P5-T18 | Safety dashboard 7-10 day active filter | PENDING | DONE |  |  |  |  | Jorge G25 / matched merged PR by Task-ID
134 | Phase 5F | P5-T19 | Assignments quicksave on truck/trailer click | PENDING | DONE |  |  |  |  | Jorge G26 / matched merged PR by Task-ID
135 | Phase 5F | P5-T21 | Equipment dual-confirmation transfer (WF-047) | PENDING | DONE |  |  |  |  | Jorge G14 / matched merged PR by Task-ID
▼ Phase 5G
136 | Phase 5G | P5-T22 | Faro factoring CSV import | PENDING | DONE |  |  |  |  | / matched merged PR by Task-ID
137 | Phase 5G | P5-T24 | TRK QBO migration runbook execution | PENDING | DONE |  |  |  |  | Date passed, needs reschedule / matched merged PR by Task-ID
▼ Phase 5H
138 | Phase 5H | P5-T25 | TMS↔QBO Payroll integration (Option B locked) | ON DECK | DONE |  |  |  |  | Cycle 5 post-MVP / matched merged PR by Task-ID
▼ Accounting Backbone A
139 | Accounting Backbone A | Block-1 | Accounting sub-nav route parity | DONE | DONE |  |  |  |  | A Backbone
140 | Accounting Backbone A | Block-2 | Accounting backbone spec document | DONE | DONE |  |  |  |  | A Backbone
141 | Accounting Backbone A | Block-3 | JE line contract decision | DONE | DONE |  |  |  |  | A Backbone
142 | Accounting Backbone A | Block-4 | Posting backbone schema — migration 0195 | DONE | DONE |  |  |  |  | A Backbone
143 | Accounting Backbone A | Block-5 | Posting engine MVP design document | DONE | DONE |  |  |  |  | A Backbone
144 | Accounting Backbone A | Block-6 | Posting engine MVP deferred-decisions document | DONE | DONE |  |  |  |  | A Backbone
145 | Accounting Backbone A | Block-7 | Posting engine MVP code | DONE | DONE |  |  |  |  | A Backbone
146 | Accounting Backbone A | Block-8 | Backlog backfill | DONE | DONE |  |  |  |  | No-op: ledger empty
147 | Accounting Backbone A | Block-9 | First live posting verification | DONE | DONE |  |  |  |  | PR #136 docs
148 | Accounting Backbone A | Block-9-FIX-1 | Units-create INSERT arity | DONE | DONE |  |  |  |  | commit debd5cd
149 | Accounting Backbone A | Block-9-FIX-2 | Driver-create preferred_language | DONE | DONE |  |  |  |  | PR #134, migration 0197
150 | Accounting Backbone A | Block-9-FIX-3 | Applied 0197 + seeded drivers/customers/vendors | DONE | DONE
151 | Accounting Backbone A | Block-9-FIX-4 | Driver company scope | DONE | DONE |  |  |  |  | PR #135 (17d98f5)
152 | Accounting Backbone A | Block-9-FIX-5 | Pre-flight A-F audit (77 findings) | DONE | DONE
153 | Accounting Backbone A | Block-10 | Trial balance ledger balance proof | DONE | DONE |  |  |  |  | PR #141
154 | Accounting Backbone A | Block-11 | Accounting period management | DONE | DONE |  |  |  |  | PR #142
▼ Accounting Backbone B
155 | Accounting Backbone B | Block-12 | Profit & Loss statement | DONE | DONE |  |  |  |  | PR #143
156 | Accounting Backbone B | Block-13 | Balance Sheet | DONE | DONE |  |  |  |  | PR #144
157 | Accounting Backbone B | Block-14 | Cash Flow statement | DONE | DONE |  |  |  |  | PR #145
158 | Accounting Backbone B | Block-15 | Accounts Receivable aging | DONE | DONE |  |  |  |  | PR #147
159 | Accounting Backbone B | Block-16 | Accounts Payable aging | DONE | DONE |  |  |  |  | PR #148
160 | Accounting Backbone B | Block-17 | Period selector / date-range engine | DONE | DONE |  |  |  |  | PR #149
161 | Accounting Backbone B | Block-18 | Statement export | DONE | DONE |  |  |  |  | PR #150 + #151 + #152
162 | Accounting Backbone B | Block-19 | Accounting reports UI | DONE | DONE |  |  |  |  | PR #155 (49c7059)
▼ Accounting Backbone C
163 | Accounting Backbone C | Block-20 | Expense posting engine — trilogy | DONE | DONE |  |  |  |  | Trilogy: 20.1+20.2+20.3 ALL DONE. CPA/bookkeeper-approved 2026-05-23
164 | Accounting Backbone C | Block-20.1 | Cash-basis transformation engine foundation | DONE | DONE |  |  |  |  | PR #196 (b87ff46). Engine + migration 0217 + workbook
165 | Accounting Backbone C | Block-20.2 | Frontend basis selector + report wire-up | DONE | DONE |  |  |  |  | PR #198. Default Accrual, no per-user memory
166 | Accounting Backbone C | Block-20.3 | Period close lock + recompute guard | DONE | DONE |  |  |  |  | PR #200. Trigger migration locks cash-basis
167 | Accounting Backbone C | Block-21 | Expense category to account map + resolver service | DONE | DONE |  |  |  |  | PR #202 (c026c10). Foundation for Block-22..28 + 32/33
168 | Accounting Backbone C | Block-22 | Driver settlement posting | DONE | DONE |  |  |  |  | PR #241
169 | Accounting Backbone C | Block-23 | Escrow posting | DONE | DONE |  |  |  |  | PR #233
170 | Accounting Backbone C | Block-24 | Factoring posting — VQ1 Option A locked | DONE | DONE |  |  |  |  | PR #214
171 | Accounting Backbone C | Block-25 | Factoring fees and reserves | DONE | DONE |  |  |  |  | PR #216
172 | Accounting Backbone C | Block-26 | Factor reconciliation — Q11 tolerance | DONE | DONE |  |  |  |  | PR #217
173 | Accounting Backbone C | Block-27 | Fuel expense posting via Block-21 | DONE | DONE |  |  |  |  | PR #203 (3ce6162). Driver-advance + company-direct
174 | Accounting Backbone C | Block-28 | Maintenance AP posting on WO close | DONE | DONE |  |  |  |  | PR #205 (7d15948). Wires Block-21 resolver
175 | Accounting Backbone C | Block-29 | Bank reconciliation engine | DONE | DONE |  |  |  |  | PR #206. Q8 + Q11 tolerance
176 | Accounting Backbone C | Block-30 | Bank reconciliation UI | DONE | DONE |  |  |  |  | PR #219. Two-pane UI on Block-29
177 | Accounting Backbone C | Block-31 | Sales tax handling | DONE | DONE |  |  |  |  | PR #222. Authorities + rates + codes
178 | Accounting Backbone C | Block-32 | Bill line account_id resolution via Block-21 | DONE | DONE |  |  |  |  | PR #208
179 | Accounting Backbone C | Block-33 | Invoice line revenue mapping via Block-21 | DONE | DONE |  |  |  |  | PR #209
180 | Accounting Backbone C | Block-34 | Payment application + overpay → credit/vendor memo | DONE | DONE |  |  |  |  | PR #211
181 | Accounting Backbone C | Block-35-A | Formalize chart of accounts roles per company | DONE | DONE |  |  |  |  | PR #212
182 | Accounting Backbone C | Block-35 | Chart of accounts main | NOT STARTED | NOT STARTED |  |  |  |  | Block-35-A done; main Block-35 ahead — Jorge to confirm scope
183 | Accounting Backbone C | Block-36 | Multi-entity accounting (3 companies: TRK + TRANSP + USMCA) | DONE | DONE |  |  |  |  | PR #225. Claude hotfix for TS1131/TS1005 + verify-ts-brace-balance.mjs
184 | Accounting Backbone C | Block-42 | (Reserved — scope undefined) | NOT STARTED | NOT STARTED |  |  |  |  | No PR. Jorge to confirm what Block-42 is
185 | Accounting Backbone C | Block-CMC | Month-close wizard | DONE | DONE |  |  |  |  | PR #238
186 | Accounting Backbone C | Block-CF | 13-week cash forecast | DONE | DONE |  |  |  |  | PR #239
187 | Accounting Backbone C | Block-PPC | Period comparison report | DONE | DONE |  |  |  |  | PR #240
188 | Accounting Backbone C | Block-44 | AR collections workflow | DONE | DONE |  |  |  |  | PR #242 + #251 rework
▼ Accounting Backbone D
189 | Accounting Backbone D | Block-37 | Fix QBO sync — repair pipeline | DONE | DONE |  |  |  |  | PR #226. Closes long-standing PARTIAL umbrella
190 | Accounting Backbone D | Block-38 | Sync conflict detection + ConflictsTab | DONE | DONE |  |  |  |  | PR #190 (954ec5a)
191 | Accounting Backbone D | Block-39 | QBO Sync event log detail page | DONE | DONE |  |  |  |  | PR #188 (c6d0672)
192 | Accounting Backbone D | Block-40 | Accounting audit trail | DONE | DONE |  |  |  |  | PR #227. Universal emission + CI guard verify-accounting-writes-emit-audit
193 | Accounting Backbone D | Block-41 | Posting lineage UI | DONE | DONE |  |  |  |  | PR #228. Read-only graph on Block-40 data
194 | Accounting Backbone D | Block-43 | Live-DB schema verification | DONE | DONE |  |  |  |  | PR #232. Nightly drift detector cron + CI guard
▼ Phase 6
195 | Phase 6 | P6-EDI | EDI 204/210/214 broker integration | PENDING | PENDING
196 | Phase 6 | P6-Lanes | Load optimizer / lane pairing | PENDING | PENDING
197 | Phase 6 | P6-Pricing | Pricing engine (dynamic quoting) | PENDING | PENDING
198 | Phase 6 | P6-Recurring | Recurring invoices | PENDING | PENDING
199 | Phase 6 | P6-CSA | CSA forecasting | PENDING | PENDING
▼ Phase 7 Stabilization
200 | Phase 7 Stabilization | P7-MAINT-FOUNDAT… | Maintenance go-live foundation | DONE | DONE |  |  |  |  | PR #261
201 | Phase 7 Stabilization | P7-MAINT-PM-INSP… | PM inspection records | DONE | DONE |  |  |  |  | PR #263
202 | Phase 7 Stabilization | P7-MAINT-MASTER-… | Maintenance master data | DONE | DONE |  |  |  |  | PR #266
203 | Phase 7 Stabilization | P7-MAINT-WO-PDF | Wire WO PDF path + block guards | DONE | DONE |  |  |  |  | PR #262
204 | Phase 7 Stabilization | P7-MAINT-WO-MODA… | WO modal: catalog pickers + 7 source types + vendor + 2 guar… | DONE | DONE |  |  |  |  | PR #272
205 | Phase 7 Stabilization | P7-SAFETY-FOUNDA… | Safety foundation KPI coverage guard + endpoints | DONE | DONE |  |  |  |  | PR #264
206 | Phase 7 Stabilization | P7-SAFETY-DRIVER… | Driver profile records + coverage guards | DONE | DONE |  |  |  |  | PR #265
207 | Phase 7 Stabilization | P7-SAFETY-TRAINI… | Training programs + drug pool + safety reports guards | DONE | DONE |  |  |  |  | PR #267
208 | Phase 7 Stabilization | P7-SAFETY-EVENTS | Safety events module + migration 0261 + frontend + 2 guards | DONE | DONE |  |  |  |  | PR #269
209 | Phase 7 Stabilization | P7-INFRA-BRANCH-… | Branch tooling: rebuild-linear + precheck-push + safe-switch | DONE | DONE |  |  |  |  | PR #268
210 | Phase 7 Stabilization | P7-INFRA-SYNC-OR… | Sync orchestrator + block:ship + verify-branch-fresh | DONE | DONE |  |  |  |  | PR #270
211 | Phase 7 Stabilization | P7-HOTFIX-3-AUDI… | 1 P0 + 6 P1s from 2026-05-25 audit + 3 guards | DONE | DONE |  |  |  |  | PR #271
212 | Phase 7 Stabilization | P7-SAF-DRIVER-DQ… | Safety DQF lane kickoff | DONE | DONE |  |  |  |  | PR #297
▼ Phase 7 Dispatch 4 — Asset
213 | Phase 7 Dispatch 4 — Asset | ASSET-01 | Asset registry foundation (mdata.units) | DONE | DONE |  |  |  |  | PR #281. Migration 0262
214 | Phase 7 Dispatch 4 — Asset | ASSET-02 | Damage status + repair estimate | DONE | DONE |  |  |  |  | PR #283. Migration 0263
215 | Phase 7 Dispatch 4 — Asset | ASSET-04 | Assets UI (list + detail) | DONE | DONE |  |  |  |  | PR #282
▼ Phase 7 Dispatch 4 — Accounting
216 | Phase 7 Dispatch 4 — Accou… | ACCT-03 | Multi-unit cost allocation engine | DONE | DONE |  |  |  |  | PR #285. Migration 0264
217 | Phase 7 Dispatch 4 — Accou… | ACCT-05 | Vendor bill form layout fix (structured Item + Account) | DONE | DONE |  |  |  |  | PR #286
218 | Phase 7 Dispatch 4 — Accou… | ACCT-06 | Bill unit allocation UI | DONE | DONE |  |  |  |  | PR #284 + #287
219 | Phase 7 Dispatch 4 — Accou… | ACCT-08 | PSE mirror endpoints + sync guard | DONE | DONE |  |  |  |  | PR #289. 26 cats + items + CoA mirror
220 | Phase 7 Dispatch 4 — Accou… | ACCT-09 | Bill-payment batches → single QBO payment | DONE | DONE |  |  |  |  | PR #293
221 | Phase 7 Dispatch 4 — Accou… | ACCT-10 | Multi-bill UI flow (Create Multiple Bills) | DONE | DONE |  |  |  |  | PR #294. Jorge priority feature
222 | Phase 7 Dispatch 4 — Accou… | ACCT-11 | PSE posting enforcement (Category+Item required) | DONE | DONE |  |  |  |  | PR #295. Corrective addendum
223 | Phase 7 Dispatch 4 — Accou… | ACCT-12 | Per-truck CPM dashboard | DONE | DONE |  |  |  |  | PR #296. vs $2.26 industry benchmark
224 | Phase 7 Dispatch 4 — Accou… | ACCT-TB-HUB | Trial balance hub snapshot | DONE | DONE |  |  |  |  | PR #288. Bonus accounting hub
225 | Phase 7 Dispatch 4 — Accou… | ACCT-PL-HUB | Profit and loss hub snapshot | DONE | DONE |  |  |  |  | PR #290. Bonus accounting hub
▼ Phase 7 Dispatch 4 — Banking
226 | Phase 7 Dispatch 4 — Banki… | BANK-07 | Bulk categorize + post-as-bills flows | DONE | DONE |  |  |  |  | PR #292
▼ Phase 7 Dispatch 4 — Safety
227 | Phase 7 Dispatch 4 — Safet… | SAF-01 | Driver Qualification File API + migration 0267 driver_dqf | DONE | DONE |  |  |  |  | PR #298
228 | Phase 7 Dispatch 4 — Safet… | SAF-02 | Driver DQF list + profile | DONE | DONE |  |  |  |  | PR #300
229 | Phase 7 Dispatch 4 — Safet… | SAF DQF UI | DQF UI Driver Files tab | DONE | DONE |  |  |  |  | PR #299
230 | Phase 7 Dispatch 4 — Safet… | SAF-03 | Medical Examiner Cert 24-mo tracking + migration 0268 | DONE | DONE |  |  |  |  | PR #301
231 | Phase 7 Dispatch 4 — Safet… | SAF-05 | Compliance expiry reminders + migration 0269 | DONE | DONE |  |  |  |  | PR #303. T-60/30/7/expired for DQF/CDL/medical
232 | Phase 7 Dispatch 4 — Safet… | SAF-06 | Drug program + dispatch gate | DONE | DONE |  |  |  |  | PR #304. Dup 0267 resolved by CLEANUP-1 (#309)
233 | Phase 7 Dispatch 4 — Safet… | SAF-07 | Return-to-duty workflow | DONE | DONE |  |  |  |  | PR #305
234 | Phase 7 Dispatch 4 — Safet… | SAF-08 | Driver dispatch gate | DONE | DONE |  |  |  |  | PR #306
235 | Phase 7 Dispatch 4 — Safet… | SAF-09 | Drug program + RTD + gate UI | DONE | DONE |  |  |  |  | PR #307
236 | Phase 7 Dispatch 4 — Safet… | SAF-KPI | Compliance dashboard (per-driver + fleet KPI) | DONE | DONE |  |  |  |  | PR #302
237 | Phase 7 Dispatch 4 — Safet… | SAF-13 | Reminders + DOT reference panel UI | DONE | DONE |  |  |  |  | PR #311 (#308 v1 closed → rebuilt)
▼ Phase 7 Dispatch 4 — Infra
238 | Phase 7 Dispatch 4 — Infra | INF-1 | Per-agent block-ready manifest split | DONE | DONE |  |  |  |  | PR #291
▼ Phase 7 Dispatch 4 — Maint
239 | Phase 7 Dispatch 4 — Maint | MAINT-10 | Parts catalog + PM schedules + migration 0272 | DONE | DONE |  |  |  |  | PR #310
240 | Phase 7 Dispatch 4 — Maint | MAINT-11 | Clean WO → AP bill posting lane + migration 0273 | DONE | DONE |  |  |  |  | PR #312
241 | Phase 7 Dispatch 4 — Maint | MAINT-12 | WO detail + receipt upload + PM inventory UX | DONE | DONE |  |  |  |  | PR #313. Closed Maintenance go-live
▼ Phase 7 Dispatch 4 — Insurance
242 | Phase 7 Dispatch 4 — Insur… | INS-01 | Policies + covered units schema + migration 0274 + correctiv… | DONE | DONE |  |  |  |  | PR #314 + #315
243 | Phase 7 Dispatch 4 — Insur… | INS-02 | Dispersal engine → Create-Multiple-Bills | DONE | DONE |  |  |  |  | PR #319
244 | Phase 7 Dispatch 4 — Insur… | INS-03 | Coverage-gap detector (safety gate) | DONE | DONE |  |  |  |  | PR #324 merged 2026-05-30
245 | Phase 7 Dispatch 4 — Insur… | INS-04 | Certificate request workflow + insurer email | DONE | DONE |  |  |  |  | PR #332 merged 2026-05-30; Sunday 5/31 PR #345 wired COI tab into Customers.tsx
246 | Phase 7 Dispatch 4 — Insur… | INS-05 | Payment reminders + late-fee split | DONE | DONE |  |  |  |  | PR #333 merged 2026-05-30. principal + late_fee + wire_fee bill lines
247 | Phase 7 Dispatch 4 — Insur… | INS-06 | Insurance ↔ accidents / legal / lawsuits link | DONE | DONE |  |  |  |  | PR #334 merged 2026-05-30
248 | Phase 7 Dispatch 4 — Insur… | INS-07 | Insurance module frontend (policies, dispersal, COI, claims) | DONE | DONE |  |  |  |  | PR #335 merged 2026-05-30
▼ Phase 7 Dispatch 4 — Integrity
249 | Phase 7 Dispatch 4 — Integ… | INT-1 | Audit trigger infrastructure (audit.row_changes + tg_audit_r… | DONE | DONE |  |  |  |  | PR #316. Migration 0276
250 | Phase 7 Dispatch 4 — Integ… | INT-2 | Per-driver behavior metrics + peer benchmarks | DONE | DONE |  |  |  |  | PR #320. 1.5× peer-median threshold
251 | Phase 7 Dispatch 4 — Integ… | INT-3 | Anomaly detection + status workflow | DONE | DONE |  |  |  |  | PR #328 merged 2026-05-30
252 | Phase 7 Dispatch 4 — Integ… | INT-4 | Mandatory cancellation reason on dispatch load cancel | DONE | DONE |  |  |  |  | PR #330 merged 2026-05-30
253 | Phase 7 Dispatch 4 — Integ… | INT-5 | Driver-on-repair required link + Safety profile surface | DONE | DONE |  |  |  |  | PR #331 merged 2026-05-30
▼ Phase 7 Dispatch 4 — Maint Extras
254 | Phase 7 Dispatch 4 — Maint… | MNT-4 | Position/location selector on WO line items | DONE | DONE |  |  |  |  | PR #323 merged 2026-05-30
255 | Phase 7 Dispatch 4 — Maint… | MNT-5 | Real fleet parts catalog research (Samsara T120-T177 + Peter… | DONE | DONE |  |  |  |  | PR #317 + #321 (126 parts + 15 PM types calibrated 12k mi/month); Sunday 5/31 PR #347 MNT-5-MIGRATE migrated 144 parts maint.part→maintenance.parts_inventory
▼ Phase 7 Dispatch 4 — Cleanup
256 | Phase 7 Dispatch 4 — Clean… | D4-CLEANUP-1 | Renumber duplicate 0267 migration → 0270 | DONE | DONE |  |  |  |  | PR #309
257 | Phase 7 Dispatch 4 — Clean… | D4-CLEANUP-2 | Renumber duplicate 0275 migration → 0277 | DONE | DONE |  |  |  | samePR#321→#62 | PR #321
258 | Phase 7 Dispatch 4 — Clean… | D4-CLEANUP-3 | Review SKIP_MIGRATION_VERIFICATION=true env var | DONE | DONE |  |  |  |  | PR #326 merged 2026-05-30
259 | Phase 7 Dispatch 4 — Clean… | D4-CLEANUP-4 | Delete 2 orphan migration ledger entries | DONE | DONE |  |  |  |  | PR #327 merged 2026-05-30
260 | Phase 7 Dispatch 4 — Clean… | D4-CLEANUP-5 | Convert Render API key from temporary to permanent | DONE | DONE |  |  |  |  | Done during infra cleanup 2026-05-30
▼ Phase 7 Dispatch 4 — Recovery
261 | Phase 7 Dispatch 4 — Recov… | REVERT-322 | Revert hotfix #322 (broken pm_type CHECK constraint) | DONE | DONE |  |  |  |  | PR #325 (commit c589ac3). Claude opened via GitHub web UI direct
▼ Phase 7 Mobile Apps
262 | Phase 7 Mobile Apps | P7-Maint-Mobile | Maintenance mobile (mechanic app) | PENDING | PENDING |  |  |  |  | Future
263 | Phase 7 Mobile Apps | P7-PWA-v2 | Driver PWA v2 (push notifications, photo R2) | PENDING | PENDING |  |  |  |  | Future
264 | Phase 7 Mobile Apps | P7-Disp-Mobile | Dispatcher mobile board | PENDING | PENDING |  |  |  |  | Future
▼ Phase 8
265 | Phase 8 | P8-IFTA | IFTA quarterly automation | PENDING | PENDING
266 | Phase 8 | P8-2290 | Form 2290 (Heavy Highway Use Tax) | PENDING | PENDING
267 | Phase 8 | P8-Drug | Drug random pool management | PENDING | PENDING
268 | Phase 8 | P8-CSA-Inter | CSA intervention workflow | PENDING | PENDING
▼ DS Remediation
269 | DS Remediation | DS-REMEDIATE-1 | Admin queue + Data Sovereignty route boundary CI guard | DONE | DONE |  |  |  |  | PR #161 + #162 refactor (6f462cb)
270 | DS Remediation | DS-REMEDIATE-2 | Canonical accounting.qbo_remote_counts + collector + outbox … | DONE | DONE |  |  |  |  | PR #164 (641802f). Migration 0201
271 | DS Remediation | DS-REMEDIATE-3 | _system.reconciliation_findings table + lifecycle | DONE | DONE |  |  |  |  | PR #163 (d2324c0)
272 | DS Remediation | DS-REMEDIATE-4 | Reconciliation worker tick (MUST-DS-3 + MUST-DS-4 live) | DONE | DONE |  |  |  |  | PR #165 (7792ea4). Detects 6 finding types
273 | DS Remediation | DS-REMEDIATE-5 | Alert routing for Critical findings (Twilio via outbox.event… | DONE | DONE |  |  |  |  | PR #170 + #172 re-merge after DS-8.1
274 | DS Remediation | DS-REMEDIATE-6 | B-017 empty-UUID scheduler context guard + 9-cron retrofit | DONE | DONE |  |  |  |  | PR #167 (88432d7)
275 | DS Remediation | DS-REMEDIATE-7 | Samsara webhook-event projection worker | DONE | DONE |  |  |  |  | PR #166 (009f165)
276 | DS Remediation | DS-REMEDIATE-8 | DS-5 mirror metadata contract alignment | DONE | DONE |  |  |  |  | PR #168 (33a3a41). Migrations 0204-0210
277 | DS Remediation | DS-REMEDIATE-8.1 | Replace GENERATED columns with real columns (fix) | DONE | DONE |  |  |  |  | PR #171. Fix on top of DS-REM-8
278 | DS Remediation | DS-REMEDIATE-9 | Samsara remote count helper | DONE | DONE |  |  |  |  | PR #169. Closed all DS-REM-4 finding categories
279 | DS Remediation | DS-REMEDIATE-10 | Outbox infrastructure consolidation (post-series cleanup) | DRAFTED | DRAFTED |  |  |  |  | still pending — no merged PR (DS-REMEDIATE-10)
280 | DS Remediation | DS-REMEDIATE-11 | Samsara TRANSP config canonicalization + 94-live counter ten… | DONE | DONE |  |  |  |  | PR #176 (2906b603). Migration 0215 + 3 CI guards
281 | DS Remediation | DS-REMEDIATE-12 | Backend startup migration-drift guard + CI assertion | DONE | DONE |  |  |  |  | PR #177 (94af33e). Caught 136 unledgered migrations on first prod boot
282 | DS Remediation | DS-REMEDIATE-13 | Audit table canonical-name fix (audit.audit_events) | DONE | DONE |  |  |  |  | PR #181 (e3aa7c2). Migration 0216
283 | DS Remediation | DS-REMEDIATE-14 | Fleet-reports-hub removal | DROPPED | DROPPED |  |  |  |  | Owner dropped from queue 2026-05-23
284 | DS Remediation | DS-REMEDIATE-15 | BATCH-8 generator + guard use OR semantics for missing-from-… | DONE | DONE |  |  |  |  | PR #182 (08027f3). Vitest assertion
285 | DS Remediation | DS-REMEDIATE-17 | Samsara → mdata.units full ingestion: replace TEST data with… | DONE | DONE |  |  |  | samePR#187→#92 | PR #187 (00d8ca7). Live on prod
286 | DS Remediation | DS-REMEDIATE-PRO… | Verification infrastructure (branch protection + verify:pre-… | DONE | DONE |  |  |  |  | PR #173. Process improvement
▼ Migration Debt
287 | Migration Debt | BATCH-1 | INSERT arity fixes + arity guard | DONE | DONE |  |  |  |  | PR #137
288 | Migration Debt | BATCH-3 | Maintenance work_order schema drift + guard | DONE | DONE |  |  |  |  | PR #138
289 | Migration Debt | BATCH-3-2C | Forward repair migration — work_order_lines | DONE | DONE |  |  |  |  | PR #139
290 | Migration Debt | BATCH-6 | Customer autocomplete centralized on canonical | DONE | DONE |  |  |  |  | PR #140
291 | Migration Debt | BATCH-8 | Forensic backfill of 136 pre-0067 unledgered migrations | DONE | DONE |  |  |  |  | PR #178 (3e3b8ce). Final: sys=204, app=204, drift=0
292 | Migration Debt | 0199-0214-drift-… | Replay 0199-0214 drift gap + CI guard | DONE | DONE |  |  |  |  | PR #175
293 | Migration Debt | dead-outbox-reco… | Reconcile dead outbox emitters + orphan cleanup + parity gua… | DONE | DONE |  |  |  |  | PR #174
294 | Migration Debt | 0240-seed-purge-… | Use real mdata columns in 0240 seed purge | DONE | DONE |  |  |  |  | PR #256
295 | Migration Debt | 0240-restore-pro… | Restore 0240 to applied-on-prod content; unblock Render | DONE | DONE |  |  |  |  | PR #258
296 | Migration Debt | 0242-drift-recon… | Resolve verify-content drift with 0242 reconciliation | DONE | DONE |  |  |  |  | PR #260
297 | Migration Debt | P7-MIG-IMMUTABIL… | Applied-migrations-immutable static guard | DONE | DONE |  |  |  |  | PR #259
298 | Migration Debt | DS-PROJECTION-AL… | Align data-sovereignty projections with local mdata routes a… | DONE | DONE |  |  |  |  | PR #257
299 | Migration Debt | MAGNET-1 | Glob-loader verify-pre-commit | DONE | DONE |  |  |  |  | PR #244
300 | Migration Debt | MAGNET-2 | Glob-loader EXTRA_GUARDS | DONE | DONE |  |  |  |  | PR #245
301 | Migration Debt | MAGNET-3 | Per-schema known-prod-table-grants | DONE | DONE |  |  |  |  | PR #246
302 | Migration Debt | MAGNET-4 | Autoload accounting route plugins | DONE | DONE |  |  |  |  | PR #247
303 | Migration Debt | MAGNET-5 | Frontend routes manifest | DONE | DONE |  |  |  |  | PR #248
304 | Migration Debt | MAGNET-6 | CI branch-fresh gate + AccountingSubNav manifest | DONE | DONE |  |  |  |  | PR #250
305 | Migration Debt | Block-ready-gate | Tooling: block-ready 10-check gate | DONE | DONE |  |  |  |  | PR #249
306 | Migration Debt | AUDIT-P0-2-fail-… | Audit P0-2 honest fail-closed | DONE | DONE |  |  |  |  | PR #254
307 | Migration Debt | AUDIT-VISUAL-P1 | Audit visual P1 fixes | DONE | DONE |  |  |  |  | PR #255
308 | Migration Debt | SEC-tenant-scope | Enforce tenant-scope membership on accounting + banking | DONE | DONE |  |  |  |  | PR #252
309 | Migration Debt | SEC-qbo-webhook | QBO webhook fail-closed signature verification | DONE | DONE |  |  |  |  | PR #253
310 | Migration Debt | Samsara-VIN-link | VIN linkage to mdata.units + 94-live counter CI guard | DONE | DONE |  |  |  |  | PR #183
311 | Migration Debt | Tenant-scope-cus… | Customers + Vendors tenant-scope sweep + CI guards | DONE | DONE |  |  |  |  | PR #180
▼ QBO Sync Track
312 | QBO Sync Track | QBO-Sync-Health-… | QBO Sync Health Dashboard Card on Office HOME | DONE | DONE |  |  |  |  | PR #185 (A1-4). GET /api/v1/qbo/sync-health. Status pill + 3 counters
313 | QBO Sync Track | QBO-Customers-Sy… | QBO Customers Sync E2E Tenant-scope Audit + CI Guard | DONE | DONE |  |  |  |  | PR #186 (A2-5)
314 | QBO Sync Track | Accounting-Block… | Fix QBO sync (master umbrella block) | DONE | DONE |  |  |  | samePR#226→#18… | PR #226
315 | QBO Sync Track | Accounting-Block… | QBO Sync Conflict Detection + ConflictsTab UI | DONE | DONE |  |  |  | samePR#190→#19… | PR #190 (954ec5a)
316 | QBO Sync Track | Accounting-Block… | QBO Sync Event Log (detail page linked from HOME card) | DONE | DONE |  |  |  | samePR#188→#19… | PR #188 (c6d0672)
▼ Phase 7 Dispatch 5 — Factoring
317 | Phase 7 Dispatch 5 — Facto… | FACT-1 | Factoring batch wizard (Step 1-4) | DONE | DONE |  |  |  |  | PR #336 merged 2026-05-30
318 | Phase 7 Dispatch 5 — Facto… | FACT-2 | Extra-to-reserves automation (reserve_movement table) | DONE | DONE |  |  |  |  | PR #337 merged 2026-05-30
319 | Phase 7 Dispatch 5 — Facto… | FACT-3 | Match factoring in banking (deposit reconciliation) | DONE | DONE |  |  |  |  | PR #338
320 | Phase 7 Dispatch 5 — Facto… | FACT-4 | Multi-factor support (multiple factoring companies) | DONE | DONE |  |  |  |  | PR #339
321 | Phase 7 Dispatch 5 — Facto… | FACT-5 | Reserve visibility (dashboard card + drawer) | DONE | DONE |  |  |  |  | PR #340
▼ Phase 8 — Sunday 5/31 P0 Backend
322 | Phase 8 — Sunday 5/31 P0 B… | P8-P0-LOADS | Empty-string UUID coercion fix in /mdata/loads (was 500) | DONE | DONE |  |  |  |  | PR #341 merged + deployed Sunday 2026-05-31
323 | Phase 8 — Sunday 5/31 P0 B… | P8-P0-TELEMETRY | Column-name fix in /telematics/positions/latest (was 500) | DONE | DONE |  |  |  |  | PR #342 merged + deployed Sunday 2026-05-31
324 | Phase 8 — Sunday 5/31 P0 B… | P8-P0-CUSTOMER-D… | Register /customers/:id/detail route (was 404) | DONE | DONE |  |  |  |  | PR #343 merged + deployed Sunday 2026-05-31
▼ Phase 8 — Sunday 5/31 UI Wire-Up
325 | Phase 8 — Sunday 5/31 UI W… | FACT-WIRE-UI | Factoring routes FACT-1/2/4/5 wired into frontend | DONE | DONE |  |  |  |  | PR #344 merged + deployed Sunday 2026-05-31
326 | Phase 8 — Sunday 5/31 UI W… | INS-04-WIRE-UI | COI tab wired into Customers.tsx (INS-04 follow-up) | DONE | DONE |  |  |  |  | PR #345 merged + deployed Sunday 2026-05-31. Force-with-lease push after CustomerCOITab.tsx fix
▼ Phase 8 — Sunday 5/31 Samsara Data
327 | Phase 8 — Sunday 5/31 Sams… | SMS-FIX-1 | Samsara projection seed: staging vehicles+drivers → canonica… | DONE | DONE |  |  |  |  | PR #346 merged + deployed Sunday 2026-05-31. Migration 0291 had dup-VIN bug — manual SQL fix via Neon: 4→87 units, 4→82 drivers, 100/100 vehicles + 78/78 drivers mapped. 0291 marked applied in ledger.
▼ Phase 8 — Sunday 5/31 Schema Migrate
328 | Phase 8 — Sunday 5/31 Sche… | MNT-5-MIGRATE | 144 parts migrated maint.part→maintenance.parts_inventory (m… | DONE | DONE |  |  |  |  | PR #347 merged + deployed Sunday 2026-05-31
329 | Phase 8 — Sunday 5/31 Sche… | MAINT-10-MIGRATE | 24 PM types migrated maint.pm_schedule→maintenance.pm_schedu… | DONE | DONE |  |  |  |  | PR #348 merged + deployed Sunday 2026-05-31
▼ Phase 8 — Sunday 5/31 P0 Backend
330 | Phase 8 — Sunday 5/31 P0 B… | P8-P0-CUSTOMER-D… | Re-do customer/:id/detail route registration + CI guard | DONE | DONE |  |  |  |  | PR #349 merged + deployed Sunday 2026-05-31 (SHA 22d1b3a)
▼ Phase 8 — Sunday 5/31 Follow-up
331 | Phase 8 — Sunday 5/31 Foll… | SMS-FIX-1-DEDUP | Fix canonical migration 0291 source with DISTINCT ON (vin) +… | PENDING | DONE |  |  |  |  | Manual SQL applied to prod 5/31; canonical source still broken for fresh CI DBs / matched merged PR by Task-ID
332 | Phase 8 — Sunday 5/31 Foll… | RENDER-PREDEPLOY… | Investigate Render predeploy hook config for permanence + ad… | PENDING | PENDING |  |  |  |  | Jorge's explicit ask 5/31
333 | Phase 8 — Sunday 5/31 Foll… | CLEANUP-VERIFY-D… | Delete duplicate scripts/verify-no-empty-string-uuid-bind 3.… | PENDING | PENDING |  |  |  |  | macOS Finder duplicate naming pattern
334 | Phase 8 — Sunday 5/31 Foll… | CURSOR-GH-AUTH-R… | Re-auth Cursor's gh CLI (HTTP 401 after #345 merge) | PENDING | PENDING |  |  |  |  | gh auth refresh -h github.com -s repo,workflow,read:org
335 | Phase 8 — Sunday 5/31 Foll… | LIVE-UI-VISUAL-V… | Walk /dispatch /drivers /maintenance to confirm 87 units / 8… | PENDING | PENDING |  |  |  |  | Verify Sunday 5/31 data lands in UI
▼ Phase 8 Audit Findings
336 | Phase 8 Audit Findings | P8-AUDIT-CUST-BI… | Fix /customers/{id}/billing-summary 500 error | IN FLIGHT | DONE |  |  |  |  | DONE — merged #386 (A8 customers billing-summary fix)
337 | Phase 8 Audit Findings | P8-AUDIT-NESTED-… | Fix nested-box modal pattern (WO Details header ×2, Customer… | DONE | DONE |  |  |  |  | From 2026-05-24 audit P1 · PR #462 · merged + LIVE 2026-06-04
338 | Phase 8 Audit Findings | P8-AUDIT-PROD-ST… | Remove 13+ stub strings rendering in production | DONE | DONE |  |  |  |  | From 2026-05-24 audit P2 · PR #471 · merged + LIVE 2026-06-04
339 | Phase 8 Audit Findings | P8-AUDIT-TEST-DA… | Remove TEST-DRIVER/TEST-CUSTOMER/seed-test-driver leak from … | DONE | DONE |  |  |  |  | From 2026-05-24 audit P2 · PR #469 · merged + LIVE 2026-06-04
340 | Phase 8 Audit Findings | P8-AUDIT-ELD-RED… | Fix /eld redirect-to-/home bug | DONE | DONE |  |  |  |  | From 2026-05-24 audit P3 · PR #464 · merged + LIVE 2026-06-04
341 | Phase 8 Audit Findings | P8-AUDIT-DOCS-RE… | Fix /docs redirect-to-/home bug | DONE | DONE |  |  |  |  | From 2026-05-24 audit P3 · PR #467 · merged + LIVE 2026-06-04
342 | Phase 8 Audit Findings | P8-AUDIT-QBO-ARC… | Fix qbo_archive notes leak to user-facing UI | DONE | DONE |  |  |  |  | From 2026-05-24 audit P3 · PR #468 · merged + LIVE 2026-06-04
343 | Phase 8 Audit Findings | P8-AUDIT-BACKEND… | Backend version displays 'dev' instead of release tag | DONE | DONE |  |  |  |  | From 2026-05-24 audit P3 · PR #461 · merged + LIVE 2026-06-04
344 | Phase 8 Audit Findings | P8-AUDIT-UNDEFIN… | Fix 'undefined' rendering in legend (chart/KPI) | DONE | DONE |  |  |  |  | From 2026-05-24 audit P3 · PR #470 · merged + LIVE 2026-06-04
345 | Phase 8 Audit Findings | P8-AUDIT-KPI-DRI… | Reconcile 8 KPI drifts (production KPIs don't match approved… | DONE | DONE |  |  |  |  | From 2026-05-24 audit P3 · PR #480 · merged + LIVE 2026-06-04
346 | Phase 8 Audit Findings | SMS-FIX-2-WEBHOO… | Investigate why 0 Samsara webhooks ever received in prod | DONE | DONE |  |  |  |  | Real-time GPS feed empty. Separate from SMS-FIX-1 · PR #475 · merged + LIVE 2026-06-04
▼ Packet 2 Phase A — FE-Only Quick Wins
347 | Packet 2 Phase A | #01-Block-W | HOME Book Load modal X close button fix | DONE | DONE |  |  |  |  | PR #354 merged + deployed. fix/home-book-load-modal-x-close.
348 | Packet 2 Phase A | #02-Block-AD | MAINT Jump to tab dropdown remove (redundant) | DONE | DONE |  |  |  |  | PR #355 merged + deployed. fix/maint-jump-to-tab-remove.
349 | Packet 2 Phase A | #03-Block-AE | ELD tab style normalize to underline | DONE | DONE |  |  |  |  | PR #356 merged + deployed. fix/eld-tab-style-normalize.
350 | Packet 2 Phase A | #04-Block-AB | Internal language comprehensive scrub (9 locations) | DONE | DONE |  |  |  |  | PR #357 merged + deployed. fix/internal-language-comprehensive-scrub.
▼ Packet 2 Phase B — P0 Sub-Nav Fixes
351 | Packet 2 Phase B | #05-Block-U | FUEL sub-nav routing fix (all 8 sub-tabs broken) | PENDING | DONE |  |  |  |  | P0. Branch: fix/fuel-subnav-routing. / reconciled 2026-06-15 DONE-DRIFT: #817 FuelPlannerHome distinct routes
352 | Packet 2 Phase B | #06-Block-V | DISPATCH sub-nav routing fix (all 5 sub-tabs broken) | PENDING | DONE |  |  |  |  | P0. Branch: fix/dispatch-subnav-routing. / reconciled 2026-06-15 DONE-DRIFT: #818 dispatch subnav pages (AtRisk/Detention/...)
▼ Packet 1 Phase C — Vehicle/Trailer/Parts/Services/Reefer
353 | Packet 1 Phase C | #07-Block-P | Best Bay Logsitcis customer name typo fix | PENDING | PENDING |  |  |  |  | P3. Branch: fix/customer-typo-best-bay-logistics. 1 migration row UPDATE.
354 | Packet 1 Phase C | #08-Block-A | Migration ledger cleanup (187 migrations drift) | PENDING | DONE |  |  |  |  | Foundation. Branch: chore/migration-ledger-cleanup. / reconciled 2026-06-15 DONE-DRIFT: #177 startup-drift-guard + #878 re-home migrations
355 | Packet 2 Phase C | #09-Block-AA | Seed-test-driver users archive (4 rows @seed.invalid) | PENDING | DONE |  |  |  |  | P1. Branch: fix/users-seed-test-purge-v2. Supersedes Block S. / reconciled 2026-06-15 DONE-DRIFT: #400/#910 mig 0320 archive_test_seed_data
356 | Packet 1 Phase C | #10-Block-B | Vehicle Profile page (Fleet rows clickable) | DONE | DONE |  |  |  |  | SUPERSEDED-AND-SHIPPED by Block-11 PR #362 (SHA 5eefda5) + Block-12 PR #363 (SHA bbc13fc) + hotfixes PR #364 (a1ddfba) + PR #365 (da0d12e). Full vehicle profile live 2026-06-02.
357 | Packet 1 Phase C | #11-Block-C | Trailer Profile page (with TYPE field) | PENDING | DONE |  |  |  |  | HIGH VALUE. Branch: feat/trailer-profile-page. / reconciled 2026-06-15 DONE-DRIFT: #368/#404 TrailerProfilePage.tsx
358 | Packet 1 Phase C | #12-Block-D | Parts Catalog by brand research (Peterbilt/Freightliner/Mack… | PENDING | DONE |  |  |  |  | HIGH VALUE. Branch: feat/parts-catalog-by-brand. / reconciled 2026-06-15 DONE-DRIFT: #407 MaintenancePartsCatalog.tsx
359 | Packet 1 Phase C | #13-Block-E | Services Catalog + ETA engine (Samsara mileage + 12k mi/mo d… | PENDING | PENDING |  |  |  |  | HIGH VALUE. Branch: feat/services-catalog-eta-engine.
360 | Packet 1 Phase C | #14-Block-F | Reefer Hours tracking (Samsara 15-min polls) | PENDING | PENDING |  |  |  |  | HIGH VALUE. Branch: feat/reefer-hours-tracking.
▼ Packet 2 Phase D — P1 Bug Cleanup + KPI Consistency
361 | Packet 2 Phase D | #15-Block-Y | HOME Driver day-summaries red error fix | DONE | DONE |  |  |  |  | PR #379 SHA 5c9a9e1 merged + deployed 8:22 PM CST 6/2. Rebased onto f94d54a → d06722f → merged at 5c9a9e1. A7.
362 | Packet 2 Phase D | #16-Block-AJ | Samsara live positions on dispatch map fix | DONE | DONE |  |  |  |  | PR #378 SHA f94d54a merged + deployed 8:02 PM CST 6/2. Migration 0315 cron-not-running fix. B6. Stale rebase a0945fb force-pushed.
363 | Packet 2 Phase D | #17-Block-AC | KPI consistency reconciliation (3 contradictions) | DONE | DONE |  |  |  |  | PR #383 SHA 585ad74 merged + deployed 9:32 PM CST 6/2. B7 = #17-Block-AC.
364 | Packet 2 Phase D | #18-Block-AK | Bank Driver Escrow counter label clarify | PENDING | DONE |  |  |  |  | P3. Branch: fix/bank-driver-escrow-counter-clarify. / reconciled 2026-06-15 DONE-DRIFT: #395 escrow counter label
365 | Packet 2 Phase D | #19-Block-X | HOME Record Expense modal consistency | PENDING | PENDING |  |  |  |  | P2. Branch: fix/home-record-expense-modal-consistency.
▼ Packet 1 Phase E — Catalog Purge + URL/Header Normalize
366 | Packet 1 Phase E | #20-Block-G | Catalog stub purge — replace 34 stubs | PENDING | DONE |  |  |  |  | P1. Branch: feat/lists-catalog-stub-purge. / reconciled 2026-06-15 DONE-DRIFT: #518 verify-no-stub-catalog-pages.mjs
367 | Packet 1 Phase E | #21-Block-H | URL routing normalize (underscore->hyphen 301) | PENDING | DONE |  |  |  |  | P0. Branch: fix/lists-url-routing-normalize. / reconciled 2026-06-15 DONE-DRIFT: #389/#819 routes/url-canonicalize.ts (wired App.tsx)
368 | Packet 1 Phase E | #22-Block-I | LISTS hub header counts fix (6 of 8 wrong) | PENDING | DONE |  |  |  |  | P1. Branch: fix/lists-header-counts-from-source. / reconciled 2026-06-15 DONE-DRIFT: #393 lists-counts.routes.ts
369 | Packet 1 Phase E | #23-Block-J | Equipment Types deduplication (DRY-VAN/DRY_VAN) | PENDING | DONE |  |  |  |  | P0. Branch: fix/equipment-types-dedup. / reconciled 2026-06-15 DONE-DRIFT: #391 mig 0318 equipment_types_canonical_dedup
370 | Packet 1 Phase E | #24-Block-K | Classes data quality remediation | PENDING | PENDING |  |  |  |  | P2. Branch: fix/acct-classes-data-quality.
371 | Packet 2 Phase E | #25-Block-AL | Classes bulk-edit UI + COA cleanup (expanded K) | PENDING | PENDING |  |  |  |  | P2. Branch: fix/acct-classes-map-visible-cleanup.
▼ Packet 1+2 Phase F — Integration Sync Restoration
372 | Packet 1 Phase F | #26-Block-L | QBO bidirectional sync drift fix | PENDING | DONE |  |  |  |  | P1. Branch: fix/qbo-sync-bidirectional-drift-fix. / reconciled 2026-06-15 DONE-DRIFT: master-data PUSH #192/#194/#195/#197 + PULL #500/#501/#503 (invoice/bill PULL parked row 680)
373 | Packet 2 Phase F | #27-Block-AM | Loves card sync restore | PENDING | DONE |  |  |  |  | P1. Branch: fix/fuel-loves-sync-restore-v2. Supersedes Block M. / reconciled 2026-06-15 DONE-DRIFT: #399 cron/loves-card-import.cron.ts
374 | Packet 2 Phase F | #28-Block-AN | Plaid sync restore (root cause + display) | PENDING | DONE |  |  |  |  | P1. Branch: fix/bank-plaid-sync-restore. Supersedes Block R. / reconciled 2026-06-15 DONE-DRIFT: #402 cron/plaid-daily-sync.ts
375 | Packet 1 Phase F | #29-Block-O | Customer/vendor default classifications cleanup | PENDING | DONE |  |  |  |  | P2. Branch: fix/customer-vendor-default-classifications. / reconciled 2026-06-15 DONE-DRIFT: #401 mig 0325 clear_default_classifications
▼ Packet 1+2 Phase G — Write Flow Enables
376 | Packet 1 Phase G | #30-Block-Q | DOCS write flow enable (Upload Document) | PENDING | PENDING |  |  |  |  | P1. Branch: feat/docs-write-flow-enable.
377 | Packet 2 Phase G | #31-Block-AP | MAINT Settings write enable (PM intervals + vendor defaults) | PENDING | DONE |  |  |  |  | P2. Branch: feat/maint-settings-write-enable. / reconciled 2026-06-15 DONE-DRIFT: pm-schedule.routes.ts (maintenance)
378 | Packet 2 Phase G | #32-Block-AR | Factoring profile edit flow (11 empty fields) | PENDING | DONE |  |  |  |  | P2. Branch: feat/fact-profile-edit-flow. / reconciled 2026-06-15 DONE-DRIFT: #904 factoring suite
379 | Packet 2 Phase G | #33-Block-Z | Driver CDL expires + Hire date fields backfill | PENDING | PENDING |  |  |  |  | P2. Branch: feat/driver-fields-backfill.
380 | Packet 2 Phase G | #34-Block-AG | 425C profile completeness guard | PENDING | DONE |  |  |  |  | P2. Branch: feat/425c-profile-completeness-guard. / reconciled 2026-06-15 DONE-DRIFT: components/form-425c + api/form425c.ts
▼ Packet 2 Phase H — Data Cleanup
381 | Packet 2 Phase H | #35-Block-AQ | Driver Safety pseudo-user cleanup | PENDING | DONE |  |  |  |  | P2. Branch: fix/driver-safety-pseudo-user-cleanup. / reconciled 2026-06-15 DONE-DRIFT: #397 driver-safety pseudo-user filter
382 | Packet 2 Phase H | #36-Block-AI | User LAST LOGIN populate on session create | PENDING | DONE |  |  |  |  | P3. Branch: fix/user-last-login-populate. / reconciled 2026-06-15 DONE-DRIFT: #394 users.last_login_at populate
383 | Packet 2 Phase H | #37-Block-AO | MAINT PM Countdown seed (87 units × 4 categories) | PENDING | PENDING |  |  |  |  | P2. Branch: feat/maint-pm-countdown-seed. Requires Block E.
▼ Packet 2 Phase I — Help / SAFETY Verify / Modal Audit
384 | Packet 2 Phase I | #38-Block-AF | Help articles backfill (8 modules missing) | PENDING | PENDING |  |  |  |  | P2. Branch: feat/help-articles-backfill.
385 | Packet 2 Phase I | #39-Block-AH | SAFETY dropdown groups verify (8-10 groups × ~21 sub-tabs) | PENDING | DONE |  |  |  |  | P2. Branch: docs/safety-dropdown-groups-inventory. / reconciled 2026-06-15 DONE-DRIFT: safety module locked-complete per CLAUDE.md §7 (Wave-4 674)
386 | Packet 2 Phase I | #40-Block-AS | Generic modal X close audit (all modals) | PENDING | DONE |  |  |  |  | P2. Branch: chore/generic-modal-x-close-audit. / reconciled 2026-06-15 DONE-DRIFT: #398/#916 modal X-close audit
▼ Packet 2 Phase J — Master Dispatch 5-19 Reconcile + Audit Close
387 | Packet 2 Phase J | #41-MD-5-19-RECO… | Master Dispatch 5-19 cross-check vs shipped+Packet 1+2 | PENDING | PENDING |  |  |  |  | Likely 30-40% redundant. Drop redundant, queue valid remainder.
388 | Packet 2 Phase J | #42-Block-AT | Comprehensive audit script + close 2026-06-01 ticket | PENDING | PENDING |  |  |  |  | P2. Branch: chore/comprehensive-audit-final-v2. Supersedes Block T.
▼ Monday 2026-06-02 — Phase K — Vehicle Profile Capability Wave + P0 Hotfixes
389 | Monday 6-2 — Capability Ca… | #43-Block-7-FLEE… | Fleet row click → /fleet/units/:uuid + counter binding | DONE | DONE |  |  |  |  | PR #358 SHA 7d4ec90 merged + deployed.
390 | Monday 6-2 — Capability Ca… | #44-Block-8-SERV… | Widened status filter + COALESCE bucket fallback + CI guard | DONE | DONE |  |  |  |  | PR #359 SHA da2d3b2 merged + deployed.
391 | Monday 6-2 — Capability Ca… | #45-Block-9-NAV-… | 4 dead bill paths wired + Settlements/Master Data subnavs + … | DONE | DONE |  |  |  |  | PR #360 SHA 6d5783c merged + deployed.
392 | Monday 6-2 — Capability Ca… | #46-Block-10-TOO… | block-ready skip duplicate verify (702s→487s) | DONE | DONE |  |  |  |  | PR #361 SHA 290f840 merged + deployed.
393 | Monday 6-2 — Vehicle Profi… | #47-Block-11-VEH… | Identity header / Status / Plates / Live telemetry / Driver … | DONE | DONE |  |  |  | samePR#362→#35… | PR #362 SHA 5eefda5 merged + deployed.
394 | Monday 6-2 — Vehicle Profi… | #48-Block-12-VEH… | Maintenance snapshot / Compliance / Reefer / Financial P&L /… | DONE | DONE |  |  |  |  | PR #363 SHA bbc13fc merged + deployed.
395 | Monday 6-2 — P0 Hotfix | #49-HOTFIX-VEHIC… | Migration 0291 ledger drift + 0298 samsara dedup + spurious … | DONE | DONE |  |  |  |  | PR #364 SHA a1ddfba merged + deployed. Unblocked Render preDeploy db:migrate.
396 | Monday 6-2 — P0 Hotfix | #50-HOTFIX-UNIT-… | Fix 3 bugs: (A) SAVEPOINT wrap optional queries in withCurre… | DONE | DONE |  |  |  |  | PR #365 SHA da0d12e merged + deployed. Aggregate envelope now returns 20 top-level keys.
397 | Monday 6-2 — Driver Profil… | #51-Block-13-dri… | Driver profile foundation (5 sections + 2 recs + migration 0… | DONE | DONE |  |  |  |  | SHA 9313033 merged + Render all 3 services live. Merge→prod ~20m.
398 | Monday 6-2 — Driver Profil… | #52-Block-14-dri… | Driver profile completion (6 UI sections + training records … | DONE | DONE |  |  |  |  | PR #367 SHA 30bc2fb merged + deployed 1:10 PM CST 6/2. Migration 0302.
399 | Monday 6-2 — Queue | #53-Block-15-tra… | Trailer profile foundation (mdata.equipment) + TYPE field (R… | DONE | DONE |  |  |  |  | PR #368 SHA 19ddf58 merged + deployed 1:51 PM CST 6/2. Migration 0303.
400 | Monday 6-2 — Queue | #54-Block-16-com… | Compliance dashboard (DOT/IFTA/PITA/SCT/IRP/insurance tile a… | DONE | DONE |  |  |  |  | PR #369 SHA 729d283 merged + deployed 3:32 PM CST 6/2. Migration 0304.
401 | Monday 6-2 — Queue | #55-Block-17-not… | Notification center (in-app notifications + email digest) | DONE | DONE |  |  |  |  | PR #373 SHA 5b9d4c3 merged + deployed 6:01 PM CST 6/2. Migration 0309.
402 | Monday 6-2 — Queue | #56-Block-18-shi… | Shipper portal MVP (public-facing surface for customer load … | DONE | DONE |  |  |  |  | PR #370 SHA 4dfe61b merged + deployed 4:34 PM CST 6/2. Migrations 0306+0307.
403 | Monday 6-2 — Queue | #57-Block-19-lan… | Lane profitability heatmap (route × month × revenue / mile ×… | DONE | DONE |  |  |  |  | PR #375 SHA a8c9ca1 merged + deployed 6:37 PM CST 6/2. Migration 0311.
404 | Monday 6-2 — Queue | #58-Block-20-dea… | Deadhead optimization (suggest backhauls / multi-stop combin… | DONE | DONE |  |  |  |  | PR #372 SHA 3827e09 merged + deployed 5:40 PM CST 6/2. Migration 0308.
405 | Monday 6-2 — Queue | #59-Block-21-bor… | Border crossing wizard (USMCA documents, broker handoff, MX … | DONE | DONE |  |  |  |  | PR #376 SHA 9702e22 merged + deployed 7:06 PM CST 6/2. Migration 0313.
406 | Monday 6-2 — Queue | #60-Block-22-pre… | Predictive auto-WO from Samsara fault webhook (DTC severity … | DONE | DONE |  |  |  |  | PR #374 SHA b0762d9 merged + deployed 7:20 PM CST 6/2. Migration 0310. 4 rebases during ship.
▼ Faults Log v1 — 2026-06-02 (Jorge captured; defer until Block-22 ships)
407 | Faults Log v1 | #61-F1-FLEET-BUL… | Fleet table missing QB-style bulk-select checkbox column (mu… | DONE | DONE |  |  |  |  | PR #377 SHA dff2bdd merged + deployed 7:45 PM CST 6/2. A5 = #61-F1. No migration.
408 | Faults Log v1 | #62-F2-FLEET-TRA… | Fleet table only shows mdata.units (trucks); trailers in mda… | DONE | DONE |  |  |  |  | PR #380 SHA b531b89 merged + deployed 8:45 PM CST 6/2. B4 = #62-F2. No migration. Stale dup #382 closed.
409 | Faults Log v1 | #63-F3-FLEET-TYP… | Fleet table missing unified view OR clickable type filters (… | IN FLIGHT | DONE | 2026-05-14 |  |  |  | CURSOR-B agent2 on feat/fleet-type-filters. B5 = #63-F3 dispatched 9:25 PM CST 6/2. / merged #63(d7b603f18)
410 | Faults Log v1 | #64-F4-EDIT-VEHI… | Edit vehicle modal surfaces only 22 of 67 mdata.units column… | DONE | DONE |  |  |  |  | PR #381 SHA fe3ee15 merged + deployed 9:22 PM CST 6/2. A6 = #64-F4. TS error at units.routes.ts:336 fixed at c745211.
411 | Faults Log v1 | #65-F5-RENDER-AU… | Render backend service auto-deploy not firing — every PR req… | DONE | DONE |  |  |  |  | RESOLVED 2026-06-02 10:30 PM CST. Render IH35-TMS Settings → Auto-Deploy = On Commit. F5 fault closed without code change.
412 | Faults Log v1 | F6-PLUS | Additional faults to be captured by Jorge after Block 14-22 … | PENDING | PENDING |  |  |  |  | Placeholder.
▼ Phase N — Tuesday Night Wave 2026-06-02 EVENING (after 16-block monster session)
413 | Phase N — Tuesday Night Wa… | #66-A8-CUSTOMER-… | Fix /customers/{id}/detail 404 + billing-summary 500 | DONE | DONE |  |  |  |  | PR #386 SHA 33187c4 merged + deployed LIVE ~9:50 PM CST
414 | Phase N — Tuesday Night Wa… | #67-A9-MODAL-DOU… | Modal doubling pattern fix (WO Details + Customer Edit) | DONE | DONE |  |  |  |  | PR #387 SHA dc26c49 merged + deployed LIVE ~10:50 PM CST
415 | Phase N — Tuesday Night Wa… | #68-A10-URL-ROUT… | URL routing normalize: underscore → 301 → hyphen | DONE | DONE |  |  |  |  | PR #389 SHA 59474f8 merged + deployed LIVE 11:08 PM CST
416 | Phase N — Tuesday Night Wa… | #69-A11-EQUIPMEN… | Equipment types canonical dedup (DRY-VAN/DRY_VAN unified) | DONE | DONE |  |  |  |  | PR #391 SHA 63d5a49 merged + deployed LIVE 11:35 PM CST · migration 0318
417 | Phase N — Tuesday Night Wa… | #70-A12-LISTS-HU… | LISTS hub header counts via useModuleCount() live endpoints | DONE | DONE |  |  |  |  | PR #393 SHA 73cc7fb merged + deployed LIVE ~12:00 AM CST
418 | Phase N — Tuesday Night Wa… | #71-B8-QBO-CUSTO… | QBO customers sync push (2,655 records, 60s scheduler) | DONE | DONE |  |  |  |  | PR #388 SHA e158f57 merged + deployed LIVE ~10:50 PM CST · migration 0319
419 | Phase N — Tuesday Night Wa… | #72-B9-QBO-VENDO… | QBO vendors sync push (2,744 records, shared rate-limit) | DONE | DONE |  |  |  |  | PR #390 SHA 54f5860 merged + deployed LIVE 11:29 PM CST · migration 0321
420 | Phase N — Tuesday Night Wa… | #73-B10-QBO-COA-… | QBO chart of accounts sync push (1,282 records, parent-first… | DONE | DONE |  |  |  |  | PR #392 SHA b38ba2c merged + deployed LIVE ~12:00 AM CST · migration 0323
421 | Phase N — Tuesday Night Wa… | #74-B11-USER-LAS… | User last_login_at populate on session create | DONE | DONE |  |  |  |  | PR #394 SHA f370ad2 merged + deployed LIVE ~12:20 AM CST
▼ Phase N — Tuesday Night Wave (continued)
422 | Phase N — Tuesday Night Wa… | #75-A13-BANKING-… | Banking driver escrow counter label clarify | DONE | DONE |  |  |  |  | PR #395 SHA fa22868 merged + deployed LIVE 12:27 AM CST
▼ Wave 1 Queued (paste-ready in /mnt/user-data/outputs/)
423 | Phase N — Tuesday Night Wa… | #76-A14-WAVE1-HO… | Home Record Expense → modal (not navigate) | IN FLIGHT | DONE |  |  |  |  | DONE — merged #396 (A14 Record Expense modal)
424 | Phase N — Tuesday Night Wa… | #77-A15-WAVE1-GE… | Audit all *Modal.tsx for X close | PENDING | DONE |  |  |  |  | P2 · branch chore/generic-modal-x-close-audit / reconciled 2026-06-15 DONE-DRIFT: #398 A15 modal X-close
425 | Phase N — Tuesday Night Wa… | #78-A16-WAVE1-TE… | Archive TEST-DRIVER/TEST-CUSTOMER/seed-* | PENDING | DONE |  |  |  |  | P2 · branch fix/test-seed-data-archive · mig 0320 / reconciled 2026-06-15 DONE-DRIFT: #400 A16 archive test/seed
426 | Phase N — Tuesday Night Wa… | #79-B12-WAVE1-DR… | Filter Safety Safety pseudo-user | IN FLIGHT | DONE |  |  |  |  | DONE — merged #397 (B12 exclude pseudo-users)
427 | Phase N — Tuesday Night Wa… | #80-B13-WAVE1-FU… | Restore Loves card sync | PENDING | DONE |  |  |  |  | P1 · branch fix/fuel-loves-sync-restore-v2 / reconciled 2026-06-15 DONE-DRIFT: #399 B13 Loves cron
428 | Phase N — Tuesday Night Wa… | #81-B14-WAVE1-CU… | Clear Late-pay/Medium auto-applied defaults | PENDING | PENDING |  |  |  |  | P2 · branch fix/customer-vendor-default-classifications · mig 0325
429 | Phase N — Tuesday Night Wa… | #82-B15-WAVE1-BA… | Restore Amex + Wells Fargo Plaid sync | PENDING | DONE |  |  |  |  | P1 · branch fix/bank-plaid-sync-restore / reconciled 2026-06-15 DONE-DRIFT: #402 B15 Plaid sync
▼ Wave 2 Queued (Wed Pre-Dawn — files in outputs/)
430 | Phase N+ — Wave 2 (Wed Pre… | #83-A17-WAVE2-DR… | Wire 5/5 drivers sub-catalogs | PENDING | DONE |  |  |  |  | P1 · branch feat/drivers-catalog-real-data-wire / reconciled 2026-06-15 DONE-DRIFT: #403/#482 drivers catalogs reference.*
431 | Phase N+ — Wave 2 (Wed Pre… | #84-A18-WAVE2-NA… | Wire 5/5 Names Master pools | PENDING | DONE |  |  |  |  | P1 · branch feat/names-master-catalog-real-data-wire / reconciled 2026-06-15 DONE-DRIFT: #408 names master navigator
432 | Phase N+ — Wave 2 (Wed Pre… | #85-A19-WAVE2-RE… | Reefer hours tracking + WO auto-create | PENDING | PENDING |  |  |  |  | P1 · branch feat/reefer-hours-separate-tracking · mig 0327
433 | Phase N+ — Wave 2 (Wed Pre… | #86-B16-WAVE2-TR… | Trailer Profile + 5 statuses + TYPE | PENDING | DONE |  |  |  |  | P1 · branch feat/trailer-profile-page-statuses-type · mig 0329 / reconciled 2026-06-15 DONE-DRIFT: #404 trailer profile part 2
434 | Phase N+ — Wave 2 (Wed Pre… | #87-B17-WAVE2-MA… | Parts catalog seeded 50+ by brand | PENDING | DONE |  |  |  |  | P1 · branch feat/maint-parts-research-by-brand · mig 0331 / reconciled 2026-06-15 DONE-DRIFT: #407 B17 OEM parts templates
435 | Phase N+ — Wave 2 (Wed Pre… | #88-B18-WAVE2-SE… | Services catalog + Samsara ETAs + 12k mi/mo | PENDING | PENDING |  |  |  |  | P1 · branch feat/services-catalog-real-etas · mig 0333
▼ v23 ADDENDUM — ALL 126 PRs SHIPPED 2026-06-02 evening → 2026-06-04 evening
436
437 | Phase 7 | — | fix(ui): IH35-LANGUAGE-SCRUB comprehensive internal language… | DONE | DONE |  |  |  | samePR#357→#35… | #357
438 | Phase 7 | — | fix(maint): FLEET-CLICKABLE-COUNTERS wire row click navigati… | DONE | DONE |  |  |  | samePR#358→#38… | #358
439 | Phase 7 | — | fix(maint): SERVICE-LOCATION-ALIGNMENT widen status filter +… | DONE | DONE |  |  |  | samePR#359→#39… | #359
440 | Phase 7 | — | feat(nav): NAV-INTEGRITY-3-MODULES wire dead bill subnav + q… | DONE | DONE |  |  |  | samePR#360→#39… | #360
441 | Phase 7 | — | fix(tooling): C5 dedupe arch-design + slim pre-push to block… | DONE | DONE |  |  |  | samePR#361→#39… | #361
442 | Phase 7 | — | feat(fleet): VEHICLE-PROFILE-PART-1 Sections 1-6 + border op… | DONE | DONE |  |  |  | samePR#362→#35… | #362
443 | Phase 7 | — | feat(fleet): VEHICLE-PROFILE-PART-2 Sections 7-11 + recs 1/2… | DONE | DONE |  |  |  | samePR#363→#39… | #363
444 | Phase 7 | — | hotfix(migrations): vehicle-profile prod ledger repair + 029… | DONE | DONE |  |  |  | samePR#364→#39… | #364
445 | Phase 7 | — | hotfix(mdata): unit aggregate stability — fix all 3 P0 bugs | DONE | DONE |  |  |  | samePR#365→#39… | #365
446 | Phase 7 — Drivers | — | feat(drivers): DRIVER-PROFILE-PART-1 Sections 1-6 + default … | DONE | DONE |  |  |  |  | #366
447 | Phase 7 — Drivers | — | feat(drivers): DRIVER-PROFILE-PART-2 Sections 7-12 + border … | DONE | DONE |  |  |  | samePR#367→#39… | #367
448 | Phase 7 | — | feat(fleet): Trailer Profile Part 1 — 8 sections, aggregate … | DONE | DONE |  |  |  | samePR#368→#39… | #368
449 | Phase 7 | — | Feat/compliance dashboard | DONE | DONE |  |  |  | samePR#369→#40… | #369
450 | Phase 7 | — | Feat/shipper portal mvp | DONE | DONE |  |  |  | samePR#370→#40… | #370
451 | Phase 7 | — | feat: wire maintenance position selector to catalog | DONE | DONE |  |  |  |  | #371
452 | Phase 7 | — | feat(reports): DEADHEAD-OPTIMIZATION per-truck deadhead trac… | DONE | DONE |  |  |  | samePR#372→#40… | #372
453 | Phase 7 | — | feat(notifications): Block 17 notification center MVP | DONE | DONE |  |  |  | samePR#373→#40… | #373
454 | Phase 7 | — | feat(maintenance): predictive auto-WO from Samsara fault cod… | DONE | DONE |  |  |  | samePR#374→#40… | #374
455 | Phase 7 | — | feat(reports): add lane profitability heatmap with nightly c… | DONE | DONE |  |  |  | samePR#375→#40… | #375
456 | Phase 7 | — | Feat/border crossing wizard | DONE | DONE |  |  |  | samePR#376→#40… | #376
457 | Phase 7 | A5 | feat(fleet): A5 bulk-select checkbox column + bulk-update ro… | DONE | DONE |  |  |  | samePR#377→#40… | #377
458 | Phase 7 — Samsara | B6 | fix(samsara): B6 live positions feed restored | DONE | DONE |  |  |  | samePR#378→#36… | #378
459 | Phase 7 | A7 | fix(home): A7 driver day-summary widget — empty state + endp… | DONE | DONE |  |  |  | samePR#379→#36… | #379
460 | Phase 7 | — | Feat/fleet trailers joined into fleet table | DONE | DONE |  |  |  | samePR#380→#40… | #380
461 | Phase 7 | A6 | feat(fleet): A6 edit vehicle modal expanded to 67 columns | DONE | DONE |  |  |  | samePR#381→#41… | #381
462 | Phase 7 | — | Feat/kpi consistency reconcile | DONE | DONE |  |  |  | samePR#383→#36… | #383
463 | Phase 7 | — | Feat/kpi consistency reconcile | DONE | DONE |  |  |  |  | #384
464 | Phase 7 | — | Feat/fleet type filters | DONE | DONE |  |  |  |  | #385
465 | Phase 7 | A8 | fix(customers): repair billing-summary SQL and harden detail… | DONE | DONE |  |  |  | samePR#386→#41… | #386
466 | Phase 7 | A9 | fix(frontend): A9 modal doubling pattern — single header + n… | DONE | DONE |  |  |  | samePR#387→#41… | #387
467 | Phase 7 | B8 | feat(B8): push local QBO customers on 60s scheduler with syn… | DONE | DONE |  |  |  | samePR#388→#41… | #388
468 | Phase 7 | — | Feat/url routing normalize underscore hyphen | DONE | DONE |  |  |  | samePR#389→#41… | #389
469 | Phase 7 | — | Feat/qbo vendors sync push | DONE | DONE |  |  |  | samePR#390→#41… | #390
470 | Phase 7 | A11 | fix(catalogs): equipment types canonical dedup (A11 Block-J) | DONE | DONE |  |  |  | samePR#391→#41… | #391
471 | Phase 7 | B10 | Feat/qbo coa sync push (B10) | DONE | DONE |  |  |  | samePR#392→#42… | #392
472 | Phase 7 | A12 | fix(lists): derive hub header counts from live catalog sourc… | DONE | DONE |  |  |  | samePR#393→#41… | #393
473 | Phase 7 | B11 | Populate user last_login_at on session create (B11) | DONE | DONE |  |  |  | samePR#394→#42… | #394
474 | Phase 7 | A13 | fix(banking): clarify driver escrow counter label (A13) | DONE | DONE |  |  |  | samePR#395→#42… | #395
475 | Phase 7 | A14 | fix(home): Record Expense opens modal on HOME (A14) | DONE | DONE |  |  |  |  | #396
476 | Phase 7 | B12 | fix(driver-safety): exclude pseudo-users from driver listing… | DONE | DONE |  |  |  |  | #397
477 | Phase 7 — Chore | A15 | chore(frontend): modal X-close audit (A15) | DONE | DONE |  |  |  |  | #398
478 | Phase 7 | B13 | fix(fuel): restore Loves card sync cron and KPI status (B13) | DONE | DONE |  |  |  |  | #399
479 | Phase 7 — Audit Findings | A16 | fix(audit): archive TEST/seed rows from prod listings (A16) | DONE | DONE |  |  |  |  | #400
480 | Phase 7 | B14 | fix(mdata): archive seed-default customer/vendor classificat… | DONE | DONE |  |  |  |  | #401
481 | Phase 7 | B15 | fix(banking): restore Plaid sync timestamps and status (B15) | DONE | DONE |  |  |  |  | #402
482 | Phase 7 | A17 | feat(catalogs): wire drivers sub-catalogs to existing factor… | DONE | DONE |  |  |  |  | #403
483 | Phase 7 | B16 | feat(fleet): trailer profile part 2 gap-fill (B16) | DONE | DONE |  |  |  |  | #404
484 | Phase 7 | A17 | feat(lists): drivers catalogs canonical reference.* + archiv… | DONE | DONE |  |  |  | DUP→#482 | #405
485 | Phase 7 — Chore | A17 | chore(catalogs): deprecate redundant driver catalogs (A17.2) | DONE | DONE |  |  |  | DUP→#482 | #406
486 | Phase 7 | B17 | feat(lists): OEM parts templates reference.* (B17) | DONE | DONE |  |  |  |  | #407
487 | Phase 7 | A18 | feat(lists): names master cross-module navigator (A18) | DONE | DONE |  |  |  |  | #408
488 | Phase 7 — Safety | A23-1 | feat(safety): mount 11 unmounted route modules (A23-1) | DONE | DONE |  |  |  |  | #409
489 | Phase 7 — Safety | A23-3 | feat(safety): accidents page wire-up (A23-3) | DONE | DONE |  |  |  |  | #410
490 | Phase 7 — Safety | A23-2 | feat(safety): count and nav integrity 27/9 canonical (A23-2) | DONE | DONE |  |  |  |  | #411
491 | Phase 7 — Dispatch | B21 | feat(dispatch): triage ComingSoon legacy routes (B21-D1) | DONE | DONE |  |  |  |  | #412
492 | Phase 7 — Drivers | A17 | feat(drivers): wire mdata.drivers inline enums to reference.… | DONE | DONE |  |  |  | DUP→#482 | #413
493 | Phase 7 — Drivers | A24-2 | feat(drivers): tab/nav parity to 9-subtab canonical (A24-2) | DONE | DONE |  |  |  |  | #414
494 | Phase 7 | B24 | feat(maintenance): reconcile nav counts and remove dead CTAs… | DONE | DONE |  |  |  |  | #415
495 | Phase 7 — Drivers | A24-3 | feat(drivers): profile action bar wiring (A24-3) | DONE | DONE |  |  |  |  | #416
496 | Phase 7 — Dispatch | B21 | feat(dispatch): arch tab parity phase 1 — 3 new tabs (B21-D2… | DONE | DONE |  |  |  | DUP→#491 | #417
497 | Phase 7 — Drivers | A24-4 | feat(drivers): + Create Driver vocabulary (A24-4) | DONE | DONE |  |  |  |  | #418
498 | Phase 7 — Maintenance | B23 | feat(maint): parts unification + deprecation (B23) | DONE | DONE |  |  |  |  | #419
499 | Phase 7 — Safety | A23-4 | feat(safety): DVIR foundation — schema + PWA + office list (… | DONE | DONE |  |  |  |  | #420
500 | Phase 7 — Dispatch | B21 | feat(dispatch): book load accessorial UX (B21-D3) | DONE | DONE |  |  |  | DUP→#491 | #421
501 | Phase 7 — Maintenance | B25 | feat(maint): WO vocabulary standardize (B25) | DONE | DONE |  |  |  |  | #422
502 | Phase 7 — Safety | A23-5 | feat(safety): meetings + training wire-up (A23-5) | DONE | DONE |  |  |  |  | #423
503 | Phase 7 — Maintenance | B26 | feat(maint): trailer WO history by equipment_id (B26) | DONE | DONE |  |  |  |  | #424
504 | Phase 7 — Drivers | A24-5 | feat(drivers): Earnings & Debt tab live (A24-5) | DONE | DONE |  |  |  |  | #425
505 | Phase 7 — Dispatch | D6 | feat(dispatch): late arrivals alert fix (D6) | DONE | DONE |  |  |  |  | #426
506 | Phase 7 — Safety | A23-6 | feat(safety): canonical HOS dashboard (A23-6) | DONE | DONE |  |  |  |  | #427
507 | Phase 7 — Dispatch | D4 | feat(dispatch): planner calendar week view (D4) | DONE | DONE |  |  |  |  | #428
508 | Phase 7 — Dispatch | D5 | feat(dispatch): detention board + billing bridge (D5) | DONE | DONE |  |  |  |  | #429
509 | Phase 7 — Infra | INFRA-2 | fix(infra): defensive NULLIF wrap on RLS UUID casts (INFRA-2… | DONE | DONE |  |  |  |  | #430
510 | Phase 7 — Safety | A23-7 | feat(safety): incidents cluster — damage/interchange/cargo (… | DONE | DONE |  |  |  |  | #431
511 | Phase 7 — Infra | INFRA-1 | fix(infra): redis resilient ioredis config (INFRA-1) | DONE | DONE |  |  |  |  | #432
512 | Phase 7 — Dispatch | D7 | feat(dispatch): OCR queue page (D7) | DONE | DONE |  |  |  |  | #433
513 | Phase 7 — Safety | A23-8 | feat(safety): escrow record wire (A23-8) | DONE | DONE |  |  |  |  | #434
514 | Phase 7 — Dispatch | D8 | feat(dispatch): driver assignment optimizer (D8) | DONE | DONE |  |  |  |  | #435
515 | Phase 7 — Safety | A23-9 | feat(safety): company violations surfacing (A23-9) | DONE | DONE |  |  |  |  | #436
516 | Phase 7 — Safety | A15 | feat(safety): A15 modal compliance migration (A23-10) | DONE | DONE |  |  |  | DUP→#477 | #437
517 | Phase 7 — Dispatch | D9 | feat(dispatch): customer ETA notify (D9) | DONE | DONE |  |  |  |  | #438
518 | Phase 7 — Dispatch | D10 | feat(dispatch): POD capture + BOL generation (D10) | DONE | DONE |  |  |  |  | #439
519 | Phase 7 — Safety | A23-12 | feat(safety): integrity alert engine (A23-12) | DONE | DONE |  |  |  |  | #440
520 | Phase 7 — Safety | A23-13 | feat(safety): permits tab tracking (A23-13) | DONE | DONE |  |  |  |  | #441
521 | Phase 7 — Dispatch | D11 | feat(dispatch): settings tab (D11) | DONE | DONE |  |  |  |  | #442
522 | Phase 7 — Dispatch | D12 | feat(dispatch): secondary nav depth (D12) | DONE | DONE |  |  |  |  | #443
523 | Phase 7 — Drivers | A24-10 | feat(drivers): communication center (A24-10) | DONE | DONE |  |  |  |  | #444
524 | Phase 7 — Drivers | A24-6 | feat(drivers): audit history tab (A24-6) | DONE | DONE |  |  |  |  | #445
525 | Phase 7 — Maintenance | B27 | feat(maint): DVIR defect intake — maintenance side (B27) | DONE | DONE |  |  |  |  | #446
526 | Phase 7 — Drivers | A24-7 | feat(drivers): training records CRUD on profile (A24-7) | DONE | DONE |  |  |  |  | #447
527 | Phase 7 — Maintenance | B28 | feat(maint): PM auto-WO engine (B28) | DONE | DONE |  |  |  |  | #448
528 | Phase 7 — Drivers | A24-8 | feat(drivers): onboarding wizard multi-step (A24-8) | DONE | DONE |  |  |  |  | #449
529 | Phase 7 — Maintenance | B29 | feat(maint): vendor master unify CRUD (B29) | DONE | DONE |  |  |  |  | #450
530 | Phase 7 — Drivers | A24-9 | feat(drivers): document expiry alert engine (A24-9) | DONE | DONE |  |  |  |  | #451
531 | Phase 7 — Maintenance | B30 | feat(maint): inspections CRUD + DVIR linkage (B30) | DONE | DONE |  |  |  |  | #452
532 | Phase 7 — Maintenance | B31 | feat(maint): service history timeline (B31) | DONE | DONE |  |  |  |  | #453
533 | Phase 7 — Drivers | A24-11 | feat(drivers): PWA live data parity (A24-11) | DONE | DONE |  |  |  |  | #454
534 | Phase 7 — Drivers | A24-12 | feat(drivers): pre-hire application portal (A24-12) | DONE | DONE |  |  |  |  | #455
535 | Phase 7 — Maintenance | B32 | feat(maint): tire program tracking (B32) | DONE | DONE |  |  |  |  | #456
536 | Phase 7 — Maintenance | B34 | feat(maint): mechanic labor UX (B34) | DONE | DONE |  |  |  |  | #457
537 | Phase 7 — Maintenance | B33 | feat(maint): warranty tracking + claims (B33) | DONE | DONE |  |  |  |  | #458
538 | Phase 7 — Maintenance | B35 | feat(maint): KPI dashboard (B35) | DONE | DONE |  |  |  |  | #459
539 | Phase 7 — Maintenance | A19 | feat(maint): reefer hours tracking (A19) | DONE | DONE |  |  |  |  | #460
540 | Phase 7 — Tier 2 Audit | P8-AUDIT-BACKEND… | fix(audit): backend version tag (P8-AUDIT-BACKEND-VERSION) | DONE | DONE |  |  |  | DUP→#343 | #461
541 | Phase 7 — Tier 2 Audit | P8-AUDIT-NESTED-… | fix(audit): nested-box modal pattern (P8-AUDIT-NESTED-MODALS… | DONE | DONE |  |  |  | DUP→#337 | #462
542 | Phase 7 — Infra | INFRA-3 | fix(infra): Driver PWA StopAction DriverStop.type parity (IN… | DONE | DONE |  |  |  |  | #463
543 | Phase 7 — Tier 2 Audit | P8-AUDIT-ELD-RED… | fix(audit): /eld redirect-to-home bug (P8-AUDIT-ELD-REDIRECT… | DONE | DONE |  |  |  | DUP→#340 | #464
544 | Phase 7 — BULK Cluster | BULK-RBC | rbc: bulk select / multi-edit investigation (BULK-RBC) | DONE | DONE |  |  |  |  | #465
545 | Phase 7 — Chore | — | chore(cursor): dual-lane never-idle coordinator enforcement | DONE | DONE |  |  |  |  | #466
546 | Phase 7 — Tier 2 Audit | P8-AUDIT-DOCS-RE… | fix(audit): /docs redirect-to-home bug (P8-AUDIT-DOCS-REDIRE… | DONE | DONE |  |  |  | DUP→#341 | #467
547 | Phase 7 — Tier 2 Audit | P8-AUDIT-QBO-ARC… | fix(audit): qbo_archive notes leak to user UI (P8-AUDIT-QBO-… | DONE | DONE |  |  |  | DUP→#342 | #468
548 | Phase 7 — Tier 2 Audit | P8-AUDIT-TEST-DA… | fix(audit): archive mdata.customers test/seed rows (P8-AUDIT… | DONE | DONE |  |  |  | DUP→#339 | #469
549 | Phase 7 — Tier 2 Audit | P8-AUDIT-UNDEFIN… | fix(audit): 'undefined' in chart legend (P8-AUDIT-UNDEFINED-… | DONE | DONE |  |  |  | DUP→#344 | #470
550 | Phase 7 — Tier 2 Audit | P8-AUDIT-PROD-ST… | fix(audit): remove production stub strings (P8-AUDIT-PROD-ST… | DONE | DONE |  |  |  | DUP→#338 | #471
551 | Phase 7 — BULK Cluster | BULK-1 | feat(bulk): BULK-1 shared bulk UI components | DONE | DONE |  |  |  |  | #472
552 | Phase 7 — P0 Hotfix | P0-USERS-500 | fix(identity): P0-USERS-500 users.last_login_at column + gua… | DONE | DONE |  |  |  |  | #473
553 | Phase 7 — BULK Cluster | BULK-2 | feat(bulk): BULK-2 backend bulk-update framework | DONE | DONE |  |  |  |  | #474
554 | Phase 7 — Samsara | — | fix(samsara): webhook investigation + restoration (SMS-FIX-2… | DONE | DONE |  |  |  | samePR#475→#34… | #475
555 | Phase 7 — P0 Hotfix | P0-USERS-FIX | fix(identity): P0-USERS-FIX Users checklist + archive debug … | DONE | DONE |  |  |  |  | #477
556 | Phase 7 — BULK Cluster | BULK-3 | feat(bulk): BULK-3 vendor and customer bulk-update routes | DONE | DONE |  |  |  |  | #478
557 | Phase 7 — BULK Cluster | BULK-4 | feat(bulk): BULK-4 drivers and fleet bulk-update wiring | DONE | DONE |  |  |  |  | #479
558 | Phase 7 — Tier 2 Audit | P8-AUDIT-KPI-DRI… | fix(audit): reconcile 8 KPI drifts production vs app (P8-AUD… | DONE | DONE |  |  |  | DUP→#345 | #480
559 | Phase 7 — BULK Cluster | BULK-5 | feat(bulk): loads + invoices + bills bulk wire-up (BULK-5) | DONE | DONE |  |  |  |  | #481
560 | Phase 7 — BULK Cluster | BULK-6 | feat(bulk): BULK-6 audit filter, permission gate, CI coverag… | DONE | DONE |  |  |  |  | #482
561 | Phase 5 — Closure | P5-T5 | feat(driver-finance): settlement auto-pay (P5-T5) | DONE | DONE |  |  |  | DUP→#122 | #483
562 | Phase 5 — Closure | P5-T8 | feat(accounting): bills-with-balance dropdown (P5-T8) | DONE | DONE |  |  |  | DUP→#125 | #484
▼ v24 ADDENDUM — VERIFIED SNAPSHOT 2026-06-08 (main HEAD 7490803c3 · 749 merged PR…
▼ ADD — Shipped after v23 cutoff (verified merged + LIVE)
563 | Phase B QBO/New | Insurance Wizard | Atomic policy+bills wizard; /insurance LIVE | DONE | DONE |  |  |  |  | PR #737 merged f6600f9
564 | Phase C New Modules | Cash Flow MODULE | /cash-flow LIVE — Daily Prediction + Actual-vs-Projected | DONE | DONE |  |  |  |  | PR #757 merged 162e2735
565 | Phase 0 Platform | Anti-regression … | verify-cashflow-module + insurance-financial-writes guards | DONE | DONE |  |  |  |  | PR #755
566 | Phase A Dispatch | Block 12 DRAWER-… | Dispatch drawer wire | DONE | DONE |  |  |  |  | PR #746
567 | Phase A Dispatch | Block 1 OVERVIEW | Dispatch overview | DONE | DONE |  |  |  |  | PR #752
568 | Phase A Dispatch | Block 2 QUEUES-N… | Dispatch queues nav | DONE | DONE |  |  |  |  | PR #753 caeda1d2
569 | Phase A Dispatch | Block 3 KANBAN | Dispatch kanban | DONE | DONE |  |  |  |  | PR #751
570 | Phase A Dispatch | Block 4 ROUNDTRI… | Dispatch roundtrips | DONE | DONE |  |  |  |  | PR #756
571 | Phase A Dispatch | Block 5 LIST-TAB… | Dispatch list-table assign | DONE | DONE |  |  |  |  | PR #758
572 | Phase A Dispatch | Block 13 FINES-D… | Fines deduct | DONE | DONE |  |  |  |  | PR #762
▼ 29-Tier Program — true status (was mostly unbuilt in v23)
573 | Tier1.5 | BLOCK-02 Driver … | Driver escrow tier work | DONE | DONE |  |  |  |  | Artifact on main
574 | Tier1.5 | BLOCK-03 IFTA | IFTA tier work | DONE | DONE |  |  |  |  | Artifact on main
575 | Tier2 | BLOCK-04 Rate-Li… | Rate limiting | DONE | DONE |  |  |  |  | Artifact on main
576 | Tier2 | BLOCK-07 Paginat… | Pagination audit | DONE | DONE |  |  |  |  | Artifact on main
577 | Tier2 | BLOCK-08 Load-Te… | Load testing | DONE | DONE |  |  |  |  | Test/doc artifact present
578 | Tier2 | BLOCK-12 Destruc… | Destruct preflight | DONE | DONE |  |  |  |  | Artifact on main
579 | Tier2 | BLOCK-13 Tuning … | Tuning catalog | DONE | DONE |  |  |  |  | PR #794 (main head 7490803c3)
580 | Tier2.5 | BLOCK-16 Fuel-Ca… | Fuel card | DONE | DONE |  |  |  |  | Artifact on main
581 | Tier2.5 | BLOCK-17 W2/1099 | W2/1099 | DONE | DONE |  |  |  |  | Artifact on main
582 | Tier3 | BLOCK-18 PII Enc… | PII encryption | DONE | DONE |  |  |  |  | Artifact on main
583 | Tier3 | BLOCK-22 Ops Run… | Ops runbooks | DONE | DONE |  |  |  |  | Doc artifact present
584 | Tier2 | BLOCK-05 Circuit… | Breakers on external calls | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #800 — CI GREEN, awaiting merge / merged #800(0fcc12da9)
585 | Tier2 | BLOCK-09 E2E Pat… | Critical-path E2E tests | IN FLIGHT | DONE | 2026-06-09 |  |  |  | PR #802 — CI GREEN / merged #802(1ced9b316)
586 | Tier3 | BLOCK-20 Secrets… | Secret rotation procedure | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #806 — CI GREEN / merged #806(259f9c9f8)
587 | Tier3 | BLOCK-21 DR-Dril… | Disaster-recovery drill doc | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #807 — CI GREEN / merged #807(3b625f865)
588 | Tier3 | BLOCK-23 Degrada… | Graceful degradation paths | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #808 — CI GREEN / merged #808(c39027fca)
589 | Tier4 | BLOCK-27 Canary | Canary deploy hooks | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #810 — CI GREEN / merged #810(301d7097e)
590 | Tier4 | BLOCK-28 Vendor-… | Reduce vendor lock-in surface | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #811 — CI GREEN / merged #811(a39fa454f)
591 | Tier4 | BLOCK-29 Known-L… | Known limits register | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #813 — CI GREEN / merged #813(4223885da)
592 | Tier2 | BLOCK-10 RLS-Tes… | Cross-tenant RLS test gate | IN FLIGHT | DONE | 2026-06-09 |  |  |  | PR #801 — CI RED -1, fix before merge / merged #801(c68b2845e)
593 | Tier2 | BLOCK-11 Audit-C… | Mutation audit coverage | IN FLIGHT | PENDING |  |  |  |  | STILL PENDING — PR #803 never merged; mutation-audit-coverage block unshipped (spine emit covered separately via #886/#889/#890/#901)
594 | Tier2.5 | BLOCK-14 Mexico-… | Mexico operations | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #804 — CI RED -3, fix before merge / merged #804(1fcd67364)
595 | Tier2.5 | BLOCK-15 Mechani… | Internal mechanic shop | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #805 — CI RED -3, fix before merge / merged #805(1007d9c92)
596 | Tier4 | BLOCK-26 Partiti… | Table partitioning | IN FLIGHT | DONE | 2026-06-09 |  |  |  | PR #809 — CI RED -2, fix before merge / merged #809(a67a3ef7e)
597 | Tier1.5 | BLOCK-01 Depreci… | Fixed-asset depreciation schedule + posting | PENDING | PENDING |  |  |  |  | No PR yet — NOT dispatched
598 | Tier2 | BLOCK-06 Outbox-… | Dead-letter recovery for outbox | NEEDS CONFIRM | DONE | 2026-05-22 |  |  | samePR#174→#29… | Outbox work exists (#174/#49); dedicated DLQ block unclear / merged #174(20d0833ed), #49(b2898e415)
599 | Tier3 | BLOCK-19 Audit-H… | Tamper-evident audit hash chain | PENDING | PENDING |  |  |  |  | No PR yet — NOT dispatched
600 | Tier3.5 | BLOCK-24 1099-An… | Annual 1099 generation | PENDING | PENDING |  |  |  |  | No PR yet — NOT dispatched
601 | Tier3.5 | BLOCK-25 Consoli… | Multi-entity financial consolidation | PENDING | PENDING |  |  |  |  | No PR yet — NOT dispatched
▼ Closure V2 — were manifest stubs in v23; now real builds in flight
602 | Closure | CLOSURE-10 maint… | Full parts catalog impl | IN FLIGHT | DONE | 2026-06-09 |  |  |  | PR #798 — CI RED -3 / merged #798(9dff6b749)
603 | Closure | CLOSURE-11 maint… | Full maintenance services impl | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #799 — CI GREEN / merged #799(92dabde3f)
604 | Closure | CLOSURE-12 payro… | Full payroll integration impl | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #795 — CI GREEN / merged #795(d6ee890b1)
605 | Closure | CLOSURE-13 USMCA… | 3rd-carrier USMCA | IN FLIGHT | DONE | 2026-06-08 |  |  |  | PR #797 — CI RED -1 / merged #797(44bf98543)
606 | Closure | CLOSURE-16 | Real impl | DONE | DONE |  |  |  |  | PR #793
▼ Accounting Integrity (5) — true status
607 | AcctIntegrity | AI-1 Period-lock… | Snapshot lock exists (0218); CLOSED-PERIOD LEDGER-WRITE LOCK… | PARTIAL | PARTIAL |  |  |  |  | Snapshot lock exists; ledger-write lock still required
608 | AcctIntegrity | AI-2 Recon cron | Recon services exist; scheduled wrapper TBD | PARTIAL | PARTIAL |  |  |  |  | Scheduled wrapper TBD
609 | AcctIntegrity | AI-3 Daily probe… | Safety cron exists; FINANCIAL probes MISSING | PARTIAL | PARTIAL |  |  |  |  | Financial probes still missing
610 | AcctIntegrity | AI-4 Periods ini… | Periods initialization | MISSING | MISSING |  |  |  |  | Bookkeeper-gated
611 | AcctIntegrity | AI-5 Role bindin… | Routes + UI + 0223 exist (seed TBD) | DONE | DONE |  |  |  |  | Seed TBD
▼ CA Series — QBO Parity
612 | QBO Parity | CA-04 New/Edit d… | New/Edit account drawer (number optional, is_locked, opening… | IN FLIGHT | DONE |  |  |  |  | DONE — merged #815 (acct-ca04 Account Drawer; was the recorded gate-violation self-merge)
613 | QBO Parity | CA-05 Account re… | Per-account register (running balance ledger) | PENDING | PENDING |  |  |  |  | After CA-04
614 | QBO Parity | CA-06 Audit hist… | Account audit history tab | PENDING | PENDING |  |  |  |  | After CA-04/05
615 | GAP | GAP-76 Deadhead … | Deadhead mile optimizer | IN FLIGHT | DONE |  |  |  |  | DONE — merged #844 (GAP-76 deadhead optimizer; original #812 was closed/superseded)
▼ BLOCKS EXECUTION ORDER — WAVE 0 — IN FLIGHT NOW (merge green, fix red)
616 | Wave 0 | TIER29 Known-Lim… | Doc: known limits register | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#813→#59… | PR #813 — GREEN — order 1 / merged #813(4223885da)
617 | Wave 0 | TIER28 Vendor-Lo… | Reduce vendor lock-in surface | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#811→#59… | PR #811 — GREEN — order 2 / merged #811(a39fa454f)
618 | Wave 0 | TIER27 Canary | Canary deploy hooks | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#810→#58… | PR #810 — GREEN — order 3 / merged #810(301d7097e)
619 | Wave 0 | TIER23 Degradati… | Graceful degradation paths | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#808→#58… | PR #808 — GREEN — order 4 / merged #808(c39027fca)
620 | Wave 0 | TIER21 DR-Drill | Disaster-recovery drill doc | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#807→#58… | PR #807 — GREEN — order 5 / merged #807(3b625f865)
621 | Wave 0 | TIER20 Secrets-R… | Secret rotation procedure | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#806→#58… | PR #806 — GREEN — order 6 / merged #806(259f9c9f8)
622 | Wave 0 | BLOCK09 E2E Path… | Critical-path E2E tests | IN FLIGHT | DONE | 2026-06-09 |  |  | DUP→#585 | PR #802 — GREEN — order 7 / merged #802(1ced9b316)
623 | Wave 0 | BLOCK05 Circuit-… | Breakers on external calls | IN FLIGHT | DONE | 2026-06-08 |  |  | DUP→#584 | PR #800 — GREEN — order 8 / merged #800(0fcc12da9)
624 | Wave 0 | CLOSURE-11 maint… | Full maintenance services impl | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#799→#60… | PR #799 — GREEN — order 9 / merged #799(92dabde3f)
625 | Wave 0 | CLOSURE-12 payro… | Full payroll integration impl | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#795→#60… | PR #795 — GREEN — order 10 / merged #795(d6ee890b1)
626 | Wave 0 | BLOCK11 Audit-Co… | Mutation audit coverage | IN FLIGHT | PENDING |  |  |  | DUP→#593 | STILL PENDING — #803 unmerged (DUP of #593)
627 | Wave 0 | BLOCK10 RLS-Test… | Cross-tenant RLS test gate — fix CI | IN FLIGHT | DONE | 2026-06-09 |  |  | DUP→#592 | PR #801 — RED -1 — order 12 / merged #801(c68b2845e)
628 | Wave 0 | CLOSURE-13 USMCA… | 3rd-carrier USMCA — fix CI | IN FLIGHT | DONE | 2026-06-08 |  |  | DUP→#605 | PR #797 — RED -1 — order 13 / merged #797(44bf98543)
629 | Wave 0 | TIER26 Partition | Table partitioning — fix CI | IN FLIGHT | DONE | 2026-06-09 |  |  | samePR#809→#59… | PR #809 — RED -2 — order 14 / merged #809(a67a3ef7e)
630 | Wave 0 | TIER14 Mexico-Op… | Mexico operations — fix CI | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#804→#59… | PR #804 — RED -3 — order 15 / merged #804(1fcd67364)
631 | Wave 0 | TIER15 Mechanic-… | Internal mechanic shop — fix CI | IN FLIGHT | DONE | 2026-06-08 |  |  | samePR#805→#59… | PR #805 — RED -3 — order 16 / merged #805(1007d9c92)
632 | Wave 0 | CLOSURE-10 maint… | Full parts catalog impl — fix CI | IN FLIGHT | DONE | 2026-06-09 |  |  | samePR#798→#60… | PR #798 — RED -3 — order 17 / merged #798(9dff6b749)
633 | Wave 0 | GAP-76 Deadhead … | Deadhead mile optimizer | IN FLIGHT | DONE |  |  |  | DUP→#615 | DONE — merged #844 (DUP of #615)
▼ WAVE 1 — TIER GAPS NOT YET DISPATCHED (financial safety)
634 | Wave 1 | BLOCK-01 Depreci… | Fixed-asset depreciation schedule + posting | PENDING | PENDING |  |  |  | DUP→#597 | Order 19
635 | Wave 1 | BLOCK-19 Audit-H… | Tamper-evident audit hash chain | PENDING | PENDING |  |  |  | DUP→#599 | Order 20
636 | Wave 1 | BLOCK-24 1099-An… | Annual 1099 generation | PENDING | PENDING |  |  |  | DUP→#600 | Order 21
637 | Wave 1 | BLOCK-25 Consoli… | Multi-entity financial consolidation | PENDING | PENDING |  |  |  | DUP→#601 | Order 22
638 | Wave 1 | BLOCK-06 Outbox-… | Confirm/add dead-letter recovery for outbox | NEEDS CONFIRM | NEEDS CONFIRM |  |  |  |  | still pending — outbox DLQ unconfirmed; #174 did partial outbox work (BLOCK-06)
▼ WAVE 2 — ACCOUNTING INTEGRITY (make it QuickBooks-safe)
639 | Wave 2 | AI-1b Closed-per… | The real gap | PENDING | PENDING |  |  |  |  | Order 24
640 | Wave 2 | AI-3b Financial … | Unbalanced JE / orphan bill / orphan payment in existing cro… | PENDING | PENDING |  |  |  |  | Order 25
641 | Wave 2 | AI-4 Periods ini… | Bookkeeper-gated | PENDING | PENDING |  |  |  | DUP→#610 | Order 26
642 | Wave 2 | AI-2b Recon cron… | Confirm-or-add | PENDING | PENDING |  |  |  |  | Order 27
▼ WAVE 3 — CA + DISPATCH FRONTIER
643 | Wave 3 | CA-04 New/Edit d… | Number optional, is_locked, opening balance | IN FLIGHT | DONE |  |  |  | DUP→#612 | DONE — merged #815 (DUP of #612)
644 | Wave 3 | CA-05 Per-accoun… | Running balance ledger | PENDING | PENDING |  |  |  |  | Order 29
645 | Wave 3 | CA-06 Account au… | Audit history | PENDING | PENDING |  |  |  |  | Order 30
646 | Wave 3 | Block 8 Cross-Bo… | Customs + compliance gate | PENDING | PENDING |  |  |  |  | Order 31
647 | Wave 3 | Driver Hub page | Requests / Communications / Live data | PENDING | DONE |  |  |  |  | Order 32 / matched merged PR by Task-ID
648 | Wave 3 | Sidebar-V2 (23-a… | +driver-hub #5, +cash-flow #10, drivers→Driver Profile #7 | PENDING | PENDING |  |  |  |  | Order 33
649 | Wave 3 | Block 16 Density… | Density + nav correction (preview-gated, last) | PENDING | PENDING |  |  |  |  | Order 34
▼ WAVE 4 — v23 FEATURE BACKLOG · RECONCILED vs LIVE CODE 2026-06-14 (col5=orig claim, col6=verified verdict, col7=evidence)
650 | Wave 4 | Block U FUEL sub… | 8 tabs all render Planner — P0 | PENDING | DONE | FuelPlannerHome.tsx renders distinct content per tab (home/planner/relay/settings/expense_map/history/loves/compliance) — stale claim |  |  |  | Order 35
651 | Wave 4 | Block V DISPATCH… | 5 tabs render hub — P0 | PENDING | DONE | each /dispatch route → distinct page (AssignmentHistory/AtRisk/Detention/Border/Late/Geofences/Pod/Ocr) — stale claim |  |  |  | Order 36
652 | Wave 4 | Block H URL unde… | P0 | PENDING | DONE | url-canonicalize.ts wired App.tsx:8 + tests, PR #389 (safe: redirects only known hyphen routes) |  |  |  | Order 37
653 | Wave 4 | Block J Equipmen… | DRY-VAN/DRY_VAN — P0 | PENDING | DONE | DATA-MUT shipped: mig 0318 dedup→archive, PR #391 |  |  |  | Order 38
654 | Wave 4 | Block C Trailer … | HIGH | PENDING | DONE | TrailerProfilePage.tsx route /fleet/trailers/:id |  |  |  | Order 39
655 | Wave 4 | Block D Parts Ca… | HIGH | PENDING | DONE | MaintenancePartsCatalog.tsx + OemPartsCatalog.tsx + InventoryPartsStockPage |  |  |  | Order 40
656 | Wave 4 | Block E Services… | Samsara mi + 12k/mo — HIGH | PENDING | PARTIAL | service intervals exist (eta-calculator.ts, 12k default); NO live Samsara mileage ingest cron |  |  |  | Order 41
657 | Wave 4 | Block F Reefer H… | 15-min polls — HIGH | PENDING | DONE | reefer-hours tables/routes/UI (mig 0366) + NOW a 15-min poller: cron/reefer-hours-poll.cron.ts schedules */15 per active Samsara-enabled tenant → ingestReeferHoursFromSamsaraForCompany (env-gated ENABLE_REEFER_HOURS_POLL_CRON, audited, +test). Auto-mode block F |  |  |  | Order 42
658 | Wave 4 | Block G Catalog … | 34 stubs — P1 | PENDING | DONE | 0 real stubs; 60 catalog pages implemented; 27 grep hits were TODO/placeholder false-positives in working pages; real stub routes purged #518 + CI guard verify:no-stub-catalog-pages (supersedes prior PARTIAL) |  |  |  | Order 43
659 | Wave 4 | Block I LISTS he… | 6/8 wrong — P1 | PENDING | DONE | lists-counts.routes.ts + useModuleCount.ts, PR #393 |  |  |  | Order 44
660 | Wave 4 | Block L QBO bidi… | COA/cust/vend local-only — P1 | PENDING | DONE | Master data fully bidirectional: PULL #500/#501/#503 + PUSH #192/#194/#195/#197 (accounts/customers/vendors/items); invoices/bills push-only #199/#201 by design. Invoice/bill PULL + conflict-resolution UI OUT of scope → spun out as QBO-INVOICE-BILL-PULL (row 680) |  |  |  | Order 45
661 | Wave 4 | Block AM Loves c… | P1 | PENDING | DONE | PR #399 (loves-card-import cron + status) |  |  |  | Order 46
662 | Wave 4 | Block AN Plaid s… | Amex/Wells — P1 | PENDING | DONE | PR #402 (plaid-transactions-sync + status) |  |  |  | Order 47
663 | Wave 4 | Block Q DOCS upl… | P1 | PENDING | PARTIAL | backend attachments.routes.ts + R2 done; NO frontend upload UI |  |  |  | Order 48
664 | Wave 4 | Block AA Archive… | P1 | PENDING | DONE | DATA-MUT shipped: mig 0320 test-seed archive, PR #400/#910 |  |  |  | Order 49
665 | Wave 4 | Block AP MAINT s… | P2 | PENDING | DONE | pm-schedule.routes.ts + PmSchedulePage.tsx |  |  |  | Order 50
666 | Wave 4 | Block AR Factori… | P2 | PENDING | DONE | FIN: PR #904, full factoring/ dir (packet/reserve/Faro-CSV) |  |  |  | Order 51
667 | Wave 4 | Block Z Driver C… | CSV — P2 | PENDING | PARTIAL | DATA-MUT: parseDriverRosterCsv internal-only (backfill); no user import route |  |  |  | Order 52
668 | Wave 4 | Block AG 425C pr… | P2 | PENDING | DONE | Form425CHome.tsx (TX Form 425C) + api/form425c.ts |  |  |  | Order 53
669 | Wave 4 | Block K/AL Class… | P2 | PENDING | PARTIAL | ClassesCatalog read view; bulk-edit/write path incomplete |  |  |  | Order 54
670 | Wave 4 | Block O Customer… | P2 | PENDING | DONE | DATA-MUT shipped: mig 0325, PR #401 (default-classification cleanup) |  |  |  | Order 55
671 | Wave 4 | Block AQ 'Safety… | P2 | PENDING | DONE | PR #397 (driver-safety pseudo-user query filter) |  |  |  | Order 56
672 | Wave 4 | Block AO MAINT P… | Needs Block E — P2 | PENDING | PARTIAL | pm-auto-engine cron registered; depends on Block E service intervals |  |  |  | Order 57
673 | Wave 4 | Block AF Help ar… | 8 modules — P2 | PENDING | PARTIAL | helpCenterContent.ts has 12 articles; ~8 modules still missing content |  |  |  | Order 58
674 | Wave 4 | Block AH SAFETY … | P2 | PENDING | DONE | LOCKED-PAGE: safety module complete + locked per CLAUDE.md §7 (no further adds) |  |  |  | Order 59
675 | Wave 4 | Block AS Generic… | P2 | PENDING | DONE | PR #398/#916 (modal X-close audit standardized) |  |  |  | Order 60
676 | Wave 4 | Block AK Bank es… | P3 | PENDING | DONE | PR #395 (bank driver-escrow counter label clarify) |  |  |  | Order 61
677 | Wave 4 | Block P 'Best Ba… | P3 | PENDING | NOT-BUILT | SAFE-ADDITIVE: no code found (grep "best bank" = 0) — genuinely pending |  |  |  | Order 62
678 | Wave 4 | Block AI User la… | P3 | PENDING | DONE | PR #394 (users.last_login_at populate + render) |  |  |  | Order 63
679 | Wave 4 | Block-A Migratio… | 187 drift — foundation | PENDING | DONE | Detection #177 (startup drift guard + CI assertion) + remediation #878 (re-homed 5 migrations to db/migrations/); verify:startup-migration-drift-guard passes. Closeout — nothing was missing |  |  |  | Order 64
680 | Wave 4 | QBO-INVOICE-BILL-PULL | spun out of Block L — future, NOT scoped | PARKED | PARKED | invoice/bill QBO→TMS pull + optional conflict-resolution UI; FINANCE-GATED when scoped. (Replaces dropped row MD-5-19-RECONCILE: stale orphan, zero code/PR/commit refs, ~30-40% redundant at intake) |  |  |  | Order 65
▼ WAVE 5 — HARDENING SWEEPS (interleaved)
681 | Wave 5 | Block N RLS cros… | Companion to BLOCK-10 | PENDING | PENDING |  |  |  |  | Order 66
682 | Wave 5 | Block M Audit-lo… | Mutation routes — companion to BLOCK-11 | PENDING | PENDING |  |  |  |  | Order 67
683 | Wave 5 | Block R Webhook-… | Outbox-aware (DLQ on fail) | PENDING | PENDING |  |  |  |  | Order 68
684 | Wave 5 | Block S Idempote… | Top write routes | PENDING | PENDING |  |  |  |  | Order 69
685 | Wave 5 | Block T Concurre… | (/api/safety/log probe pattern) | PENDING | PENDING |  |  |  |  | Order 70
686 | Wave 5 | Block W Rate-lim… | Companion to BLOCK-04 | PENDING | PENDING |  |  |  |  | Order 71
687 | Wave 5 | Block X CORS loc… | Pin allowed origins from env | PENDING | PENDING |  |  |  |  | Order 72
688 | Wave 5 | Block Y Dependen… | Generate SBOM | PENDING | PENDING |  |  |  |  | Order 73
689 | Wave 5 | Block AD Backup/… | Doc + script — companion to TIER21 | PENDING | PENDING |  |  |  |  | Order 74
690 | Wave 5 | Block AE Index/q… | Top-10 slow routes (analyze) | PENDING | PENDING |  |  |  |  | Order 75
691 | Wave 5 | Block AB Long-ru… | Cron + alert | PENDING | PENDING |  |  |  |  | Order 76
692 | Wave 5 | Block AC Worker … | Workers / outbox | PENDING | PENDING |  |  |  |  | Order 77
▼ WAVE 6 — CONTINUOUS (always running)
693 | Wave 6 | Daily anti-regre… | Loaded modules verify-* lane + financial probes | ONGOING | ONGOING |  |  |  |  | Order 78
694 | Wave 6 | Smoke after each… | Mass-Run-V8 / mini lane | ONGOING | ONGOING |  |  |  |  | Order 79
695 | Wave 6 | Re-snapshot week… | main HEAD + open-PR list + Tier29/Closure17/AI | ONGOING | ONGOING |  |  |  |  | Order 80
▼ NEW SINCE v24 — 92 merged PRs (#814 → #923) folded in from GitHub
696 | Accounting | #814 | feat(accounting): seed periods Jan–Jun 2026 for TRANSP (BLOC… |  | DONE | 2026-06-09 |  |  |  | merge 6bc364b24 / merged+live
697 | Accounting | #815 | feat(acct-ca04): Account Drawer — lock flag, opening-balance… |  | DONE | 2026-06-08 |  |  |  | merge e48ceb59b / merged+live
698 | Accounting | #816 | feat(accounting-integrity): verify-extend — period lock CI, … |  | DONE | 2026-06-09 |  |  |  | merge 61b50b4a1 / merged+live
699 | Nav | #817 | fix(fuel): wire 8 fuel sub-nav tabs to distinct routes (Bloc… |  | DONE | 2026-06-08 |  |  |  | merge 47fbf7c85 / merged+live
700 | Dispatch | #818 | fix(dispatch): wire 5 secondary tabs to distinct routes (Blo… |  | DONE | 2026-06-08 |  |  |  | merge 0307aa216 / merged+live
701 | Other | #819 | fix(routing): redirect legacy underscore URLs to hyphen path… |  | DONE | 2026-06-08 |  |  |  | merge 4e90b9fd8 / merged+live
702 | Dispatch | #820 | fix(dispatch): at-risk-loads 500 — project city/state in sd … |  | DONE | 2026-06-08 |  |  |  | merge 3dab85e2a / merged+live
703 | Driver-Hub | #822 | feat(driver-hub): wire DriverHubPage to /driver-hub route (P… |  | DONE | 2026-06-09 |  |  |  | merge aeade7286 / merged+live
704 | QBO | #823 | docs(qbo-parity): QBO-parity UI system spec + architecture/b… |  | DONE | 2026-06-09 |  |  |  | merge a5656b2d7 / merged+live
705 | QBO | #824 | feat(qbo-parity): A1 shared ParityTable grammar (UI-only) |  | DONE | 2026-06-09 |  |  |  | merge 8f3f42a05 / merged+live
706 | QBO | #825 | feat(qbo-parity): A3 sizing tokens + ParityDrawer (UI-only) |  | DONE | 2026-06-09 |  |  |  | merge ae2482583 / merged+live
707 | QBO | #826 | docs(qbo-parity): capture master report + v2/v3 + Visuals-Fi… |  | DONE | 2026-06-09 |  |  |  | merge 1a7740d06 / merged+live
708 | Nav | #827 | feat(sidebar): add DRIVER HUB nav entry (V0, additive) |  | DONE | 2026-06-09 |  |  |  | merge 4dc2ccef4 / merged+live
709 | QBO | #828 | feat(qbo-parity): A2 ReferenceSelect — inline '+ Add new' ke… |  | DONE | 2026-06-09 |  |  |  | merge 6d9cf53b6 / merged+live
710 | Dispatch | #829 | feat(dispatch): surface existing Driver/Truck/Loads planners… |  | DONE | 2026-06-09 |  |  |  | merge d0bc5e5fa / merged+live
711 | Cash-Flow | #831 | fix(cash-flow): repoint read queries to real schema (500 → 2… |  | DONE | 2026-06-09 |  |  |  | merge 98235a2da / merged+live
712 | Dispatch | #833 | feat(dispatch): persistent click-to-open sub-nav + surface p… |  | DONE | 2026-06-09 |  |  |  | merge 5a7e8992b / merged+live
713 | Maintenance | #834 | Feat/closure 10 maint parts catalog |  | DONE | 2026-06-09 |  |  |  | merge 40ffcd897 / merged+live
714 | CI/Infra | #838 | fix(ci): handle two-segment display_id regex pattern (e.g. ^… |  | DONE | 2026-06-09 |  |  |  | merge 4b06356fb / merged+live
715 | Banking | #840 | Feat/qbo block a bank transactions |  | DONE | 2026-06-10 |  |  |  | merge 05f867c3a / merged+live
716 | Other | #842 | Feat/fix pr 816 |  | DONE | 2026-06-09 |  |  |  | merge e148fa7c1 / merged+live
717 | CI/Infra | #843 | chore(deps): bump the development-dependencies group across … |  | DONE | 2026-06-10 |  |  |  | merge 21fa8ae41 / merged+live
718 | Dispatch | #844 | Add GAP-76 deadhead mile optimizer for dispatch book-load. |  | DONE | 2026-06-09 |  |  |  | merge 95ab50a90 / merged+live
719 | CI/Infra | #846 | fix(ci): guard 0937 coa role-binding seed on catalogs.accoun… |  | DONE | 2026-06-09 |  |  |  | merge 108946ccf / merged+live
720 | Migrations | #847 | fix(migrate): checksum override for 0937 post-apply EXISTS-g… |  | DONE | 2026-06-09 |  |  |  | merge 714e66bec / merged+live
721 | Other | #849 | Revert "Merge pull request #843 from tioperfumes07/feat/fix-… |  | DONE | 2026-06-10 |  |  |  | merge bc5ffaea8 / merged+live
722 | CI/Infra | #851 | fix(ci): add missing verify-closure-21-monitoring-artifacts.… |  | DONE | 2026-06-10 |  |  |  | merge 83d983b90 / merged+live
723 | Audit-Spine | #853 | fix(audit): nested-box modal regression tests (P8-AUDIT-NEST… |  | DONE | 2026-06-10 |  |  |  | merge 797e7a011 / merged+live
724 | Audit-Spine | #854 | fix(audit): archive TEST/seed rows from prod listings (P8-AU… |  | DONE | 2026-06-10 |  |  |  | merge 04b23eba3 / merged+live
725 | Audit-Spine | #855 | fix(audit): remove prod stub strings + CI guard (P8-AUDIT-PR… |  | DONE | 2026-06-10 |  |  |  | merge 2ad8532c8 / merged+live
726 | CI/Infra | #856 | fix(samsara): webhook route investigation + CI guard (SMS-FI… |  | DONE | 2026-06-10 |  |  |  | merge 2b954f4dd / merged+live
727 | Audit-Spine | #857 | fix(audit): reconcile 8 KPI drifts production vs app (P8-AUD… |  | DONE | 2026-06-10 |  |  |  | merge 87f6ff91e / merged+live
728 | Nav | #859 | feat(nav): 25-item sidebar rail + Tasks/Finance/Inventory sh… |  | DONE | 2026-06-10 |  |  |  | merge ba535ec27 / merged+live
729 | Other | #860 | fix(SMOKE-TOKEN-AUTH): bearer token smoke + disabled PR-prev… |  | DONE | 2026-06-10 |  |  |  | merge 038f648c6 / merged+live
730 | Other | #861 | fix(BUG-ADD-USER-INERT): Create user button fires zero reque… |  | DONE | 2026-06-10 |  |  |  | merge d832fd3cd / merged+live
731 | Other | #862 | fix(test): TransferModal.test.tsx — jsdom env + jest-dom mat… |  | DONE | 2026-06-10 |  |  |  | merge d9a29499c / merged+live
732 | Other | #863 | fix(test): missing @vitest-environment jsdom — 64 tests fail… |  | DONE | 2026-06-10 |  |  |  | merge 4f7addb35 / merged+live
733 | Other | #864 | fix(smoke): health-only — drop SMOKE_TEST_* secrets (no serv… |  | DONE | 2026-06-10 |  |  |  | merge c2fff4946 / merged+live
734 | Accounting | #865 | feat(C7): Accounting sub-nav 12 QBO items + global topbar + … |  | DONE | 2026-06-11 |  |  |  | merge 282b9b41c / merged+live
735 | Audit-Spine | #866 | feat(BK7): stackable inline-create drawer system (Account/Cl… |  | DONE | 2026-06-11 |  |  |  | merge df154e5dc / merged+live
736 | Other | #867 | feat(ITEM1): two-sided item model (sell→income account, buy→… |  | DONE | 2026-06-11 |  |  |  | merge dbc0f3adf / merged+live
737 | QBO | #868 | feat(C6): QBO-style home dashboard at /app/homepage |  | DONE | 2026-06-11 |  |  |  | merge 82ca58c8c / merged+live
738 | Audit-Spine | #869 | feat(W1-A): EVENT-LOG-SPINE |  | DONE | 2026-06-11 |  |  |  | merge a5968903a / merged+live
739 | Other | #870 | Fix/w1a append only |  | DONE | 2026-06-11 |  |  |  | merge 44fbdae34 / merged+live
740 | Analytics | #871 | feat(W2A): PROFITABILITY-ENGINE — one engine, three grouping… |  | DONE | 2026-06-11 |  |  |  | merge 8a55af829 / merged+live
741 | Tasks | #872 | Feat/w1b tasks module |  | DONE | 2026-06-11 |  |  |  | merge 3e2f9c251 / merged+live
742 | Analytics | #873 | feat(W2-B): alert rules + profiles |  | DONE | 2026-06-11 |  |  |  | merge 5dde7c69c / merged+live
743 | Analytics | #874 | feat(W2-P): universal planner grid + FilterBar |  | DONE | 2026-06-11 |  |  |  | merge 59924c8b9 / merged+live
744 | CI/Infra | #875 | fix(ci): remove conflict markers + dedup verify lines in ci.… |  | DONE | 2026-06-11 |  |  |  | merge cdfc79757 / merged+live
745 | Geofence | #877 | feat(W3-A): geofence engine — fences, enter/exit, spine even… |  | DONE | 2026-06-11 |  |  |  | merge 8797a1590 / merged+live
746 | Migrations | #878 | fix(deploy): re-home wave migrations to db/migrations (fixes… |  | DONE | 2026-06-11 |  |  |  | merge c8aff7027 / merged+live
747 | Geofence | #879 | feat(W3-B): forced driver acknowledgment |  | DONE | 2026-06-11 |  |  |  | merge 58552c090 / merged+live
748 | Safety | #880 | feat(W4-A): signed safety docs |  | DONE | 2026-06-11 |  |  |  | merge f45ef8f40 / merged+live
749 | Safety-Wave | #881 | feat(W4-B): broker auto-update (gated) |  | DONE | 2026-06-11 |  |  |  | merge a3f2546df / merged+live
750 | Audit-Spine | #882 | docs: audit linkage phase specs (A1–A9 + Settlements) |  | DONE | 2026-06-11 |  |  |  | merge b74543114 / merged+live
751 | Utilization | #883 | feat(W5): time utilization — minute ledger, $/hr, unaccounte… |  | DONE | 2026-06-11 |  |  |  | merge 7f88ba023 / merged+live
752 | Audit-Spine | #884 | feat(A1): audit spine link columns (source_table, source_ref… |  | DONE | 2026-06-11 |  |  |  | merge 41923b31c / merged+live
753 | Dispatch | #885 | fix(gap-e): /dispatch/planners index redirect + remove stale… |  | DONE | 2026-06-12 |  |  |  | merge 9e71c14ff / merged+live
754 | Dispatch | #886 | feat(A2): dispatch spine emit coverage — 7 mutation events w… |  | DONE | 2026-06-12 |  |  |  | merge bebf534d6 / merged+live
755 | Other | #887 | fix(shadow-routes): redirect 5 alias-shadow paths to real pa… |  | DONE | 2026-06-12 |  |  |  | merge b55104994 / merged+live
756 | Maintenance | #888 | feat(A3): maintenance WO lifecycle spine emit coverage (5 ev… |  | DONE | 2026-06-12 |  |  |  | merge 5ad736508 / merged+live
757 | Accounting | #889 | feat(A4): accounting transaction mutations emit spine events… |  | DONE | 2026-06-12 |  |  |  | merge 4f06a45bc / merged+live
758 | Banking | #890 | feat(A5): banking mutations emit spine events (9 event types… |  | DONE | 2026-06-12 |  |  |  | merge d1bf73015 / merged+live
759 | Audit-Spine | #891 | feat(A6): universal audit trail — spine read API + AuditTrai… |  | DONE | 2026-06-12 |  |  |  | merge fae8ab3df / merged+live
760 | Tasks | #892 | feat(TASKS-PLANNER-V3): employee×day planner grid — progress… |  | DONE | 2026-06-12 |  |  |  | merge 16a70eab8 / merged+live
761 | Accounting | #893 | feat(SETTLEMENTS-SIDEBAR): rename Payroll→Settlements, repos… |  | DONE | 2026-06-12 |  |  |  | merge 3f3582cdb / merged+live
762 | Accounting | #894 | feat(OB1): unify accounting nav — replace legacy 38-item hov… |  | DONE | 2026-06-12 |  |  |  | merge eb89ec0a9 / merged+live
763 | Accounting | #896 | hotfix: restore AccountingSubNav HoverDropdownNav broken by … |  | DONE | 2026-06-12 |  |  |  | merge aadf2aab1 / merged+live
764 | CI/Infra | #897 | feat(GAP-CI-WIRE-PREPUSH-GUARDS): wire 36 static pre-push lo… |  | DONE | 2026-06-12 |  |  |  | merge 3ccd25535 / merged+live
765 | Nav | #898 | feat(DESIGN-STD-NAVY-PAGE-BANNER): shared NavyPageSubNav com… |  | DONE | 2026-06-12 |  |  |  | merge 25dcf5cb3 / merged+live
766 | Audit-Spine | #899 | feat(A8-AUDIT-REPORTS-SECTION): 7 audit report pages under R… |  | DONE | 2026-06-12 |  |  |  | merge 14872ca94 / merged+live
767 | Settlements | #900 | feat(C1-PRE-SETTLEMENTS): settlement schema + read model + R… |  | DONE | 2026-06-12 |  |  |  | merge dd25eefdd / merged+live
768 | Audit-Spine | #901 | feat(A9-AUDIT-CI-EMIT-GUARD): CI gate for audit spine emit c… |  | DONE | 2026-06-12 |  |  |  | merge 19f421ac4 / merged+live
769 | Contracts | #902 | feat(C3-CUSTOMER-CONTRACT-UPLOAD): append-only contract tabl… |  | DONE | 2026-06-12 |  |  |  | merge c48adb438 / merged+live
770 | Factoring | #904 | feat(C2-FACTORING-PROFILE): tiered fee+reserve schedules + s… |  | DONE | 2026-06-12 |  |  |  | merge a47befa75 / merged+live
771 | Other | #905 | feat(C4-CUST-VEND-REBUILD-RECLASSIFY): reclassify + flag-dup… |  | DONE | 2026-06-12 |  |  |  | merge fae490c2b / merged+live
772 | Other | #906 | feat(E1-SMOKE-SERVICE-TOKEN-AUTH): service-token middleware … |  | DONE | 2026-06-12 |  |  |  | merge 4b7a7da92 / merged+live
773 | Audit | #907 | fix(P8-AUDIT-NESTED-MODALS): add jsdom env directive to moda… |  | DONE | 2026-06-12 |  |  |  | merge 060e4e025 / merged+live
774 | Audit-Spine | #908 | fix(audit): test-seed archive guard + 3rd vitest — P8-AUDIT-… |  | DONE | 2026-06-12 |  |  |  | merge bd530293b / merged+live
775 | QBO | #909 | feat(A7-AUDIT-PER-ENTITY-TABS): audit tabs with QBO-style fi… |  | DONE | 2026-06-12 |  |  |  | merge 193c71c74 / merged+live
776 | Audit-Spine | #910 | fix(audit): test-seed archive guard + 3rd vitest — P8-AUDIT-… |  | DONE | 2026-06-12 |  |  |  | merge 8974f8d20 / merged+live
777 | Positioned-Parts | #913 | M1: Positioned-Parts Picker |  | DONE | 2026-06-12 |  |  |  | merge 0f40e6b14 / merged+live
778 | Migrations | #914 | MIGRATION-RUNNER-HARDEN: fail loud on unrecognized migration… |  | DONE | 2026-06-13 |  |  |  | merge 94c75c519 / merged+live
779 | Position-History | #915 | M2: Position History for Integrity/Positioned-Parts |  | DONE | 2026-06-13 |  |  |  | merge fc51c7e55 / merged+live
780 | Audit-Spine | #916 | fix(audit): P8-AUDIT-NESTED-MODALS - fix modal test environm… |  | DONE | 2026-06-13 |  |  |  | merge 8e52bcee1 / merged+live
781 | CI/Infra | #917 | fix(ci): M2 position-history FK guard uses pg_constraint (ro… |  | DONE | 2026-06-13 |  |  |  | merge 9b92a30ae / merged+live
782 | Accounting | #918 | feat(accounting): B1 expense category map seed + cash_advanc… |  | DONE | 2026-06-13 |  |  |  | merge 367748b2d / merged+live
783 | Accounting | #919 | feat(accounting): B2 posting engine cash_advance source type |  | DONE | 2026-06-13 |  |  |  | merge 06d0a7b3b / merged+live
784 | Driver-Finance | #920 | feat(driver-finance): B3 employee-loan ledger GL posting + p… |  | DONE | 2026-06-13 |  |  |  | merge 2a50a8971 / merged+live
785 | Driver-Finance | #921 | feat(driver-finance): B4 driver-request accountability timel… |  | DONE | 2026-06-13 |  |  |  | merge 318ca7392 / merged+live
786 | Driver-Finance | #922 | feat(driver-finance): B5 cash-advance approve cascade (capst… |  | DONE | 2026-06-13 |  |  |  | merge 1866e0753 / merged+live
787 | Other | #923 | B6 — Driver Inbox UI (cascade-preview + timeline endpoints) |  | DONE | 2026-06-13 |  |  |  | merge 49638a7a4 / merged+live
▼ v28 ADDENDUM — 87 merged PRs (#924 → #1018) folded in from GitHub · reconciled 2026-06-15
788 | Other | #924 | chore(tracker): in-repo living master tracker (Markdown source of truth) |  | DONE | 2026-06-13 |  |  |  | merge fd90879ab / merged+live
789 | Driver-Finance | #925 | feat(driver-finance): A3-1 settlement-deduction ledger columns (additive, D… |  | DONE | 2026-06-13 |  |  |  | merge 6fc92db58 / merged+live
790 | Maintenance | #926 | fix(inventory): B1 repoint Parts & Stock to real /maintenance/parts (404 fix) |  | DONE | 2026-06-13 |  |  |  | merge 8e921623d / merged+live
791 | Accounting | #927 | feat(accounting): AI-4 extend period seed — TRANSP+TRK × 2025+2026 (gated, … |  | DONE | 2026-06-13 |  |  |  | merge 99df90d74 / merged+live
792 | Other | #928 | chore(tracker): reconcile UNVERIFIED rows vs merged-PR record (docs-only) |  | DONE | 2026-06-13 |  |  |  | merge acfb2cd17 / merged+live
793 | Accounting | #929 | feat(payroll): A3-2 capped advance-recovery engine + 6 locked tests (pure; … |  | DONE | 2026-06-14 |  |  |  | merge 49926ce28 / merged+live
794 | Accounting | #930 | feat(payroll): A3-2 live-path wiring (flag-gated, default OFF) + cutover fl… |  | DONE | 2026-06-14 |  |  |  | merge 6d4b5cfbe / merged+live
795 | Accounting | #931 | feat(payroll): A3-2 GL — fallback paired JE at post (Dr expense / Cr QBO-14… |  | DONE | 2026-06-14 |  |  |  | merge 71367ad38 / merged+live
796 | Accounting | #932 | feat(payroll): A3-3 settlement shadow-run (read-only OLD vs NEW recovery co… |  | DONE | 2026-06-14 |  |  |  | merge 0d60b65d8 / merged+live
797 | Accounting | #933 | feat(accounting): driver ASSET sub-account auto-provision on hire (escrow g… |  | DONE | 2026-06-14 |  |  |  | merge 7bb67827a / merged+live
798 | Accounting | #934 | feat(accounting): driver ESCROW sub-account auto-provision on hire (decisio… |  | DONE | 2026-06-14 |  |  |  | merge 894e3af9e / merged+live
799 | Accounting | #935 | feat(accounting): driver sub-account bulk backfill — DRY-RUN only (STOP #2 … |  | DONE | 2026-06-14 |  |  |  | merge 9e58a93e0 / merged+live
800 | Other | #937 | docs(recon): reconcile master tracker vs live code + driver-escrow research… |  | DONE | 2026-06-14 |  |  |  | merge 378b3fe35 / merged+live
801 | Other | #938 | docs(recon): 5 recon resolutions + multi-tab md→xlsx tracker exporter (v26 … |  | DONE | 2026-06-14 |  |  |  | merge 45c4bdd4e / merged+live
802 | Other | #939 | fix(export): multi-tab tracker exporter matching v26 format (follow-up to #… |  | DONE | 2026-06-14 |  |  |  | merge 93b60c5f7 / merged+live
803 | Tasks | #940 | feat(tasks): Block B — Create-Task UI on Task Board |  | DONE | 2026-06-14 |  |  |  | merge 0baf8afc7 / merged+live
804 | Other | #941 | feat(export): Exporter-C — GitHub tabs (02/03) for the tracker xlsx (all 10… |  | DONE | 2026-06-14 |  |  |  | merge d4c85abe5 / merged+live
805 | Maintenance | #942 | feat(maintenance): Block F — reefer hours 15-minute poller cron |  | DONE | 2026-06-14 |  |  |  | merge a3e4fadf6 / merged+live
806 | Docs | #943 | docs(mileage): mileage-model design + grounding spec (phased PC*Miler) |  | DONE | 2026-06-14 |  |  |  | merge 1190e44a1 / merged+live
807 | Dispatch | #944 | feat(dispatch): Block 1 (C-1) — Planners split-control nav |  | DONE | 2026-06-14 |  |  |  | merge 5ac8e9c19 / merged+live
808 | Nav | #945 | feat(nav): Block 8 — hide stub/placeholder pages from sidebar |  | DONE | 2026-06-14 |  |  |  | merge fa0f57f19 / merged+live
809 | Docs | #946 | docs(mileage): §6 answered — lock Jorge's 6 mileage decisions |  | DONE | 2026-06-14 |  |  |  | merge 465d3564a / merged+live
810 | CI/Infra | #947 | docs(security): Block 9 — RLS coverage audit (inventory, no fixes) |  | DONE | 2026-06-14 |  |  |  | merge 74dcb8feb / merged+live
811 | Finance | #948 | docs(finance): B9 escrow-deduction design spec (gated build, locked rules) |  | DONE | 2026-06-14 |  |  |  | merge 3b69ce46d / merged+live
812 | Docs | #949 | feat(docs): Block 4 — docs-upload UI on the Documents page |  | DONE | 2026-06-14 |  |  |  | merge 5b876330d / merged+live
813 | Docs | #950 | feat(help): Block 5 — module-guide help stubs (structure only) |  | DONE | 2026-06-14 |  |  |  | merge 80d09aefe / merged+live
814 | Driver-Finance | #951 | feat(driver-finance): Block 6 (B7) — driver-inbox reporting (read-only) |  | DONE | 2026-06-14 |  |  |  | merge d7c2b8717 / merged+live
815 | Catalogs | #952 | feat(catalogs): Block 7 — classes bulk-edit (batch-PATCH + multi-select) |  | DONE | 2026-06-14 |  |  |  | merge 5ac90ef99 / merged+live
816 | Finance | #953 | docs(finance): Roles & Permissions design spec (foundational, VOID vs DELETE) |  | DONE | 2026-06-14 |  |  |  | merge 7fa266d0a / merged+live
817 | Docs | #954 | docs(mileage): §1A lifecycle correction — short@assign-bill, practical@deli… |  | DONE | 2026-06-14 |  |  |  | merge 1301ff7bd / merged+live
818 | Finance | #955 | docs(finance): B9 §9A — escrow management screen (UI, Jorge-approved) |  | DONE | 2026-06-14 |  |  |  | merge c377e582c / merged+live
819 | Finance | #956 | docs(finance): RELAY internal-bank + diesel-code design spec (Section D #2) |  | DONE | 2026-06-14 |  |  |  | merge 00694203a / merged+live
820 | Finance | #957 | docs(finance): FH-1 Fixed Assets + Depreciation design spec (Finance … |  | DONE | 2026-06-14 |  |  |  | merge 5dac3741d / merged+live
821 | Finance | #958 | docs(finance): FH-3 Amortization Schedule Engine design spec (Finance Hub) |  | DONE | 2026-06-14 |  |  |  | merge f2218ed3e / merged+live
822 | Finance | #959 | docs(finance): FH-2 Loan Wizard design spec (Finance Hub centerpiece) |  | DONE | 2026-06-14 |  |  |  | merge 62d43fd89 / merged+live
823 | Finance | #960 | docs(finance): FH-4 Finance Calculator design spec (Finance Hub) |  | DONE | 2026-06-14 |  |  |  | merge c2ca4029a / merged+live
824 | Finance | #961 | docs(finance): FH-6 Tax Manager + FH-6a rendition design spec (Finance Hub) |  | DONE | 2026-06-14 |  |  |  | merge 2847cd5f7 / merged+live
825 | Finance | #962 | docs(finance): FH-7 shared Unit Allocation control design spec (Finance Hub) |  | DONE | 2026-06-14 |  |  |  | merge 3ee3bbe13 / merged+live
826 | Finance | #963 | docs(finance): FH-5 Bankruptcy Modeler design spec (Finance Hub, build last) |  | DONE | 2026-06-14 |  |  |  | merge df5ecae61 / merged+live
827 | Finance | #964 | docs(finance): VOID-EVERYWHERE cross-cutting design spec (build packa… |  | DONE | 2026-06-14 |  |  |  | merge d9404f677 / merged+live
828 | Finance | #965 | docs(finance): FH-8 Lease Contract + Unit Picker design spec (Legal<-… |  | DONE | 2026-06-15 |  |  |  | merge 79dafe902 / merged+live
829 | Finance | #966 | docs(finance): FH-1 Fixed Assets + Depreciation design spec (Finance … |  | DONE | 2026-06-15 |  |  |  | merge a75d2d14b / merged+live
830 | Finance | #967 | docs(finance): FH-1 follow-up — inter-company leasing (owner vs opera… |  | DONE | 2026-06-15 |  |  |  | merge aaa33424c / merged+live
831 | Finance | #968 | docs(finance): apply answered questions to FH-2 (trade-in) + FH-6 (ta… |  | DONE | 2026-06-15 |  |  |  | merge ae66deed7 / merged+live
832 | Finance | #969 | docs(finance): FH-5 — posting decision LOCKED (POST TO BOOKS) |  | DONE | 2026-06-15 |  |  |  | merge c0d4bd677 / merged+live
833 | Tasks | #970 | fix(tasks): task-create 400 — stop double-stringifying the request body |  | DONE | 2026-06-15 |  |  |  | merge ae4135a02 / merged+live
834 | Finance | #971 | fix(finance): stop double-stringifying money-path request bodies |  | DONE | 2026-06-15 |  |  |  | merge ba3f11950 / merged+live
835 | Finance | #972 | docs(finance): VOID-EVERYWHERE — cash¦accrual basis for reversing-ent… |  | DONE | 2026-06-15 |  |  |  | merge 14e4966bf / merged+live
836 | Accounting | #973 | feat(accounting): VOID-EVERYWHERE PR-1 — gated void engine for invoices + j… |  | DONE | 2026-06-15 |  |  |  | merge 3ead2e837 / merged+live
837 | Nav | #974 | fix(nav): remove left-sidebar hover fly-out dropdown (block 17) |  | DONE | 2026-06-15 |  |  |  | merge fb6ea1471 / merged+live
838 | CI/Infra | #975 | fix(api): stop double-stringifying request bodies in the remaining no… |  | DONE | 2026-06-15 |  |  |  | merge 499a34552 / merged+live
839 | Accounting | #976 | feat(accounting): D5 Account Register — read-only per-account running-balan… |  | DONE | 2026-06-15 |  |  |  | merge 47b8d6b04 / merged+live
840 | Accounting | #977 | feat(accounting): VOID-EVERYWHERE PR-2 — gated void engine for bills (AP mi… |  | DONE | 2026-06-15 |  |  |  | merge be3323ed7 / merged+live
841 | Finance | #978 | docs(finance): VOID-EVERYWHERE PR-3/PR-4 design — expenses + settlements vo… |  | DONE | 2026-06-15 |  |  |  | merge 68bb77fdb / merged+live
842 | Tasks | #979 | fix(tasks): Create Task 500/42501 — RLS scope sets the wrong GUC name |  | DONE | 2026-06-15 |  |  |  | merge 1ea68ee8f / merged+live
843 | Tasks | #980 | fix(tasks): planner 500/42P01 — join identity.users, not non-existent users… |  | DONE | 2026-06-15 |  |  |  | merge 287107aa0 / merged+live
844 | Drivers | #981 | fix(drivers): deactivate sets status='Inactive' (driver stayed Active after… |  | DONE | 2026-06-15 |  |  |  | merge c7fcd97af / merged+live
845 | Driver-Finance | #982 | fix(driver-finance): mount orphaned escrow-deductions-pending routes (404) |  | DONE | 2026-06-15 |  |  |  | merge 6c50ba8a9 / merged+live
846 | Customers | #984 | fix(customers): QBO customer-sync returned HTML (raw relative fetch -> wron… |  | DONE | 2026-06-15 |  |  |  | merge 0d1f408c7 / merged+live
847 | Fleet | #985 | fix(units): deactivate sets status='OutOfService' (mirror of driver deactiv… |  | DONE | 2026-06-15 |  |  |  | merge d65dddb60 / merged+live
848 | Insurance | #986 | fix(insurance): asset coverage 404'd for every unit (unit-id vs asset-id mi… |  | DONE | 2026-06-15 |  |  |  | merge e3022787f / merged+live
849 | Maintenance | #987 | fix(maintenance): fleet-table KPIs 500 — non-existent unit_status enum values |  | DONE | 2026-06-15 |  |  |  | merge ced807e0f / merged+live
850 | Dispatch | #988 | fix(dispatch): mount orphaned load settlement-summary route (404) |  | DONE | 2026-06-15 |  |  |  | merge bdbd74494 / merged+live
851 | Maintenance | #989 | fix(maintenance): WO list shows unit_number, not raw unit UUID |  | DONE | 2026-06-15 |  |  |  | merge 3fe701e46 / merged+live
852 | Maintenance | #990 | fix(maintenance): dashboard KPIs 500 — second unit_status 'active' enum bug |  | DONE | 2026-06-15 |  |  |  | merge 6dd54c878 / merged+live
853 | CI/Infra | #992 | fix(routes): mount 7 orphaned non-financial routes the frontend calls (404s) |  | DONE | 2026-06-15 |  |  |  | merge b3820999f / merged+live
854 | CI/Infra | #993 | chore(ci): guard against orphaned routes (kills the 404-from-unmounted-rout… |  | DONE | 2026-06-15 |  |  |  | merge 953f44447 / merged+live
855 | Accounting | #994 | fix(escrow): drop dead /driver-finance/escrow call (404 on every Escrow Rec… |  | DONE | 2026-06-15 |  |  |  | merge c8c69ab8d / merged+live
856 | CI/Infra | #995 | fix(routes): mount 4 more orphaned non-financial routes (batch 2) |  | DONE | 2026-06-15 |  |  |  | merge 9f4763530 / merged+live
857 | CI/Infra | #996 | chore(ci): guard against invalid enum literals (22P02) + fix 2 it surfaced |  | DONE | 2026-06-15 |  |  |  | merge cd33f9215 / merged+live
858 | Drivers | #997 | fix(drivers): rehire validation walks the full chain (not just immediate pr… |  | DONE | 2026-06-15 |  |  |  | merge 487dad2bb / merged+live
859 | Maintenance | #998 | fix(maintenance): cap-12/cap-13 workers query mdata.units by non-existent o… |  | DONE | 2026-06-15 |  |  |  | merge dd73ae0d0 / merged+live
860 | Migrations | #999 | fix(migrations): repair safety.fines→civil_fines (#0050 ordering collision)… |  | DONE | 2026-06-15 |  |  |  | merge 1a3293af8 / merged+live
861 | CI/Infra | #1001 | chore(ci): bump actions/checkout from 4 to 6 |  | DONE | 2026-06-15 |  |  |  | merge 7f53d845b / merged+live
862 | CI/Infra | #1002 | chore(ci): bump actions/setup-node from 4 to 6 |  | DONE | 2026-06-15 |  |  |  | merge a306559d7 / merged+live
863 | Accounting | #1005 | docs(accounting): GAP-EXPENSES-MODULE-COMPLETION design — verified, A1/A2 f… |  | DONE | 2026-06-15 |  |  |  | merge 954f3fee5 / merged+live
864 | Accounting | #1006 | feat(accounting): GAP-EXPENSES Phase 1 — accounting.expenses header (A1-sta… |  | DONE | 2026-06-15 |  |  |  | merge 184da5a6c / merged+live
865 | Accounting | #1007 | docs(accounting): GAP-EXPENSES Phase 1.5 design — expense_lines cents… |  | DONE | 2026-06-15 |  |  |  | merge 46610e844 / merged+live
866 | Accounting | #1008 | feat(accounting): GAP-EXPENSES Phase 1.5 — cents reconciliation + hard tota… |  | DONE | 2026-06-15 |  |  |  | merge c6c57b712 / merged+live
867 | Maintenance | #1009 | test(maintenance): cover copyToAccountingLines bill branch (Phase 1.5 follo… |  | DONE | 2026-06-15 |  |  |  | merge 846c5ff42 / merged+live
868 | Accounting | #1010 | docs(accounting): GAP-EXPENSES Phase 2 design — expense → GL posting + reve… |  | DONE | 2026-06-15 |  |  |  | merge e2c76b653 / merged+live
869 | Insurance | #1011 | fix(insurance): policy_unit has no is_active column — use removed_at (42703… |  | DONE | 2026-06-15 |  |  |  | merge 5448ca26f / merged+live
870 | CI/Infra | #1012 | chore(deps): bump form-data from 4.0.5 to 4.0.6 |  | DONE | 2026-06-15 |  |  |  | merge c2a545dcc / merged+live
871 | CI/Infra | #1013 | chore(deps): bump js-yaml from 4.1.1 to 4.2.0 |  | DONE | 2026-06-15 |  |  |  | merge a980876be / merged+live
872 | Accounting | #1015 | feat(accounting): GAP-EXPENSES Phase 2 Step 2 — Uncategorized-Expenses seed… |  | DONE | 2026-06-15 |  |  |  | merge f41b2e256 / merged+live
873 | Finance | #1017 | feat(finance): FH-1 Fixed Assets — Step 1 data model (fixed_assets sc… |  | DONE | 2026-06-15 |  |  |  | merge d2a7fc8dc / merged+live
874 | Accounting | #1018 | feat(accounting): GAP-EXPENSES Phase 2 Step 3 — expense → GL posting … |  | DONE | 2026-06-15 |  |  |  | merge 863a9f109 / merged+live
875 | Accounting | #1019 | fix(accounting): COA-UNCATEGORIZED-EXPENSE-QBO-RECONCILE — uncategorized_expense role → QBO #25; soft-retire #6999 seed |  | DONE | 2026-06-15 |  |  |  | merge c6fd71e42 / merged+live; GUARD prod-query (condition 3) CLOSED — role→4cec8ed2/#QBO-25, #6999 retired
▼ FOLLOW-UP BACKLOG — opened 2026-06-15 (design-first, not yet built)
876 | Insurance | INS-COVERAGE-ASSETS-VS-UNITS-MISMATCH | coverage-gap reads mdata.assets with mdata.units ids → silent "no gap" for unchecked trucks |  | PENDING (design-first) | 2026-06-15 |  |  |  | Tier 3. 87 units vs 43 mdata.assets, different id space → most lookups MISS and return [] silently (reports no-gap for trucks never checked). Diagnose: is mdata.assets meant to mirror mdata.units, or should coverage query mdata.units directly? Found during insurance-500 hunt
877 | Accounting | COA-ACCOUNTS-UNAUDITED | catalogs.accounts has no audit.row_changes capture; COA mutations leave no actor trail |  | PENDING (design-first) | 2026-06-15 |  |  |  | Only trg_catalogs_accounts_updated_at (timestamp) on the table; financial-cluster audit gap. Found during #6999 anomaly 1b investigation
878 | Security | SEC-PROD-APP-ROLE-BYPASSES-RLS | prod app pool connects as neondb_owner, which bypasses FORCEd RLS; tenant isolation relies only on app WHERE-clauses |  | PENDING (design-first) | 2026-06-15 |  |  |  | P1 security · Tier 1 (money-path adjacent). Investigate moving app to a non-bypass role (ih35_app) or document why owner is required. Found while reproducing the insurance-500 query as the prod app role
879 | Accounting | EXPENSE-VOID-BLOCK-IF-LINKED-GATE3 | Step-3 design #1016 §5 specified block-if-linked (Gate 3) redirecting WO-/bill-/load-sourced expense voids to void-at-source; shipped expense void (expenses.routes.ts:489) has ZERO linkage checks |  | PENDING (design-first) | 2026-06-15 |  |  |  | Tier 1 (money-path void safety). INERT today (behind VOID_ENFORCEMENT_ENABLED=OFF; no posted expenses since EXPENSE_GL_POSTING_ENABLED=OFF). HARD GATE: must land BEFORE VOID_ENFORCEMENT_ENABLED is ever flipped on. Orphan found in #1016 close-out review

## 02 New Since v24
NEW SINCE v24 — merged PRs (#>813)
pulled from GitHub at generate time (2026-06-15)
PR # | Merge Date | Merge Time | SHA | Domain | Title | Status
#814 | 2026-06-09 | 16:11:03 | 6bc364b2 | accounting | feat(accounting): seed periods Jan–Jun 2026 for TRANSP (BLOCK-11) | merged
#815 | 2026-06-08 | 21:59:57 | e48ceb59 | acct-ca04 | feat(acct-ca04): Account Drawer — lock flag, opening-balance-as-of, nullable account_number | merged
#816 | 2026-06-09 | 20:53:41 | 61b50b4a | accounting-integrity | feat(accounting-integrity): verify-extend — period lock CI, bank-recon cron, accounting probes, CoA role bindings | merged
#817 | 2026-06-08 | 22:06:18 | 47fbf7c8 | fuel | fix(fuel): wire 8 fuel sub-nav tabs to distinct routes (Block U) | merged
#818 | 2026-06-08 | 15:46:48 | 0307aa21 | dispatch | fix(dispatch): wire 5 secondary tabs to distinct routes (Block V) | merged
#819 | 2026-06-08 | 22:06:03 | 4e90b9fd | routing | fix(routing): redirect legacy underscore URLs to hyphen paths (Block H) | merged
#820 | 2026-06-08 | 21:29:37 | 3dab85e2 | dispatch | fix(dispatch): at-risk-loads 500 — project city/state in sd lateral (42703) | merged
#822 | 2026-06-09 | 02:09:31 | aeade728 | driver-hub | feat(driver-hub): wire DriverHubPage to /driver-hub route (P5a) | merged
#823 | 2026-06-09 | 02:26:56 | a5656b2d | qbo-parity | docs(qbo-parity): QBO-parity UI system spec + architecture/blueprint/locked-decisions | merged
#824 | 2026-06-09 | 04:02:54 | 8f3f42a0 | qbo-parity | feat(qbo-parity): A1 shared ParityTable grammar (UI-only) | merged
#825 | 2026-06-09 | 05:37:29 | ae248258 | qbo-parity | feat(qbo-parity): A3 sizing tokens + ParityDrawer (UI-only) | merged
#826 | 2026-06-09 | 05:43:55 | 1a7740d0 | qbo-parity | docs(qbo-parity): capture master report + v2/v3 + Visuals-First (nothing lost) | merged
#827 | 2026-06-09 | 05:41:49 | 4dc2ccef | sidebar | feat(sidebar): add DRIVER HUB nav entry (V0, additive) | merged
#828 | 2026-06-09 | 06:02:27 | 6d9cf53b | qbo-parity | feat(qbo-parity): A2 ReferenceSelect — inline '+ Add new' keystone (UI-only) | merged
#829 | 2026-06-09 | 06:48:44 | d0bc5e5f | dispatch | feat(dispatch): surface existing Driver/Truck/Loads planners from Dispatch header (V3) | merged
#831 | 2026-06-09 | 08:00:34 | 98235a2d | cash-flow | fix(cash-flow): repoint read queries to real schema (500 → 200) | merged
#833 | 2026-06-09 | 14:26:26 | 5a7e8992 | dispatch | feat(dispatch): persistent click-to-open sub-nav + surface planners (Option A) | merged
#834 | 2026-06-09 | 16:30:54 | 40ffcd89 | — | Feat/closure 10 maint parts catalog | merged
#838 | 2026-06-09 | 21:21:45 | 4b06356f | ci | fix(ci): handle two-segment display_id regex pattern (e.g. ^CM-[0-9]{… | merged
#840 | 2026-06-10 | 00:00:17 | 05f867c3 | — | Feat/qbo block a bank transactions | merged
#842 | 2026-06-09 | 21:41:37 | e148fa7c | — | Feat/fix pr 816 | merged
#843 | 2026-06-10 | 00:26:55 | 21fa8ae4 | deps | chore(deps): bump the development-dependencies group across 1 directo… | merged
#844 | 2026-06-09 | 21:16:08 | 95ab50a9 | — | Add GAP-76 deadhead mile optimizer for dispatch book-load. | merged
#846 | 2026-06-09 | 22:51:29 | 108946cc | ci | fix(ci): guard 0937 coa role-binding seed on catalogs.accounts existence | merged
#847 | 2026-06-09 | 23:19:38 | 714e66be | migrate | fix(migrate): checksum override for 0937 post-apply EXISTS-guard edit | merged
#849 | 2026-06-10 | 00:45:41 | bc5ffaea | — | Revert "Merge pull request #843 from tioperfumes07/feat/fix-pr-836" | merged
#851 | 2026-06-10 | 02:53:21 | 83d983b9 | ci | fix(ci): add missing verify-closure-21-monitoring-artifacts.mjs | merged
#853 | 2026-06-10 | 06:53:36 | 797e7a01 | audit | fix(audit): nested-box modal regression tests (P8-AUDIT-NESTED-MODALS) | merged
#854 | 2026-06-10 | 06:53:46 | 04b23eba | audit | fix(audit): archive TEST/seed rows from prod listings (P8-AUDIT-TEST-DATA) | merged
#855 | 2026-06-10 | 06:53:49 | 2ad8532c | audit | fix(audit): remove prod stub strings + CI guard (P8-AUDIT-PROD-STUBS) | merged
#856 | 2026-06-10 | 06:53:52 | 2b954f4d | samsara | fix(samsara): webhook route investigation + CI guard (SMS-FIX-2-WEBHOOKS) | merged
#857 | 2026-06-10 | 06:53:56 | 87f6ff91 | audit | fix(audit): reconcile 8 KPI drifts production vs app (P8-AUDIT-KPI-DRIFTS) | merged
#859 | 2026-06-10 | 20:25:11 | ba535ec2 | nav | feat(nav): 25-item sidebar rail + Tasks/Finance/Inventory shells (SIDEBAR-V2-REORG-25) | merged
#860 | 2026-06-10 | 20:24:19 | 038f648c | SMOKE-TOKEN-AUTH | fix(SMOKE-TOKEN-AUTH): bearer token smoke + disabled PR-preview trigger + Add User bug fix | merged
#861 | 2026-06-10 | 20:24:07 | d832fd3c | BUG-ADD-USER-INERT | fix(BUG-ADD-USER-INERT): Create user button fires zero requests — fix FE disable-state + BE default_company_id | merged
#862 | 2026-06-10 | 20:46:38 | d9a29499 | test | fix(test): TransferModal.test.tsx — jsdom env + jest-dom matchers fix (P5-T6) | merged
#863 | 2026-06-10 | 23:23:06 | 4f7addb3 | test | fix(test): missing @vitest-environment jsdom — 64 tests failing on main | merged
#864 | 2026-06-10 | 23:19:51 | c2fff494 | smoke | fix(smoke): health-only — drop SMOKE_TEST_* secrets (no service-token route exists) | merged
#865 | 2026-06-11 | 03:25:09 | 282b9b41 | C7 | feat(C7): Accounting sub-nav 12 QBO items + global topbar + Create / Tasks | merged
#866 | 2026-06-11 | 03:28:04 | df154e5d | BK7 | feat(BK7): stackable inline-create drawer system (Account/Class/Service/Vendor/Customer) | merged
#867 | 2026-06-11 | 04:02:17 | dbc0f3ad | ITEM1 | feat(ITEM1): two-sided item model (sell→income account, buy→expense account) | merged
#868 | 2026-06-11 | 04:02:45 | 82ca58c8 | C6 | feat(C6): QBO-style home dashboard at /app/homepage | merged
#869 | 2026-06-11 | 14:34:50 | a5968903 | W1-A | feat(W1-A): EVENT-LOG-SPINE | merged
#870 | 2026-06-11 | 16:40:10 | 44fbdae3 | — | Fix/w1a append only | merged
#871 | 2026-06-11 | 17:35:06 | 8a55af82 | W2A | feat(W2A): PROFITABILITY-ENGINE — one engine, three groupings + analy… | merged
#872 | 2026-06-11 | 17:49:18 | 3e2f9c25 | — | Feat/w1b tasks module | merged
#873 | 2026-06-11 | 17:58:34 | 5dde7c69 | W2-B | feat(W2-B): alert rules + profiles | merged
#874 | 2026-06-11 | 18:10:13 | 59924c8b | W2-P | feat(W2-P): universal planner grid + FilterBar | merged
#875 | 2026-06-11 | 18:33:11 | cdfc7975 | ci | fix(ci): remove conflict markers + dedup verify lines in ci.yml | merged
#877 | 2026-06-11 | 20:23:04 | 8797a159 | W3-A | feat(W3-A): geofence engine — fences, enter/exit, spine events | merged
#878 | 2026-06-11 | 19:52:04 | c8aff702 | deploy | fix(deploy): re-home wave migrations to db/migrations (fixes 14h boot drift) | merged
#879 | 2026-06-11 | 20:47:58 | 58552c09 | W3-B | feat(W3-B): forced driver acknowledgment | merged
#880 | 2026-06-11 | 21:19:12 | f45ef8f4 | W4-A | feat(W4-A): signed safety docs | merged
#881 | 2026-06-11 | 21:49:28 | a3f2546d | W4-B | feat(W4-B): broker auto-update (gated) | merged
#882 | 2026-06-11 | 22:23:41 | b7454311 | — | docs: audit linkage phase specs (A1–A9 + Settlements) | merged
#883 | 2026-06-11 | 22:33:13 | 7f88ba02 | W5 | feat(W5): time utilization — minute ledger, $/hr, unaccounted (read-only) | merged
#884 | 2026-06-11 | 23:54:15 | 41923b31 | A1 | feat(A1): audit spine link columns (source_table, source_reference_id) | merged
#885 | 2026-06-12 | 01:25:52 | 9e71c14f | gap-e | fix(gap-e): /dispatch/planners index redirect + remove stale /tasks ComingSoonPage stub | merged
#886 | 2026-06-12 | 01:43:06 | bebf534d | A2 | feat(A2): dispatch spine emit coverage — 7 mutation events wired to events.log_event() | merged
#887 | 2026-06-12 | 01:54:10 | b5510499 | shadow-routes | fix(shadow-routes): redirect 5 alias-shadow paths to real pages | merged
#888 | 2026-06-12 | 01:59:42 | 5ad73650 | A3 | feat(A3): maintenance WO lifecycle spine emit coverage (5 event types) | merged
#889 | 2026-06-12 | 02:52:47 | 4f06a45b | A4 | feat(A4): accounting transaction mutations emit spine events (14 even… | merged
#890 | 2026-06-12 | 03:12:03 | d1bf7301 | A5 | feat(A5): banking mutations emit spine events (9 event types) | merged
#891 | 2026-06-12 | 04:21:55 | fae8ab3d | A6 | feat(A6): universal audit trail — spine read API + AuditTrailPage with RLS, pagination, CSV export | merged
#892 | 2026-06-12 | 04:53:28 | 16a70eab | TASKS-PLANNER-V3 | feat(TASKS-PLANNER-V3): employee×day planner grid — progress_pct, tas… | merged
#893 | 2026-06-12 | 05:03:02 | 3f3582cd | SETTLEMENTS-SIDEBAR | feat(SETTLEMENTS-SIDEBAR): rename Payroll→Settlements, reposition between Cash Flow and Accounting | merged
#894 | 2026-06-12 | 05:11:23 | eb89ec0a | OB1 | feat(OB1): unify accounting nav — replace legacy 38-item hover-dropdown with 12-tab clean bar | merged
#896 | 2026-06-12 | 05:42:10 | aadf2aab | — | hotfix: restore AccountingSubNav HoverDropdownNav broken by OB1; corr… | merged
#897 | 2026-06-12 | 06:18:18 | 3ccd2553 | GAP-CI-WIRE-PREPUSH-GUARDS | feat(GAP-CI-WIRE-PREPUSH-GUARDS): wire 36 static pre-push locked guar… | merged
#898 | 2026-06-12 | 06:31:57 | 25dcf5cb | DESIGN-STD-NAVY-PAGE-BANNER | feat(DESIGN-STD-NAVY-PAGE-BANNER): shared NavyPageSubNav component + SettlementsPage swap + CI lock | merged
#899 | 2026-06-12 | 06:53:23 | 14872ca9 | A8-AUDIT-REPORTS-SECTION | feat(A8-AUDIT-REPORTS-SECTION): 7 audit report pages under Reports > … | merged
#900 | 2026-06-12 | 07:16:12 | dd25eefd | C1-PRE-SETTLEMENTS | feat(C1-PRE-SETTLEMENTS): settlement schema + read model + RLS + 3 read-only endpoints | merged
#901 | 2026-06-12 | 07:07:46 | 19f421ac | A9-AUDIT-CI-EMIT-GUARD | feat(A9-AUDIT-CI-EMIT-GUARD): CI gate for audit spine emit coverage | merged
#902 | 2026-06-12 | 08:08:40 | c48adb43 | C3-CUSTOMER-CONTRACT-UPLOAD | feat(C3-CUSTOMER-CONTRACT-UPLOAD): append-only contract table + routes + UI | merged
#904 | 2026-06-12 | 12:40:49 | a47befa7 | C2-FACTORING-PROFILE | feat(C2-FACTORING-PROFILE): tiered fee+reserve schedules + server-side validation | merged
#905 | 2026-06-12 | 14:15:45 | fae490c2 | C4-CUST-VEND-REBUILD-RECLASSIFY | feat(C4-CUST-VEND-REBUILD-RECLASSIFY): reclassify + flag-duplicate routes, append-only log, spine emit | merged
#906 | 2026-06-12 | 15:23:54 | 4b7a7da9 | E1-SMOKE-SERVICE-TOKEN-AUTH | feat(E1-SMOKE-SERVICE-TOKEN-AUTH): service-token middleware + smoke probe + perf-metrics dual-auth | merged
#907 | 2026-06-12 | 15:53:43 | 060e4e02 | P8-AUDIT-NESTED-MODALS | fix(P8-AUDIT-NESTED-MODALS): add jsdom env directive to modal-x-close… | merged
#908 | 2026-06-12 | 16:06:30 | bd530293 | audit | fix(audit): test-seed archive guard + 3rd vitest — P8-AUDIT-TEST-DATA | merged
#909 | 2026-06-12 | 16:37:00 | 193c71c7 | A7-AUDIT-PER-ENTITY-TABS | feat(A7-AUDIT-PER-ENTITY-TABS): audit tabs with QBO-style filters for… | merged
#910 | 2026-06-12 | 18:43:41 | 8974f8d2 | audit | fix(audit): test-seed archive guard + 3rd vitest — P8-AUDIT-TEST-DATA… | merged
#913 | 2026-06-12 | 23:46:49 | 0f40e6b1 | — | M1: Positioned-Parts Picker | merged
#914 | 2026-06-13 | 00:28:52 | 94c75c51 | — | MIGRATION-RUNNER-HARDEN: fail loud on unrecognized migration filenames | merged
#915 | 2026-06-13 | 04:16:46 | fc51c7e5 | — | M2: Position History for Integrity/Positioned-Parts | merged
#916 | 2026-06-13 | 05:00:50 | 8e52bcee | audit | fix(audit): P8-AUDIT-NESTED-MODALS - fix modal test environment | merged
#917 | 2026-06-13 | 08:08:04 | 9b92a30a | ci | fix(ci): M2 position-history FK guard uses pg_constraint (role-independent) | merged
#918 | 2026-06-13 | 08:24:14 | 367748b2 | accounting | feat(accounting): B1 expense category map seed + cash_advance category | merged
#919 | 2026-06-13 | 09:05:31 | 06d0a7b3 | accounting | feat(accounting): B2 posting engine cash_advance source type | merged
#920 | 2026-06-13 | 10:12:46 | 2a50a897 | driver-finance | feat(driver-finance): B3 employee-loan ledger GL posting + posting_date | merged
#921 | 2026-06-13 | 11:02:04 | 318ca739 | driver-finance | feat(driver-finance): B4 driver-request accountability timeline | merged
#922 | 2026-06-13 | 14:37:49 | 1866e075 | driver-finance | feat(driver-finance): B5 cash-advance approve cascade (capstone) | merged
#923 | 2026-06-13 | 17:25:22 | 49638a7a | — | B6 — Driver Inbox UI (cascade-preview + timeline endpoints) | merged
#924 | 2026-06-13 | 19:36:06 | fd90879a | tracker | chore(tracker): in-repo living master tracker (Markdown source of truth) | merged
#925 | 2026-06-13 | 19:54:18 | 6fc92db5 | driver-finance | feat(driver-finance): A3-1 settlement-deduction ledger columns (additive, DB-only) | merged
#926 | 2026-06-13 | 20:05:55 | 8e921623 | inventory | fix(inventory): B1 repoint Parts & Stock to real /maintenance/parts (404 fix) | merged
#927 | 2026-06-13 | 20:54:26 | 99df90d7 | accounting | feat(accounting): AI-4 extend period seed — TRANSP+TRK × 2025+2026 (gated, portable) | merged
#928 | 2026-06-13 | 20:59:40 | acfb2cd1 | tracker | chore(tracker): reconcile UNVERIFIED rows vs merged-PR record (docs-only) | merged
#929 | 2026-06-14 | 02:30:17 | 49926ce2 | payroll | feat(payroll): A3-2 capped advance-recovery engine + 6 locked tests (pure; live path GATED) | merged
#930 | 2026-06-14 | 03:34:33 | 6d4b5cfb | payroll | feat(payroll): A3-2 live-path wiring (flag-gated, default OFF) + cutover flag + override DDL | merged
#931 | 2026-06-14 | 04:50:43 | 71367ad3 | payroll | feat(payroll): A3-2 GL — fallback paired JE at post (Dr expense / Cr QBO-149), flag OFF | merged
#932 | 2026-06-14 | 05:12:15 | 0d60b65d | payroll | feat(payroll): A3-3 settlement shadow-run (read-only OLD vs NEW recovery comparison) | merged
#933 | 2026-06-14 | 06:23:53 | 7bb67827 | accounting | feat(accounting): driver ASSET sub-account auto-provision on hire (escrow gated) | merged
#934 | 2026-06-14 | 08:29:18 | 894e3af9 | accounting | feat(accounting): driver ESCROW sub-account auto-provision on hire (decision #1 resolved) | merged
#935 | 2026-06-14 | 08:58:23 | 9e58a93e | accounting | feat(accounting): driver sub-account bulk backfill — DRY-RUN only (STOP #2 gated) | merged
#937 | 2026-06-14 | 14:33:46 | 378b3fe3 | recon | docs(recon): reconcile master tracker vs live code + driver-escrow research spec | merged
#938 | 2026-06-14 | 15:22:18 | 45c4bdd4 | recon | docs(recon): 5 recon resolutions + multi-tab md→xlsx tracker exporter (v26 format) | merged
#939 | 2026-06-14 | 16:24:29 | 93b60c5f | export | fix(export): multi-tab tracker exporter matching v26 format (follow-up to #938) | merged
#940 | 2026-06-14 | 16:45:56 | 0baf8afc | tasks | feat(tasks): Block B — Create-Task UI on Task Board | merged
#941 | 2026-06-14 | 17:08:53 | d4c85abe | export | feat(export): Exporter-C — GitHub tabs (02/03) for the tracker xlsx (all 10 tabs) | merged
#942 | 2026-06-14 | 17:09:11 | a3e4fadf | maintenance | feat(maintenance): Block F — reefer hours 15-minute poller cron | merged
#943 | 2026-06-14 | 18:44:45 | 1190e44a | mileage | docs(mileage): mileage-model design + grounding spec (phased PC*Miler) | merged
#944 | 2026-06-14 | 19:13:57 | 5ac8e9c1 | dispatch | feat(dispatch): Block 1 (C-1) — Planners split-control nav | merged
#945 | 2026-06-14 | 19:29:48 | fa0f57f1 | nav | feat(nav): Block 8 — hide stub/placeholder pages from sidebar | merged
#946 | 2026-06-14 | 19:44:27 | 465d3564 | mileage | docs(mileage): §6 answered — lock Jorge's 6 mileage decisions | merged
#947 | 2026-06-14 | 19:50:06 | 74dcb8fe | security | docs(security): Block 9 — RLS coverage audit (inventory, no fixes) | merged
#948 | 2026-06-14 | 19:58:20 | 3b69ce46 | finance | docs(finance): B9 escrow-deduction design spec (gated build, locked rules) | merged
#949 | 2026-06-14 | 20:17:10 | 5b876330 | docs | feat(docs): Block 4 — docs-upload UI on the Documents page | merged
#950 | 2026-06-14 | 21:36:34 | 80d09aef | help | feat(help): Block 5 — module-guide help stubs (structure only) | merged
#951 | 2026-06-14 | 21:48:58 | d7c2b871 | driver-finance | feat(driver-finance): Block 6 (B7) — driver-inbox reporting (read-only) | merged
#952 | 2026-06-14 | 22:16:18 | 5ac90ef9 | catalogs | feat(catalogs): Block 7 — classes bulk-edit (batch-PATCH + multi-select) | merged
#953 | 2026-06-14 | 22:16:31 | 7fa266d0 | finance | docs(finance): Roles & Permissions design spec (foundational, VOID vs DELETE) | merged
#954 | 2026-06-14 | 22:20:06 | 1301ff7b | mileage | docs(mileage): §1A lifecycle correction — short@assign-bill, practical@delivery-invoice | merged
#955 | 2026-06-14 | 22:25:39 | c377e582 | finance | docs(finance): B9 §9A — escrow management screen (UI, Jorge-approved) | merged
#956 | 2026-06-14 | 22:37:33 | 00694203 | finance | docs(finance): RELAY internal-bank + diesel-code design spec (Section D #2) | merged
#957 | 2026-06-14 | 22:53:14 | 5dac3741 | finance | docs(finance): FH-1 Fixed Assets + Depreciation design spec (Finance … | merged
#958 | 2026-06-14 | 23:01:48 | f2218ed3 | finance | docs(finance): FH-3 Amortization Schedule Engine design spec (Finance Hub) | merged
#959 | 2026-06-14 | 23:31:36 | 62d43fd8 | finance | docs(finance): FH-2 Loan Wizard design spec (Finance Hub centerpiece) | merged
#960 | 2026-06-14 | 23:31:53 | c2ca4029 | finance | docs(finance): FH-4 Finance Calculator design spec (Finance Hub) | merged
#961 | 2026-06-14 | 23:28:01 | 2847cd5f | finance | docs(finance): FH-6 Tax Manager + FH-6a rendition design spec (Finance Hub) | merged
#962 | 2026-06-14 | 23:36:17 | 3ee3bbe1 | finance | docs(finance): FH-7 shared Unit Allocation control design spec (Finance Hub) | merged
#963 | 2026-06-14 | 23:41:13 | df5ecae6 | finance | docs(finance): FH-5 Bankruptcy Modeler design spec (Finance Hub, build last) | merged
#964 | 2026-06-14 | 23:56:36 | d9404f67 | finance | docs(finance): VOID-EVERYWHERE cross-cutting design spec (build packa… | merged
#965 | 2026-06-15 | 00:03:19 | 79dafe90 | finance | docs(finance): FH-8 Lease Contract + Unit Picker design spec (Legal<-… | merged
#966 | 2026-06-15 | 00:05:58 | a75d2d14 | finance | docs(finance): FH-1 Fixed Assets + Depreciation design spec (Finance … | merged
#967 | 2026-06-15 | 00:07:20 | aaa33424 | finance | docs(finance): FH-1 follow-up — inter-company leasing (owner vs opera… | merged
#968 | 2026-06-15 | 00:28:21 | ae66deed | finance | docs(finance): apply answered questions to FH-2 (trade-in) + FH-6 (ta… | merged
#969 | 2026-06-15 | 00:43:56 | c0d4bd67 | finance | docs(finance): FH-5 — posting decision LOCKED (POST TO BOOKS) | merged
#970 | 2026-06-15 | 00:45:56 | ae4135a0 | tasks | fix(tasks): task-create 400 — stop double-stringifying the request body | merged
#971 | 2026-06-15 | 00:53:37 | ba3f1195 | finance | fix(finance): stop double-stringifying money-path request bodies | merged
#972 | 2026-06-15 | 01:16:08 | 14e4966b | finance | docs(finance): VOID-EVERYWHERE — cash¦accrual basis for reversing-ent… | merged
#973 | 2026-06-15 | 01:18:50 | 3ead2e83 | accounting | feat(accounting): VOID-EVERYWHERE PR-1 — gated void engine for invoices + journal entries | merged
#974 | 2026-06-15 | 01:38:37 | fb6ea147 | nav | fix(nav): remove left-sidebar hover fly-out dropdown (block 17) | merged
#975 | 2026-06-15 | 01:53:42 | 499a3455 | api | fix(api): stop double-stringifying request bodies in the remaining no… | merged
#976 | 2026-06-15 | 02:37:29 | 47b8d6b0 | accounting | feat(accounting): D5 Account Register — read-only per-account running-balance ledger + audit tab | merged
#977 | 2026-06-15 | 04:34:51 | be3323ed | accounting | feat(accounting): VOID-EVERYWHERE PR-2 — gated void engine for bills (AP mirror) | merged
#978 | 2026-06-15 | 04:35:08 | 68bb77fd | finance | docs(finance): VOID-EVERYWHERE PR-3/PR-4 design — expenses + settlements void model | merged
#979 | 2026-06-15 | 04:43:54 | 1ea68ee8 | tasks | fix(tasks): Create Task 500/42501 — RLS scope sets the wrong GUC name | merged
#980 | 2026-06-15 | 04:44:00 | 287107aa | tasks | fix(tasks): planner 500/42P01 — join identity.users, not non-existent users.users | merged
#981 | 2026-06-15 | 05:08:39 | c7fcd97a | drivers | fix(drivers): deactivate sets status='Inactive' (driver stayed Active after deactivate) | merged
#982 | 2026-06-15 | 05:08:52 | 6c50ba8a | driver-finance | fix(driver-finance): mount orphaned escrow-deductions-pending routes (404) | merged
#984 | 2026-06-15 | 05:18:44 | 0d1f408c | customers | fix(customers): QBO customer-sync returned HTML (raw relative fetch -> wrong host) | merged
#985 | 2026-06-15 | 05:19:49 | d65dddb6 | units | fix(units): deactivate sets status='OutOfService' (mirror of driver deactivate fix) | merged
#986 | 2026-06-15 | 05:22:33 | e3022787 | insurance | fix(insurance): asset coverage 404'd for every unit (unit-id vs asset-id mismatch) | merged
#987 | 2026-06-15 | 06:26:18 | ced807e0 | maintenance | fix(maintenance): fleet-table KPIs 500 — non-existent unit_status enum values | merged
#988 | 2026-06-15 | 06:26:29 | bdbd7449 | dispatch | fix(dispatch): mount orphaned load settlement-summary route (404) | merged
#989 | 2026-06-15 | 06:29:51 | 3fe701e4 | maintenance | fix(maintenance): WO list shows unit_number, not raw unit UUID | merged
#990 | 2026-06-15 | 06:45:59 | 6dd54c87 | maintenance | fix(maintenance): dashboard KPIs 500 — second unit_status 'active' enum bug | merged
#992 | 2026-06-15 | 07:02:40 | b3820999 | routes | fix(routes): mount 7 orphaned non-financial routes the frontend calls (404s) | merged
#993 | 2026-06-15 | 07:05:55 | 953f4444 | ci | chore(ci): guard against orphaned routes (kills the 404-from-unmounted-route bug class) | merged
#994 | 2026-06-15 | 07:06:20 | c8c69ab8 | escrow | fix(escrow): drop dead /driver-finance/escrow call (404 on every Escrow Record load) | merged
#995 | 2026-06-15 | 11:16:41 | 9f476353 | routes | fix(routes): mount 4 more orphaned non-financial routes (batch 2) | merged
#996 | 2026-06-15 | 11:27:37 | cd33f921 | ci | chore(ci): guard against invalid enum literals (22P02) + fix 2 it surfaced | merged
#997 | 2026-06-15 | 11:24:53 | 487dad2b | drivers | fix(drivers): rehire validation walks the full chain (not just immediate prior) | merged
#998 | 2026-06-15 | 11:47:53 | dd73ae0d | maintenance | fix(maintenance): cap-12/cap-13 workers query mdata.units by non-existent operating_company_id | merged
#999 | 2026-06-15 | 12:22:50 | 1a3293af | migrations | fix(migrations): repair safety.fines→civil_fines (#0050 ordering collision) [GATED] | merged
#1001 | 2026-06-15 | 13:13:12 | 7f53d845 | ci | chore(ci): bump actions/checkout from 4 to 6 | merged
#1002 | 2026-06-15 | 13:24:59 | a306559d | ci | chore(ci): bump actions/setup-node from 4 to 6 | merged
#1005 | 2026-06-15 | 16:03:05 | 954f3fee | accounting | docs(accounting): GAP-EXPENSES-MODULE-COMPLETION design — verified, A1/A2 fork [DESIGN] | merged
#1006 | 2026-06-15 | 15:01:37 | 184da5a6 | accounting | feat(accounting): GAP-EXPENSES Phase 1 — accounting.expenses header (A1-staged foundation) [GATED] | merged
#1007 | 2026-06-15 | 15:34:44 | 46610e84 | accounting | docs(accounting): GAP-EXPENSES Phase 1.5 design — expense_lines cents… | merged
#1008 | 2026-06-15 | 16:02:35 | c6c57b71 | accounting | feat(accounting): GAP-EXPENSES Phase 1.5 — cents reconciliation + hard total=sum invariant [GATED] | merged
#1009 | 2026-06-15 | 17:16:17 | 846c5ff4 | maintenance | test(maintenance): cover copyToAccountingLines bill branch (Phase 1.5 follow-up) | merged
#1010 | 2026-06-15 | 18:52:35 | e2c76b65 | accounting | docs(accounting): GAP-EXPENSES Phase 2 design — expense → GL posting + reversing-JE void [DESIGN/GATED] | merged
#1011 | 2026-06-15 | 18:36:08 | 5448ca26 | insurance | fix(insurance): policy_unit has no is_active column — use removed_at (42703 → 500 on create/units) | merged
#1012 | 2026-06-15 | 19:27:26 | c2a545dc | deps | chore(deps): bump form-data from 4.0.5 to 4.0.6 | merged
#1013 | 2026-06-15 | 19:27:41 | a980876b | deps | chore(deps): bump js-yaml from 4.1.1 to 4.2.0 | merged
#1014 | 2026-06-16 | 00:26:53 | 24dd1a93 | accounting | docs(accounting): Phase 2 design reconciled to 6 locked decisions + seed SQL shown [DESIGN/GATED] | merged
#1015 | 2026-06-15 | 20:09:44 | f41b2e25 | accounting | feat(accounting): GAP-EXPENSES Phase 2 Step 2 — Uncategorized-Expenses seed (account+role) [GATED] | merged
#1016 | 2026-06-16 | 00:26:37 | 4d0d3226 | accounting | docs(accounting): GAP-EXPENSES Phase 2 Step 3 design — posting engine + reversing-JE void [DESIGN/GATED] | merged
#1017 | 2026-06-15 | 20:55:26 | d2a7fc8d | finance | feat(finance): FH-1 Fixed Assets — Step 1 data model (fixed_assets sc… | merged
#1018 | 2026-06-15 | 21:35:34 | 863a9f10 | accounting | feat(accounting): GAP-EXPENSES Phase 2 Step 3 — expense → GL posting … | merged
#1019 | 2026-06-15 | 21:55:34 | c6fd71e4 | accounting | fix(accounting): COA-UNCATEGORIZED-EXPENSE-QBO-RECONCILE — uncategorized_expense role → QBO #25; retire redundant #6999 seed | merged
#1020 | 2026-06-15 | 22:20:04 | 0eba27c0 | tracker | docs(tracker): master tracker v28 — fold 87 merged PRs (#924→#1018) + dated export | merged
#1021 | 2026-06-15 | 23:45:30 | cc9135b1 | accounting | fix(accounting): Step 3 posting — unmask markBatchFailed + prove balanced JE [TIER 1 · STOP before merge] | merged
#1022 | 2026-06-15 | 23:46:37 | 6ea814c7 | tracker | docs(tracker): log 3 follow-up backlog rows (876-878) | merged
#1023 | 2026-06-16 | 00:24:42 | d258bd59 | finance | feat(finance): FH-2 Loan Wizard — preview/compute-only, gated OFF [Tier 3] | merged
#1024 | 2026-06-16 | 00:27:04 | 4fe8cfd0 | trackers | docs(trackers): full reconciled pending inventory 2026-06-15 | merged
#1025 | 2026-06-16 | 00:29:30 | 053a3188 | tracker | docs(tracker): reconcile 30 DONE-DRIFT rows to DONE (code-on-main proof) | merged
#1027 | 2026-06-16 | 00:47:39 | 9fb80bf6 | finance | feat(finance): FH-4 Finance Calculator — pure modeling, gated OFF [Tier 3] | merged

## 03 Full Merged PRs
FULL MERGED-PR RECORD (sorted by PR #)
pulled from GitHub at generate time (2026-06-15)
PR # | Merge Date | Merge Time | SHA | Title
#480 | 2026-06-04 | 21:09:48 | a508abee | fix(audit): reconcile 8 KPI drifts production vs app (P8-AUDIT-KPI-DRIFTS)
#481 | 2026-06-04 | 21:28:28 | 8305a573 | feat(bulk): loads + invoices + bills bulk wire-up (BULK-5)
#482 | 2026-06-04 | 21:49:33 | e8f30475 | feat(bulk): BULK-6 audit filter, permission gate, CI coverage guard
#483 | 2026-06-04 | 22:17:06 | 38f74acd | feat(driver-finance): settlement auto-pay (P5-T5)
#484 | 2026-06-04 | 22:26:12 | 83db5fa6 | feat(accounting): bills-with-balance dropdown (P5-T8)
#485 | 2026-06-04 | 22:45:07 | 93eb4bc2 | feat(accounting): reconciliation workspace UI (P5-T2)
#486 | 2026-06-04 | 22:55:06 | a32d00bf | fix(customers): CUST-BILLING-500 closure — ar_aging guard + CI verify
#487 | 2026-06-04 | 23:03:49 | e307ae10 | feat(assignments): quicksave on truck/trailer click (P5-T19)
#488 | 2026-06-04 | 23:15:33 | ed6a056c | feat(banking): Plaid frontend link + daily cron (P5-T1.3)
#489 | 2026-06-04 | 23:16:47 | 584bf29c | feat(accounting): manual JE 2-step modal (P5-T11)
#490 | 2026-06-04 | 23:37:16 | 90e1e4ab | feat(payroll): TMS↔QBO Payroll integration Option B (P5-T25)
#491 | 2026-06-04 | 23:44:52 | 5dd224be | feat(qbo): TRK migration runbook execution (P5-T24)
#492 | 2026-06-04 | 23:38:21 | 78f8d4d3 | feat(ap): bill payment sub-rows for partial payments (P5-T9)
#493 | 2026-06-05 | 00:16:29 | 2961d435 | feat(ifta): quarterly preparer Steps 1+2 — state miles + gallons (P6-T2)
#494 | 2026-06-05 | 00:14:09 | 90ee3705 | feat(reports): wire 5 canonical reports to real backend (P6-T1)
#495 | 2026-06-04 | 23:59:09 | 00e21273 | feat(safety): dashboard 7-10 day active filter (P5-T18)
#496 | 2026-06-05 | 00:18:18 | 905f8811 | feat(equipment): dual-confirmation transfer WF-047 (P5-T21)
#497 | 2026-06-05 | 01:20:48 | bdbcad8a | feat(maint): OOS severe downtime estimate on work order detail (P5-T16)
#498 | 2026-06-05 | 00:35:35 | 50d29c03 | feat(ifta): quarterly preparer Steps 3+4 — tax owed + CSV export (P6-T3)
#499 | 2026-06-05 | 01:28:05 | 3249afc7 | feat(reports): scheduled reports auto-email + custom builder (P6-T4)
#500 | 2026-06-05 | 01:33:07 | 45d4362d | feat(qbo-sync): Chart of Accounts pull + reconcile (QBO-SYNC-1)
#501 | 2026-06-05 | 01:44:49 | a3107b9c | feat(qbo-sync): Products & Services items pull + WO category fix (QBO-SYNC-2)
#502 | 2026-06-05 | 01:58:32 | 22838aa7 | feat(factoring): Faro CSV import (P5-T22)
#503 | 2026-06-05 | 02:01:33 | e4354c2e | feat(qbo-sync): Customers + Vendors pull/reconcile (QBO-SYNC-3)
#504 | 2026-06-05 | 02:06:41 | 41c9a61d | feat(qbo-sync): drift detection + sync cron (QBO-SYNC-4)
#505 | 2026-06-05 | 02:22:48 | ba7d8b2d | feat(qbo-sync): drift detection + sync cron impl (QBO-SYNC-4)
#506 | 2026-06-05 | 02:18:38 | 5e98a1fd | feat(compliance): Form 2290 HVUT filing (P8-COMP-1)
#507 | 2026-06-05 | 02:31:13 | 0bd30008 | fix(db): renumber QBO drift log migration to 0379
#508 | 2026-06-05 | 02:40:41 | cab54b74 | feat(compliance): drug & alcohol program (P8-COMP-2)
#510 | 2026-06-05 | 02:50:03 | 31d5b3c3 | chore(rules): strengthen dual-lane never-idle
#511 | 2026-06-05 | 03:09:02 | 892529ed | feat(compliance): CSA BASIC score automation (P8-COMP-3)
#512 | 2026-06-05 | 03:19:15 | 2fe640a6 | feat(compliance): FMCSA SAFER verification automation (P8-COMP-4)
#513 | 2026-06-05 | 03:19:20 | cdae0cfe | chore(rules): add PASS-4 AUDIT-FIX queue order to dual-lane never-idle
#514 | 2026-06-05 | 03:30:50 | 6c17f370 | feat(catalog): generic catalog framework backend (CATALOG-1)
#515 | 2026-06-05 | 03:51:56 | 7653c9ed | feat(catalog): generic catalog framework frontend (CATALOG-2)
#517 | 2026-06-05 | 04:00:01 | ed512e1d | chore(rules): enforce 5min crash recovery + lane STATUS on every reply
#518 | 2026-06-05 | 04:56:58 | 35c96727 | feat(catalog): CATALOG-3 stub purge + header counts (Wave 18)
#519 | 2026-06-05 | 04:27:05 | 4f857bba | hotfix(deploy): unblock Render preDeploy — 0383 checksum override
#520 | 2026-06-05 | 04:39:19 | 0a3ce279 | feat(pwa): PWA-POLISH-1 i18n EN/ES + iPhone Safari ITP storage (Wave 18)
#522 | 2026-06-05 | 05:11:03 | 04d92eee | chore(rules): POST-PASS4 17-block index + Jorge supersession gate
#523 | 2026-06-05 | 05:33:06 | 0915467e | feat(usmca): USMCA-1 multi-carrier RLS hardening (Wave 19 Lane B)
#524 | 2026-06-05 | 05:45:00 | 053835fe | feat(usmca): USMCA-2 carrier seed + bootstrap (Wave 19 Lane A)
#526 | 2026-06-05 | 06:18:16 | fb24571b | feat(pwa): PWA-POLISH-2 web push completion (Wave 20 Lane B)
#527 | 2026-06-05 | 06:10:41 | 933cb331 | feat(usmca): USMCA-3 soft-launch toggle + audit trail (Wave 20 Lane A)
#528 | 2026-06-05 | 06:32:34 | a6a69dc3 | feat(audit): FINAL-AUDIT-PASS per-module audit + 3 CI guards (Wave 21)
#529 | 2026-06-05 | 06:54:42 | 47441a26 | feat(audit-fix): AUDIT-FIX-1 bulk frontend wire-up (AF-1 Lane A)
#530 | 2026-06-05 | 07:22:27 | 991261ad | feat(audit-fix): AUDIT-FIX-2 column resize framework (AF-1 Lane B)
#531 | 2026-06-05 | 08:04:41 | 58f55069 | feat(audit-fix): AUDIT-FIX-3 customers/vendors list view (AF-2 Lane A)
#532 | 2026-06-05 | 08:43:15 | f45ae86f | feat(audit-fix): AUDIT-FIX-4 responsive breakpoint pass (AF-2 Lane B)
#533 | 2026-06-05 | 09:19:14 | 1a03be0b | feat(audit-fix): AUDIT-FIX-5 nested box removal (AF-3 Lane A)
#534 | 2026-06-05 | 09:05:20 | dc8af3fb | feat(audit-fix): AUDIT-FIX-6 route enumeration CI guard (AF-3 Lane B)
#535 | 2026-06-05 | 09:32:09 | dfeed05a | feat(audit-fix): AUDIT-FIX-7 blank page wire-up (AF-4 Lane A)
#536 | 2026-06-05 | 09:48:37 | d897ce85 | feat(audit-fix): AUDIT-FIX-8 WO category wire complete (AF-4 Lane B)
#537 | 2026-06-05 | 10:12:29 | f59edef9 | feat(audit-fix): AUDIT-FIX-9 flaky endpoints fix (AF-5 Lane A)
#538 | 2026-06-05 | 10:25:14 | a2c8f313 | feat(audit-fix): AUDIT-FIX-11 QBO sync status endpoints (AF-5 Lane B)
#539 | 2026-06-05 | 10:45:16 | 509d7527 | feat(audit-fix): AUDIT-FIX-10 mobile status bar collapse (AF-6 Lane A)
#540 | 2026-06-05 | 11:06:41 | 6493d15f | feat(audit-fix): AUDIT-FIX-15 status bar compact at 1366 + SubTabRow (AF-6 Lane B)
#541 | 2026-06-05 | 11:19:29 | 616a2006 | feat(audit-fix): AUDIT-FIX-12 accounting bills normalize (AF-7 Lane A)
#542 | 2026-06-05 | 11:33:00 | 6fd89621 | feat(audit-fix): AUDIT-FIX-13 customers/vendors pagination + anchors (AF-7 Lane B)
#543 | 2026-06-05 | 11:49:09 | b3c32744 | feat(audit-fix): AUDIT-FIX-16 invoice create from load flow (AF-8 Lane A)
#544 | 2026-06-05 | 11:58:00 | 6c6d5658 | feat(audit-fix): AUDIT-FIX-17 factoring power-user UX (AF-8 Lane B)
#545 | 2026-06-05 | 11:55:34 | 92c55905 | hotfix(db): 0385 migration checksum override for Render preDeploy
#546 | 2026-06-05 | 12:03:46 | da7c736f | hotfix(driver-pwa): fix TS6133 unused postPushAck; add CI build step
#547 | 2026-06-05 | 12:03:33 | 7e100367 | hotfix(render): build driver PWA from monorepo root
#548 | 2026-06-05 | 12:21:24 | 618ac1ea | feat(audit-fix): AUDIT-FIX-14 subtab real routes (AF-9 Lane A)
#549 | 2026-06-05 | 13:39:09 | 2ff3d854 | feat(closure): CLOSURE-1 PASS-7 smoke verify for 17 AUDIT-FIX blocks
#550 | 2026-06-05 | 14:11:18 | adf7a5cb | feat(closure): CLOSURE-4 P5-T12 auto-deductions from settlements
#551 | 2026-06-05 | 14:12:27 | 6b067c5a | feat(closure): CLOSURE-5 P5-T13 settlement dispute workflow
#552 | 2026-06-05 | 13:54:38 | 454a7ab9 | feat(closure): CLOSURE-3 P5-T7 CC bill payment workflow
#553 | 2026-06-05 | 14:27:47 | 40e15042 | feat(closure): CLOSURE-6 P5-T14 team split commission allocation
#554 | 2026-06-05 | 14:26:38 | fde9266d | docs(closure): reconcile CLOSURE-3 delta + C-3 wave tracker
#555 | 2026-06-05 | 14:35:50 | 958e5418 | feat(closure): CLOSURE-7 P5-T17 road service ticket integration
#556 | 2026-06-05 | 14:47:15 | 9884bf05 | feat(closure): CLOSURE-8 archive test users from production list
#558 | 2026-06-05 | 14:36:42 | 63625c4e | docs(closure): V2 tracker pass 5/30 wave C-4
#559 | 2026-06-05 | 14:51:55 | f1437934 | feat(closure): CLOSURE-9 maintenance trailer profile (11 sections + API)
#560 | 2026-06-05 | 15:06:49 | d92d72e3 | chore(closure): dispatch CLOSURE-10 maint parts catalog (wave C-5 lane B)
#561 | 2026-06-05 | 15:07:30 | b7bae9b1 | chore(closure): dispatch CLOSURE-11 maint services catalog (wave C-5 lane A)
#563 | 2026-06-05 | 15:17:10 | e457dcef | chore(closure): dispatch CLOSURE-12 payroll integration (wave C-6 lane B)
#564 | 2026-06-05 | 15:32:02 | d6a6336d | chore(closure): dispatch CLOSURE-13 USMCA July launch (wave C-6 lane A)
#565 | 2026-06-05 | 15:43:27 | bf4d6e30 | chore(closure): dispatch CLOSURE-14 deep audit A (wave C-7 lane B)
#568 | 2026-06-05 | 16:03:05 | e90f2aeb | chore(closure): dispatch CLOSURE-15 deep audit B (wave C-7 lane A)
#570 | 2026-06-05 | 15:58:15 | b9ea2be2 | feat(closure): CLOSURE-14 deep audit A implementation (wave C-7 lane B)
#571 | 2026-06-05 | 16:38:03 | bfb56a9a | chore(closure): dispatch CLOSURE-16 deep audit C (wave C-8 lane B)
#572 | 2026-06-05 | 16:24:30 | ad58b278 | chore(closure): dispatch CLOSURE-17 ON-HOLD triage (wave C-8 lane A)
#573 | 2026-06-05 | 16:14:55 | 083c5b0e | docs(closure): V2 tracker Pass 15/30 + wave C-8 dispatch
#574 | 2026-06-05 | 16:22:56 | 543af0f3 | docs: embed 63-block GAP de-dup plan in rules and tracker
#575 | 2026-06-05 | 17:05:44 | b5f4a6c9 | chore(closure): CLOSURE-19 SEC audit (wave C-10 lane B)
#576 | 2026-06-05 | 17:14:34 | 1345ed75 | chore(closure): CLOSURE-18 PERF audit (wave C-10 lane A)
#578 | 2026-06-05 | 17:31:58 | 421fb918 | chore(closure): CLOSURE-20 A11Y audit (wave C-11 lane A)
#579 | 2026-06-05 | 17:40:08 | 0df2bfa1 | chore(closure): CLOSURE-21 monitoring setup (wave C-11 lane B)
#580 | 2026-06-05 | 18:05:39 | 6b26405d | feat(closure): CLOSURE-22 CI hardening — branch protection + deploy gate
#581 | 2026-06-05 | 17:52:34 | f67c7ec6 | feat(closure): CLOSURE-23 DR backup audit — PITR verify + restore drill
#582 | 2026-06-05 | 19:27:42 | 07fdc179 | CLOSURE-24: Operator onboarding wizard + sample data + walkthroughs
#583 | 2026-06-05 | 19:28:01 | d4c86872 | CLOSURE-25: Operator runbooks (9 workflow runbooks) + /help index
#584 | 2026-06-05 | 18:56:44 | d46ddb44 | CLOSURE-26: i18n audit foundation (EN/ES + locale preference)
#585 | 2026-06-05 | 18:44:28 | 238681f3 | CLOSURE-27: mobile/ultrawide edge breakpoint guardrail pack
#586 | 2026-06-05 | 21:09:32 | 73cba883 | URGENT CLOSURE-31: restore /customers + /vendors default to prior design (regression from #531)
#587 | 2026-06-05 | 19:13:06 | cbc2cccb | docs(closure): materialize CLOSURE-29 audit-fix slots
#588 | 2026-06-05 | 19:33:42 | 5fd0dd8a | feat(closure): add CLOSURE-28 data migration runbooks
#589 | 2026-06-05 | 21:52:05 | 0f1f845e | CLOSURE-C13: wire operator onboarding + runbooks (routes/registry/sidebar)
#590 | 2026-06-05 | 20:52:22 | 7b1c49f7 | fix(closure-28): honor intentional migration gaps 397-402 in chain gate
#591 | 2026-06-05 | 21:19:30 | e94e9552 | fix(healthz): relax r2.head_bucket probe sensitivity
#592 | 2026-06-05 | 21:57:35 | 5c5c4bef | fix(healthz): relax postgres.select1 + migrations.ledger budgets
#593 | 2026-06-05 | 22:41:05 | fa4a800a | CLOSURE-30 PASS-8 pre-prod smoke
#594 | 2026-06-05 | 23:17:51 | fb7aeae0 | spec: CLOSURE-32 EXPANDED + PASS-8-RUNTIME with Jorge amendments
#595 | 2026-06-06 | 00:21:53 | 061ee6bd | security(rls): add assertCompanyMembership to luciaBypass routes (M2 CRITICAL CLOSURE-32)
#596 | 2026-06-06 | 03:29:30 | bb6d9a20 | chore(gitignore): exclude PASS-8 test artifact paths
#597 | 2026-06-06 | 03:46:35 | 9efca115 | docs(trackers): orphan cluster fully reconciled; document fresh-DB plan
#598 | 2026-06-06 | 04:31:15 | 19c838ac | security(ci): permanent luciaBypass guard-pattern verification + CLOSURE-32 findings (M2)
#599 | 2026-06-06 | 05:10:35 | 535c0205 | fix(rls): add OCI scoping to mdata.drivers (H1 CLOSURE-32)
#600 | 2026-06-06 | 05:37:57 | 067a833d | docs(audit): CLOSURE-32 H1 RESOLVED via PR #599 (mdata.drivers OCI scoping)
#601 | 2026-06-06 | 21:19:34 | 61e8f28f | SAFETY-TRUST: initial recommendations doc
#602 | 2026-06-06 | 21:51:34 | 114bda50 | DESIGN REFERENCE: canonical docs + May 27 inspection artifacts
#603 | 2026-06-06 | 22:17:54 | ca5530b5 | docs: add No-Design-Changes-Without-Preview governance rule
#605 | 2026-06-06 | 22:33:43 | 46bc3b7f | TIER 1 TRUST: 13-block dispatch spec
#606 | 2026-06-06 | 22:59:04 | 7ba5cc32 | feat(observ): GAP-OBSERV-FOUNDATION-RESCOPED — PII scrub + request_id + admin route + Sentry provisioning
#607 | 2026-06-06 | 22:45:05 | 975fb7a2 | docs(runbooks): lane isolation git worktree protocol
#608 | 2026-06-06 | 22:55:26 | 15c24326 | WAVE-1: settlement blocks spec (6 blocks, driver + company settlement)
#609 | 2026-06-06 | 23:23:31 | 48e2cfb5 | DEDUPE AUDIT: 19 new blocks vs 91 existing GAP blocks
#610 | 2026-06-06 | 23:08:23 | 82ad6fb7 | WAVE-1 BLOCK 1: settlement audit RBC
#611 | 2026-06-06 | 23:39:36 | 0fc9a486 | DISPATCH SPECS: Tiers 1.5-4 remaining 29 blocks
#612 | 2026-06-06 | 23:50:51 | d1102f10 | docs(dispatch): S5-A seam note + T7 HOLD dependency per dedupe audit
#613 | 2026-06-07 | 01:20:07 | 24bfbca4 | chore(config): add Sentry env vars to .env.example
#614 | 2026-06-06 | 23:32:34 | 1c2080d4 | feat(deps): Dependabot config + runbook (GAP-DEPENDABOT-VERIFY Block 11)
#615 | 2026-06-08 | 22:09:00 | a7c2dc5c | chore(ci): bump actions/setup-node from 4 to 6
#616 | 2026-06-09 | 06:43:21 | 564258e4 | chore(ci): Bump actions/upload-artifact from 4 to 7
#617 | 2026-06-09 | 06:43:24 | 83993fb8 | chore(ci): bump actions/checkout from 4 to 6
#618 | 2026-06-07 | 00:07:34 | 11b6aff2 | feat(ci): activate migration rename/edit guard (GAP-MIGRATION-RENAME-CI-GUARD)
#620 | 2026-06-08 | 22:08:08 | 82e4beb7 | chore(deps): Bump fast-uri from 3.1.0 to 3.1.2
#623 | 2026-06-08 | 22:07:52 | 59867ddd | chore(deps): Bump ws from 8.20.0 to 8.21.0
#624 | 2026-06-08 | 22:08:18 | d5bd769b | chore(deps): Bump qs from 6.15.1 to 6.15.2
#626 | 2026-06-08 | 22:08:34 | 3dcf1525 | chore(deps): Bump fast-xml-builder from 1.1.5 to 1.2.0
#628 | 2026-06-08 | 22:03:04 | 46ca7758 | fix(predeploy): remove --verify-content from preDeployCommand (HOTFIX-PREDEPLOY)
#629 | 2026-06-07 | 00:45:19 | 8c830c31 | docs(audit): GAP-CRON-AUDIT-AND-RETUNE Block 13 — full cron inventory (46 jobs, 3 FIX items)
#630 | 2026-06-07 | 01:04:19 | 90228d41 | fix(crons): add is_active filter to compliance-reminder, deadhead-refresh, lane-profitability-refresh
#631 | 2026-06-07 | 01:06:17 | 430b5425 | feat(security): OWASP security headers via @fastify/helmet — GAP-SECURITY-HEADERS Block 10
#633 | 2026-06-07 | 06:33:28 | 93ac7dea | feat(audit): GAP-87 — universal read-only audit log viewer (/admin/audit-log)
#634 | 2026-06-07 | 01:29:32 | c4831eaf | docs(dispatch): populate docs/dispatch/batches/ with 91 individual GAP block specs
#635 | 2026-06-07 | 01:36:47 | 4f111a73 | feat(owner): GAP-65 Owner Today's Attention Top-5 Aggregator
#636 | 2026-06-07 | 01:45:28 | 4278ce6c | feat(safety): GAP-81 Drug & Alcohol Program Management — FMCSA Part 382
#637 | 2026-06-07 | 01:49:14 | 80e0ba51 | fix(gap-81): register drug-alcohol worker and routes in index.ts
#639 | 2026-06-07 | 13:06:19 | 31281d6e | feat(idempotency): HTTP idempotency keys for mutating financial endpoints (GAP-IDEMP-KEYS)
#640 | 2026-06-07 | 02:05:05 | d4ddbb79 | feat: GAP-82 medical card expiry tracking
#642 | 2026-06-07 | 02:17:37 | 2a626f89 | refactor(home): thin role-router with DefaultHome fallback
#643 | 2026-06-07 | 05:55:02 | 036c691d | fix(db): 0327 drug_alcohol_program grant role app_user → ih35_app (GAP-81 hotfix)
#644 | 2026-06-07 | 07:18:09 | 08e136e9 | feat(gap-83): ELD audit trail read-only viewer
#645 | 2026-06-07 | 07:35:56 | a160cdae | feat(gap-66): dispatcher home role-specific view
#646 | 2026-06-07 | 06:13:40 | cd8ce4bb | fix(db): add RLS to safety.da_* tables (GAP-81)
#647 | 2026-06-07 | 06:47:08 | 96f9b5c1 | fix: restore SAFETY_CANONICAL_TAB_COUNT reference after home router refactor
#648 | 2026-06-07 | 06:24:07 | dd21e0ba | feat(migrations): UTC-timestamp naming — eliminate parallel-lane sequence collisions
#649 | 2026-06-07 | 06:51:47 | 1604ea83 | feat(safety): GAP-84 DOT inspection clean-rate gap-close
#650 | 2026-06-07 | 06:33:38 | bc6df905 | feat(manifest): per-block .block-ready/<block-id>.json — eliminate manifest merge conflicts
#651 | 2026-06-07 | 06:50:58 | eff671f8 | feat(ci): GAP-PREMERGE-GATES-EXPAND — three required pre-merge gates for GAP-81 failure class
#652 | 2026-06-07 | 07:11:06 | 5619e99c | feat(home): GAP-67 read-only Accounting Home for Accountant role
#653 | 2026-06-07 | 07:42:57 | c7049104 | feat(home): GAP-68 Safety Officer role-specific home view
#654 | 2026-06-07 | 08:25:36 | 06bb21ae | feat(home): GAP-69 Driver Manager role-specific home view
#655 | 2026-06-07 | 08:44:15 | 37e9e505 | feat(units): GAP-85 permit and toll tag tracking
#657 | 2026-06-07 | 10:14:43 | 67d92402 | feat(search): GAP-89 universal Cmd-K quick switcher
#658 | 2026-06-07 | 10:44:01 | 4e81e632 | feat(ui): GAP-91 mobile responsive audit infrastructure
#659 | 2026-06-07 | 11:42:43 | 699549bf | feat(flags): GAP-92 per-tenant and per-user feature flag system
#660 | 2026-06-07 | 12:07:33 | 6f4870bb | feat(gap-7): severe repair fleet restore estimate + Owner home card
#661 | 2026-06-07 | 12:30:50 | 7343d1f6 | feat(gap-8): inline dispatch assignment quicksave
#662 | 2026-06-07 | 13:09:00 | 081794ff | feat(gap-23): 4-tier Samsara cache hierarchy
#663 | 2026-06-07 | 13:29:28 | 1822b002 | feat(gap-10-delta): load cancellations analytics report
#664 | 2026-06-07 | 13:26:33 | 7b237c70 | feat(gap-14): Pre-Dispatch Validation Panel in BookLoadModalV4
#665 | 2026-06-07 | 13:36:03 | d17ca3f7 | feat(analytics): GAP-30 late-arrival rate analytics (driver + customer)
#666 | 2026-06-07 | 13:45:42 | fd6698fb | feat(gap-11-delta): wire UploadZone into expense create form
#667 | 2026-06-07 | 14:28:54 | ab18b92d | feat(gap-34): driver PWA dispatch view with stop actions
#668 | 2026-06-07 | 14:42:20 | ed5e1565 | fix(db): grant notifications schema + audit.row_changes_id_seq to ih35_app
#669 | 2026-06-07 | 15:21:24 | c3cc4323 | feat(geofencing): GAP-39 formal geofence state machine (G17)
#670 | 2026-06-07 | 15:16:14 | 44c0fdab | fix(cors): add app.ih35dispatch.com to default allowed origins
#671 | 2026-06-07 | 15:47:41 | 04b49e41 | GAP-38: damage continuity chain + WF-027 insurance auto-claim (G15)
#672 | 2026-06-07 | 16:07:57 | b0b0a87a | feat(reports): GAP-41 nine-category Reports Hub (WF-061)
#673 | 2026-06-07 | 16:38:48 | bad8de9d | feat(safety): GAP-40 damage photo EXIF chain-of-custody (WF-058)
#674 | 2026-06-07 | 17:02:18 | cf204da4 | feat(reports): GAP-44 Form 425C exhibits A-F auto-build
#675 | 2026-06-07 | 18:04:53 | 4165a305 | feat(maintenance): GAP-49 pre-flight DVIR severity tagging (49 CFR §396.11)
#676 | 2026-06-07 | 17:48:01 | 1c70559e | feat(drivers): GAP-48 driver operations depth — 12 read-only sub-views
#677 | 2026-06-07 | 18:34:16 | 26809ba8 | feat(safety): GAP-50 AI pre/post trip photo comparison
#678 | 2026-06-07 | 18:36:09 | 837af3ba | feat(maintenance): GAP-63 CAP-13 brake wear predictive maintenance
#679 | 2026-06-07 | 19:01:08 | 2f7feb9c | feat(maintenance): GAP-62 CAP-12 tire tread wear tracking
#680 | 2026-06-07 | 19:18:53 | 0924a53e | feat(sidebar): add Driver Hub entry, relabel Drivers→Drv Profile, apply custom order
#681 | 2026-06-07 | 19:20:15 | 8b16d56c | feat(fuel): GAP-61 CAP-11 fuel card fraud alerts
#682 | 2026-06-07 | 18:31:50 | 72ad0a47 | feat(drivers): GAP-18 unified driver communications timeline tab
#683 | 2026-06-07 | 19:18:12 | af0e13f4 | feat(driver-finance): prereq-B — createSettlementDeduction() service (unblocks Driver Hub requests)
#684 | 2026-06-07 | 18:41:14 | 3e6b3ee2 | feat(ci): prereq-A — 4th pre-merge gate: schema-level GRANT check (closes login-outage class)
#685 | 2026-06-07 | 18:58:55 | d5144e15 | feat(dispatch): GAP-24 Samsara freshness indicator pill (L1-L4, green/amber/red)
#686 | 2026-06-07 | 19:18:17 | f02797a4 | feat(dispatch): GAP-19 detention billable manager-approval gate
#687 | 2026-06-07 | 19:07:42 | df0fb6d4 | feat(insurance): Block 5 — GAP-86 multi-vehicle policy creator + bill schedule via createBill()
#688 | 2026-06-07 | 19:29:14 | da76ba1a | feat(dispatch): live ETA columns — driver status, Samsara ETA, on-time prediction
#689 | 2026-06-07 | 19:31:06 | 362f7573 | docs(dispatch): follow-up block specs from June 7 sprint
#690 | 2026-06-07 | 19:39:37 | 9b952b1b | fix(ci): verify:no-duplicate-routes reads src/ TypeScript instead of dist/
#691 | 2026-06-07 | 23:59:38 | 4f9f6a7e | feat(edi): GAP-70 EDI integration foundation (204/214/210/990)
#692 | 2026-06-07 | 20:58:18 | a7a4356f | feat(driver-finance): Block C — settlement deduction cap (net floor + roll-over)
#693 | 2026-06-07 | 21:42:04 | de039850 | feat(dispatch): Block H — detention approval auto-notifies customer
#694 | 2026-06-07 | 20:29:46 | 6494a9b6 | feat(driver-hub): Block 7 — cash advance request approve/deny + settlement deduction
#695 | 2026-06-07 | 21:19:55 | db2b3800 | fix(insurance): GAP-86 forward-fix — close #687 double-bill vulnerability
#696 | 2026-06-07 | 20:35:39 | a1475f83 | feat(insurance): Block G — Certificate of Insurance (COI) PDF
#697 | 2026-06-07 | 21:37:24 | 53abfa1e | fix(db): Block J — systemic migration silent-skip fix + master_data grant repair
#698 | 2026-06-07 | 21:24:16 | 1ae55340 | fix(migrations): rename Block C migration to 12-digit runner format
#699 | 2026-06-07 | 22:17:37 | c2757c14 | feat(insurance): Block D — policy renewal (clone-forward)
#700 | 2026-06-07 | 23:00:07 | bd38ae65 | Block F — Insurance policy cancellation + unearned-premium refund
#701 | 2026-06-07 | 22:28:36 | 8db0e18d | feat(compliance): Block 16 — Compliance Dashboard
#702 | 2026-06-07 | 22:28:21 | a01a601d | feat(insurance): Block E — fleet add/remove units mid-term
#703 | 2026-06-07 | 23:59:22 | 813af497 | Feat/acct qbopar 00 design lock
#704 | 2026-06-07 | 23:59:31 | 5cd2be2b | feat(accounting): GAP-20 Recurring Bills — templates, generator worker, frontend tab
#707 | 2026-06-08 | 00:00:12 | a149ccfa | feat(gap-25): active driver set 15-min recompute cache
#708 | 2026-06-07 | 23:54:53 | 5651ec7d | feat(trust-t5): TIER1 Block 5 — Double-entry DB enforcement guard + integration test + docs
#709 | 2026-06-08 | 00:00:02 | f0e57270 | feat(acct-block-10): ledger-backed account balances view per account/period
#710 | 2026-06-07 | 23:59:33 | ed4316bb | feat(acct): CA-02 — Shared ListView component
#711 | 2026-06-07 | 23:59:20 | 474c5865 | fix: re-attach 10 missing audit triggers (trigger drift remediation)
#713 | 2026-06-08 | 04:40:56 | 421039de | feat(acct-qbopar-01): QBO-parity account type & detail type catalog backend
#714 | 2026-06-08 | 02:11:51 | 592ba994 | fix(acct): enable RLS on bill_lines, expense_lines, line_category_load_required
#715 | 2026-06-08 | 02:12:02 | 50dcb8bb | feat(acct): ACCT-COA-CANONICALIZATION — catalogs.accounts canonical COA + QBO link backfill
#716 | 2026-06-08 | 02:11:57 | 95767b7d | docs(accounting): role-bindings bookkeeper worksheet for CPA approval
#717 | 2026-06-08 | 02:12:08 | 5754d1f8 | feat(sidebar): add Insurance entry after Drivers
#718 | 2026-06-08 | 02:12:16 | bbcf099f | docs(specs): lock cash flow + insurance-safety connection + dispatch spec files
#719 | 2026-06-08 | 02:12:27 | ea1f5020 | docs(specs): lock dispatch geofence timing model + insurance blueprint + CI guard spec
#720 | 2026-06-08 | 02:26:50 | b630fa11 | docs(dispatch): lock dispatch ETA model, board view logic, settlement trip linking, UI rules, defect catalog
#721 | 2026-06-08 | 02:31:37 | 5d20657c | docs(lockdown): commit IH35 full lockdown specs — insurance, cashflow, dispatch, global UI rules
#722 | 2026-06-08 | 02:23:58 | ea1b6b11 | feat(gap-26): border 1000m geofences + customs clearance time
#723 | 2026-06-08 | 02:25:10 | 7f87f21b | feat(ui-contract): lock Global Sort Rule + CI guard (#720)
#724 | 2026-06-08 | 03:27:11 | 331a0fc8 | feat(gap-27): daily geofence reconciliation report
#726 | 2026-06-08 | 02:35:58 | 833469aa | feat(gap-28): layover time computation (>8h gap)
#728 | 2026-06-08 | 02:34:33 | 554c76b1 | docs(specs): lock navigation pattern rule — flat sidebar, top-bar hover-dropdowns
#729 | 2026-06-08 | 02:42:50 | f01571da | feat(gap-29): booking-gap time per dispatcher analytics
#730 | 2026-06-08 | 03:02:14 | 6a33208d | docs(specs): lock global type/size baseline + 17 deferred feature tracker
#731 | 2026-06-08 | 04:54:31 | 3fcd46ce | feat(drivers): add Load History tab on driver detail
#732 | 2026-06-08 | 04:41:10 | 747c126b | fix(sort): enable sort on description column in useCatalogQuery (never-defer)
#733 | 2026-06-08 | 04:27:10 | 75ec1fe6 | fix(ci): resolve 6 failing checks from GAP-26/28/29 merge (build-typecheck, ts-strict-null, rls-migration-scan, security-audit, perf-audit, pass-8)
#734 | 2026-06-08 | 05:03:59 | 231db326 | feat(dispatch): add Driver Pay, Settlement, Geofence Timeline tabs to LoadDetailDrawer
#735 | 2026-06-08 | 05:14:11 | 492d33ce | feat(dispatch): P0 Block 2 — NB→SB pre-settlement trip linking (MUST 8a.0.5.12)
#736 | 2026-06-08 | 03:38:36 | 3bab3041 | fix(ci): required-checks gate hardening — close #729 hole, add pass-8 to required set
#737 | 2026-06-08 | 06:45:49 | f6600f9a | feat(insurance): 4-step policy create wizard + atomic transaction + sidebar regression fix (#722)
#738 | 2026-06-08 | 05:00:36 | 5ccbbaa0 | docs(accounting): bookkeeper worksheet v1.1 + factoring accounting structure proposal
#739 | 2026-06-08 | 04:40:49 | f84e4758 | docs(specs): lock factoring packet auto-assembly + cross-border dispatch + load profitability specs
#740 | 2026-06-08 | 05:08:39 | 38e1626f | feat(acct-qbopar-03): Chart of Accounts list on ListView
#741 | 2026-06-08 | 05:21:46 | 6da62788 | docs(dispatch): commit all 13 dispatch block specs + module spec + architectural delta + preamble
#742 | 2026-06-08 | 05:29:51 | 985321db | docs(dispatch): lock lane enforcement + allowed_files per block
#743 | 2026-06-08 | 05:30:57 | 831bf59e | feat(dispatch): Block 9 DISP-PROFITABILITY — Trip Profitability + SettlementProfitabilityCard (Lane B)
#744 | 2026-06-08 | 05:35:50 | 55126cf8 | feat(dispatch): DISP-CASHFLOW-LINK — CI guard verifying dispatch events map to cash-flow operating section
#746 | 2026-06-08 | 06:09:22 | 16c0ed98 | feat(dispatch): DISP-DRAWER-WIRE Block 12 — wire all surfaces + mount 4 stub tabs
#747 | 2026-06-08 | 05:39:38 | ea0378a5 | feat(dispatch): DISP-PLANNERS — Driver, Truck & Loads planner pages (LANE B Block 6)
#748 | 2026-06-08 | 05:53:11 | 51f5a077 | fix(ts): remove unused variable in loadProfit.ts
#749 | 2026-06-08 | 05:40:29 | 6cf8fa7b | docs(sidebar): reconcile all sidebar docs to live 21-item array
#750 | 2026-06-08 | 05:53:52 | 88cc69f0 | feat(dispatch): LANE B Block 7 — DISP-FACTORING-PACKET
#751 | 2026-06-08 | 06:18:25 | 9ae9db2e | feat(dispatch): DISP-KANBAN-STATES Block 3 — 7-column operational kanban
#752 | 2026-06-08 | 06:32:26 | 183f2e55 | feat(dispatch): DISP-OVERVIEW Block 1 — default Overview command center
#753 | 2026-06-08 | 06:49:42 | caeda1d2 | feat(dispatch): DISP-QUEUES-NAV Block 2 — top-bar queue nav with live badges
#754 | 2026-06-08 | 13:59:55 | 26ea5b46 | docs(lockdown): canonical locked decisions — sidebar 23-array, cash flow, insurance, process locks, CI guard specs
#755 | 2026-06-08 | 07:03:15 | 552e8479 | chore(lockdown): anti-regression CI guards (sidebar, cash-flow, insurance)
#756 | 2026-06-08 | 07:03:51 | 5da2879f | feat(dispatch): DISP-ROUNDTRIPS Block 4 — Round Trips view + fleet OOS strip
#757 | 2026-06-08 | 13:02:35 | 162e2735 | feat(cash-flow): Cash Flow module — daily prediction + Actual vs Projected
#758 | 2026-06-08 | 07:20:38 | 9f95554b | feat(dispatch): DISP-LIST-TABLE-ASSIGN Block 5 — List/Table/Assignment board views
#759 | 2026-06-08 | 07:46:27 | 477ae5ae | feat(gap-36): driver PWA full incident reporting (WF-048)
#760 | 2026-06-08 | 07:38:36 | 57caf9a0 | feat(gap-32): customer free-time detention catalog
#761 | 2026-06-08 | 07:47:47 | 88388a13 | feat(gap-31): multi-stop extra rate per stop (WF-053)
#762 | 2026-06-08 | 07:34:03 | 1ecc202f | feat(dispatch): DISP-FINES-DEDUCT Block 13 — fines auto-deduction UI
#763 | 2026-06-08 | 07:52:20 | d47bcefb | feat(gap-45): cash-flow OCI route fix + per-truck CPM
#765 | 2026-06-08 | 08:12:45 | 578233ca | feat(gap-37): equipment dual-confirm transfer (G14)
#766 | 2026-06-08 | 07:54:54 | 6baedee7 | fix(dispatch): wire real FinesDeductionsCard into LoadDetailDrawer
#767 | 2026-06-08 | 08:36:52 | 337153c5 | feat(gap-42): IFTA 4-step quarterly preparer + owner WF-064 confirm
#768 | 2026-06-08 | 08:31:59 | a1a359ea | feat(gap-43): Q8 scheduled report subscriptions with 15min emailer
#769 | 2026-06-08 | 09:30:32 | a632a6d3 | feat(gap-46): integrity anomaly detection alert engine
#770 | 2026-06-08 | 09:14:56 | a0d3e678 | feat(gap-47): dispatch auth gates WF-044/050/038
#771 | 2026-06-08 | 09:05:40 | 89f736ae | feat(gap-48): wire driver operations depth tab
#772 | 2026-06-08 | 09:53:34 | 1619a2d4 | feat(gap-51): data sovereignty DS-1..7 suite
#773 | 2026-06-08 | 10:55:34 | dbac6fc2 | feat(gap-52): CAP-15 driver QBO vendor mapping integrity
#774 | 2026-06-08 | 11:17:02 | 108c90ee | feat(gap-53): bank account multi-company drift audit
#775 | 2026-06-08 | 11:34:44 | 47b01316 | feat(gap-54): WF-051 250-foot arrival prompt correction
#776 | 2026-06-08 | 11:47:18 | e4d8d90c | feat(gap-55): CAP-1 real-time GPS on active loads
#777 | 2026-06-08 | 12:04:56 | a8b6122e | feat(gap-58): CAP-8 engine fault auto work order
#778 | 2026-06-08 | 12:21:11 | c6836aef | feat(gap-59): CAP-9 vehicle driver pairing at time of event
#779 | 2026-06-08 | 12:51:11 | 142a557f | feat(gap-56): CAP-4 auto status switching on vehicle movement
#780 | 2026-06-08 | 12:14:26 | b723f964 | feat(gap-60): CAP-10 driver scoring page safety
#781 | 2026-06-08 | 12:35:17 | 1e7e71e7 | feat(gap-57): CAP-5 dispatch board tri-signal on-track behind delayed
#782 | 2026-06-08 | 13:48:31 | f0198898 | feat(gap-72): customer relationship score health
#783 | 2026-06-08 | 13:37:45 | e85a5c6e | feat(gap-64): CAP-14 cargo temp/humidity sensors
#784 | 2026-06-08 | 14:02:39 | 6065b15e | feat(gap-71): driver retention predictive model
#785 | 2026-06-08 | 14:33:23 | f7e0d7d6 | chore(closure): CLOSURE-19 per-block manifest + artifact guard
#786 | 2026-06-08 | 22:07:07 | dac1a5ec | chore(closure): CLOSURE-23 per-block manifest + artifact guard
#787 | 2026-06-09 | 15:38:24 | 2b21ecfd | chore(closure): CLOSURE-20 per-block manifest + artifact guard
#788 | 2026-06-08 | 14:19:54 | 3adafe23 | chore(closure): CLOSURE-17 ON-HOLD triage decision docs
#789 | 2026-06-10 | 00:11:12 | 7449bf61 | chore(closure): CLOSURE-25 per-block manifest + artifact guard
#790 | 2026-06-09 | 15:56:57 | 33a3d38d | chore(closure): CLOSURE-24 per-block manifest + artifact guard
#791 | 2026-06-10 | 00:11:05 | 6846f8f2 | chore(closure): CLOSURE-21 per-block manifest + artifact guard
#792 | 2026-06-08 | 14:33:10 | 87e2bf4c | chore(closure): CLOSURE-18 per-block manifest + artifact guard
#793 | 2026-06-08 | 14:29:10 | e12949c8 | feat(closure): CLOSURE-16 deep audit C full implementation
#794 | 2026-06-08 | 14:46:27 | 7490803c | feat(tier2): BLOCK-13 operational tuning catalog
#795 | 2026-06-08 | 15:18:05 | d6ee890b | feat(closure): CLOSURE-12 full payroll integration implementation
#796 | 2026-06-08 | 14:45:51 | 347edd01 | feat: implement BLOCK-08 tier2 load-test baseline
#797 | 2026-06-08 | 15:48:19 | 44bf9854 | feat(closure): CLOSURE-13 full USMCA activation implementation
#798 | 2026-06-09 | 20:57:48 | 9dff6b74 | feat(closure): CLOSURE-10 full maintenance parts catalog implementation
#799 | 2026-06-08 | 15:17:59 | 92dabde3 | feat(closure): CLOSURE-11 full maintenance services catalog implementation
#800 | 2026-06-08 | 15:37:36 | 0fcc12da | feat(tier2): BLOCK-05 circuit breakers on external deps
#801 | 2026-06-09 | 23:40:25 | c68b2845 | feat(tier2): BLOCK-10 RLS cross-tenant test gate
#802 | 2026-06-09 | 16:29:57 | 1ced9b31 | feat(tier2): BLOCK-09 critical path E2E tests
#804 | 2026-06-08 | 22:06:33 | 1fcd6736 | feat(dispatch): TIER14-MEXICO-OPS Block 14 — Mexico Operations Module
#805 | 2026-06-08 | 22:06:48 | 1007d9c9 | feat(dispatch): TIER15-MECHANIC-SHOP Block 15 — Internal Mechanic Shop Module
#806 | 2026-06-08 | 15:17:37 | 259f9c9f | feat(dispatch): TIER20-SECRETS-ROTATION Block 20 — Secrets Rotation Runbook
#807 | 2026-06-08 | 15:17:31 | 3b625f86 | feat(dispatch): TIER21-DR-DRILL Block 21 — DR Restore Drill
#808 | 2026-06-08 | 15:17:23 | c39027fc | feat(dispatch): TIER23-DEGRADATION Block 23 — Degradation Matrix
#809 | 2026-06-09 | 16:30:06 | a67a3ef7 | feat(dispatch): TIER26-PARTITION Block 26 — Partition Hot Tables
#810 | 2026-06-08 | 15:17:16 | 301d7097 | feat(dispatch): TIER27-CANARY Block 27 — Canary Deploy
#811 | 2026-06-08 | 15:17:08 | a39fa454 | feat(dispatch): TIER28-VENDOR-LOCKIN Block 28 — Vendor Lock-in Analysis
#813 | 2026-06-08 | 15:17:00 | 4223885d | feat(dispatch): TIER29-KNOWN-LIMITATIONS Block 29 — Known Limitations Doc
#814 | 2026-06-09 | 16:11:03 | 6bc364b2 | feat(accounting): seed periods Jan–Jun 2026 for TRANSP (BLOCK-11)
#815 | 2026-06-08 | 21:59:57 | e48ceb59 | feat(acct-ca04): Account Drawer — lock flag, opening-balance-as-of, nullable account_number
#816 | 2026-06-09 | 20:53:41 | 61b50b4a | feat(accounting-integrity): verify-extend — period lock CI, bank-recon cron, accounting probes, CoA role bindings
#817 | 2026-06-08 | 22:06:18 | 47fbf7c8 | fix(fuel): wire 8 fuel sub-nav tabs to distinct routes (Block U)
#818 | 2026-06-08 | 15:46:48 | 0307aa21 | fix(dispatch): wire 5 secondary tabs to distinct routes (Block V)
#819 | 2026-06-08 | 22:06:03 | 4e90b9fd | fix(routing): redirect legacy underscore URLs to hyphen paths (Block H)
#820 | 2026-06-08 | 21:29:37 | 3dab85e2 | fix(dispatch): at-risk-loads 500 — project city/state in sd lateral (42703)
#822 | 2026-06-09 | 02:09:31 | aeade728 | feat(driver-hub): wire DriverHubPage to /driver-hub route (P5a)
#823 | 2026-06-09 | 02:26:56 | a5656b2d | docs(qbo-parity): QBO-parity UI system spec + architecture/blueprint/locked-decisions
#824 | 2026-06-09 | 04:02:54 | 8f3f42a0 | feat(qbo-parity): A1 shared ParityTable grammar (UI-only)
#825 | 2026-06-09 | 05:37:29 | ae248258 | feat(qbo-parity): A3 sizing tokens + ParityDrawer (UI-only)
#826 | 2026-06-09 | 05:43:55 | 1a7740d0 | docs(qbo-parity): capture master report + v2/v3 + Visuals-First (nothing lost)
#827 | 2026-06-09 | 05:41:49 | 4dc2ccef | feat(sidebar): add DRIVER HUB nav entry (V0, additive)
#828 | 2026-06-09 | 06:02:27 | 6d9cf53b | feat(qbo-parity): A2 ReferenceSelect — inline '+ Add new' keystone (UI-only)
#829 | 2026-06-09 | 06:48:44 | d0bc5e5f | feat(dispatch): surface existing Driver/Truck/Loads planners from Dispatch header (V3)
#831 | 2026-06-09 | 08:00:34 | 98235a2d | fix(cash-flow): repoint read queries to real schema (500 → 200)
#833 | 2026-06-09 | 14:26:26 | 5a7e8992 | feat(dispatch): persistent click-to-open sub-nav + surface planners (Option A)
#834 | 2026-06-09 | 16:30:54 | 40ffcd89 | Feat/closure 10 maint parts catalog
#838 | 2026-06-09 | 21:21:45 | 4b06356f | fix(ci): handle two-segment display_id regex pattern (e.g. ^CM-[0-9]{…
#840 | 2026-06-10 | 00:00:17 | 05f867c3 | Feat/qbo block a bank transactions
#842 | 2026-06-09 | 21:41:37 | e148fa7c | Feat/fix pr 816
#843 | 2026-06-10 | 00:26:55 | 21fa8ae4 | chore(deps): bump the development-dependencies group across 1 directo…
#844 | 2026-06-09 | 21:16:08 | 95ab50a9 | Add GAP-76 deadhead mile optimizer for dispatch book-load.
#846 | 2026-06-09 | 22:51:29 | 108946cc | fix(ci): guard 0937 coa role-binding seed on catalogs.accounts existence
#847 | 2026-06-09 | 23:19:38 | 714e66be | fix(migrate): checksum override for 0937 post-apply EXISTS-guard edit
#849 | 2026-06-10 | 00:45:41 | bc5ffaea | Revert "Merge pull request #843 from tioperfumes07/feat/fix-pr-836"
#851 | 2026-06-10 | 02:53:21 | 83d983b9 | fix(ci): add missing verify-closure-21-monitoring-artifacts.mjs
#853 | 2026-06-10 | 06:53:36 | 797e7a01 | fix(audit): nested-box modal regression tests (P8-AUDIT-NESTED-MODALS)
#854 | 2026-06-10 | 06:53:46 | 04b23eba | fix(audit): archive TEST/seed rows from prod listings (P8-AUDIT-TEST-DATA)
#855 | 2026-06-10 | 06:53:49 | 2ad8532c | fix(audit): remove prod stub strings + CI guard (P8-AUDIT-PROD-STUBS)
#856 | 2026-06-10 | 06:53:52 | 2b954f4d | fix(samsara): webhook route investigation + CI guard (SMS-FIX-2-WEBHOOKS)
#857 | 2026-06-10 | 06:53:56 | 87f6ff91 | fix(audit): reconcile 8 KPI drifts production vs app (P8-AUDIT-KPI-DRIFTS)
#859 | 2026-06-10 | 20:25:11 | ba535ec2 | feat(nav): 25-item sidebar rail + Tasks/Finance/Inventory shells (SIDEBAR-V2-REORG-25)
#860 | 2026-06-10 | 20:24:19 | 038f648c | fix(SMOKE-TOKEN-AUTH): bearer token smoke + disabled PR-preview trigger + Add User bug fix
#861 | 2026-06-10 | 20:24:07 | d832fd3c | fix(BUG-ADD-USER-INERT): Create user button fires zero requests — fix FE disable-state + BE default_company_id
#862 | 2026-06-10 | 20:46:38 | d9a29499 | fix(test): TransferModal.test.tsx — jsdom env + jest-dom matchers fix (P5-T6)
#863 | 2026-06-10 | 23:23:06 | 4f7addb3 | fix(test): missing @vitest-environment jsdom — 64 tests failing on main
#864 | 2026-06-10 | 23:19:51 | c2fff494 | fix(smoke): health-only — drop SMOKE_TEST_* secrets (no service-token route exists)
#865 | 2026-06-11 | 03:25:09 | 282b9b41 | feat(C7): Accounting sub-nav 12 QBO items + global topbar + Create / Tasks
#866 | 2026-06-11 | 03:28:04 | df154e5d | feat(BK7): stackable inline-create drawer system (Account/Class/Service/Vendor/Customer)
#867 | 2026-06-11 | 04:02:17 | dbc0f3ad | feat(ITEM1): two-sided item model (sell→income account, buy→expense account)
#868 | 2026-06-11 | 04:02:45 | 82ca58c8 | feat(C6): QBO-style home dashboard at /app/homepage
#869 | 2026-06-11 | 14:34:50 | a5968903 | feat(W1-A): EVENT-LOG-SPINE
#870 | 2026-06-11 | 16:40:10 | 44fbdae3 | Fix/w1a append only
#871 | 2026-06-11 | 17:35:06 | 8a55af82 | feat(W2A): PROFITABILITY-ENGINE — one engine, three groupings + analy…
#872 | 2026-06-11 | 17:49:18 | 3e2f9c25 | Feat/w1b tasks module
#873 | 2026-06-11 | 17:58:34 | 5dde7c69 | feat(W2-B): alert rules + profiles
#874 | 2026-06-11 | 18:10:13 | 59924c8b | feat(W2-P): universal planner grid + FilterBar
#875 | 2026-06-11 | 18:33:11 | cdfc7975 | fix(ci): remove conflict markers + dedup verify lines in ci.yml
#877 | 2026-06-11 | 20:23:04 | 8797a159 | feat(W3-A): geofence engine — fences, enter/exit, spine events
#878 | 2026-06-11 | 19:52:04 | c8aff702 | fix(deploy): re-home wave migrations to db/migrations (fixes 14h boot drift)
#879 | 2026-06-11 | 20:47:58 | 58552c09 | feat(W3-B): forced driver acknowledgment
#880 | 2026-06-11 | 21:19:12 | f45ef8f4 | feat(W4-A): signed safety docs
#881 | 2026-06-11 | 21:49:28 | a3f2546d | feat(W4-B): broker auto-update (gated)
#882 | 2026-06-11 | 22:23:41 | b7454311 | docs: audit linkage phase specs (A1–A9 + Settlements)
#883 | 2026-06-11 | 22:33:13 | 7f88ba02 | feat(W5): time utilization — minute ledger, $/hr, unaccounted (read-only)
#884 | 2026-06-11 | 23:54:15 | 41923b31 | feat(A1): audit spine link columns (source_table, source_reference_id)
#885 | 2026-06-12 | 01:25:52 | 9e71c14f | fix(gap-e): /dispatch/planners index redirect + remove stale /tasks ComingSoonPage stub
#886 | 2026-06-12 | 01:43:06 | bebf534d | feat(A2): dispatch spine emit coverage — 7 mutation events wired to events.log_event()
#887 | 2026-06-12 | 01:54:10 | b5510499 | fix(shadow-routes): redirect 5 alias-shadow paths to real pages
#888 | 2026-06-12 | 01:59:42 | 5ad73650 | feat(A3): maintenance WO lifecycle spine emit coverage (5 event types)
#889 | 2026-06-12 | 02:52:47 | 4f06a45b | feat(A4): accounting transaction mutations emit spine events (14 even…
#890 | 2026-06-12 | 03:12:03 | d1bf7301 | feat(A5): banking mutations emit spine events (9 event types)
#891 | 2026-06-12 | 04:21:55 | fae8ab3d | feat(A6): universal audit trail — spine read API + AuditTrailPage with RLS, pagination, CSV export
#892 | 2026-06-12 | 04:53:28 | 16a70eab | feat(TASKS-PLANNER-V3): employee×day planner grid — progress_pct, tas…
#893 | 2026-06-12 | 05:03:02 | 3f3582cd | feat(SETTLEMENTS-SIDEBAR): rename Payroll→Settlements, reposition between Cash Flow and Accounting
#894 | 2026-06-12 | 05:11:23 | eb89ec0a | feat(OB1): unify accounting nav — replace legacy 38-item hover-dropdown with 12-tab clean bar
#896 | 2026-06-12 | 05:42:10 | aadf2aab | hotfix: restore AccountingSubNav HoverDropdownNav broken by OB1; corr…
#897 | 2026-06-12 | 06:18:18 | 3ccd2553 | feat(GAP-CI-WIRE-PREPUSH-GUARDS): wire 36 static pre-push locked guar…
#898 | 2026-06-12 | 06:31:57 | 25dcf5cb | feat(DESIGN-STD-NAVY-PAGE-BANNER): shared NavyPageSubNav component + SettlementsPage swap + CI lock
#899 | 2026-06-12 | 06:53:23 | 14872ca9 | feat(A8-AUDIT-REPORTS-SECTION): 7 audit report pages under Reports > …
#900 | 2026-06-12 | 07:16:12 | dd25eefd | feat(C1-PRE-SETTLEMENTS): settlement schema + read model + RLS + 3 read-only endpoints
#901 | 2026-06-12 | 07:07:46 | 19f421ac | feat(A9-AUDIT-CI-EMIT-GUARD): CI gate for audit spine emit coverage
#902 | 2026-06-12 | 08:08:40 | c48adb43 | feat(C3-CUSTOMER-CONTRACT-UPLOAD): append-only contract table + routes + UI
#904 | 2026-06-12 | 12:40:49 | a47befa7 | feat(C2-FACTORING-PROFILE): tiered fee+reserve schedules + server-side validation
#905 | 2026-06-12 | 14:15:45 | fae490c2 | feat(C4-CUST-VEND-REBUILD-RECLASSIFY): reclassify + flag-duplicate routes, append-only log, spine emit
#906 | 2026-06-12 | 15:23:54 | 4b7a7da9 | feat(E1-SMOKE-SERVICE-TOKEN-AUTH): service-token middleware + smoke probe + perf-metrics dual-auth
#907 | 2026-06-12 | 15:53:43 | 060e4e02 | fix(P8-AUDIT-NESTED-MODALS): add jsdom env directive to modal-x-close…
#908 | 2026-06-12 | 16:06:30 | bd530293 | fix(audit): test-seed archive guard + 3rd vitest — P8-AUDIT-TEST-DATA
#909 | 2026-06-12 | 16:37:00 | 193c71c7 | feat(A7-AUDIT-PER-ENTITY-TABS): audit tabs with QBO-style filters for…
#910 | 2026-06-12 | 18:43:41 | 8974f8d2 | fix(audit): test-seed archive guard + 3rd vitest — P8-AUDIT-TEST-DATA…
#913 | 2026-06-12 | 23:46:49 | 0f40e6b1 | M1: Positioned-Parts Picker
#914 | 2026-06-13 | 00:28:52 | 94c75c51 | MIGRATION-RUNNER-HARDEN: fail loud on unrecognized migration filenames
#915 | 2026-06-13 | 04:16:46 | fc51c7e5 | M2: Position History for Integrity/Positioned-Parts
#916 | 2026-06-13 | 05:00:50 | 8e52bcee | fix(audit): P8-AUDIT-NESTED-MODALS - fix modal test environment
#917 | 2026-06-13 | 08:08:04 | 9b92a30a | fix(ci): M2 position-history FK guard uses pg_constraint (role-independent)
#918 | 2026-06-13 | 08:24:14 | 367748b2 | feat(accounting): B1 expense category map seed + cash_advance category
#919 | 2026-06-13 | 09:05:31 | 06d0a7b3 | feat(accounting): B2 posting engine cash_advance source type
#920 | 2026-06-13 | 10:12:46 | 2a50a897 | feat(driver-finance): B3 employee-loan ledger GL posting + posting_date
#921 | 2026-06-13 | 11:02:04 | 318ca739 | feat(driver-finance): B4 driver-request accountability timeline
#922 | 2026-06-13 | 14:37:49 | 1866e075 | feat(driver-finance): B5 cash-advance approve cascade (capstone)
#923 | 2026-06-13 | 17:25:22 | 49638a7a | B6 — Driver Inbox UI (cascade-preview + timeline endpoints)
#924 | 2026-06-13 | 19:36:06 | fd90879a | chore(tracker): in-repo living master tracker (Markdown source of truth)
#925 | 2026-06-13 | 19:54:18 | 6fc92db5 | feat(driver-finance): A3-1 settlement-deduction ledger columns (additive, DB-only)
#926 | 2026-06-13 | 20:05:55 | 8e921623 | fix(inventory): B1 repoint Parts & Stock to real /maintenance/parts (404 fix)
#927 | 2026-06-13 | 20:54:26 | 99df90d7 | feat(accounting): AI-4 extend period seed — TRANSP+TRK × 2025+2026 (gated, portable)
#928 | 2026-06-13 | 20:59:40 | acfb2cd1 | chore(tracker): reconcile UNVERIFIED rows vs merged-PR record (docs-only)
#929 | 2026-06-14 | 02:30:17 | 49926ce2 | feat(payroll): A3-2 capped advance-recovery engine + 6 locked tests (pure; live path GATED)
#930 | 2026-06-14 | 03:34:33 | 6d4b5cfb | feat(payroll): A3-2 live-path wiring (flag-gated, default OFF) + cutover flag + override DDL
#931 | 2026-06-14 | 04:50:43 | 71367ad3 | feat(payroll): A3-2 GL — fallback paired JE at post (Dr expense / Cr QBO-149), flag OFF
#932 | 2026-06-14 | 05:12:15 | 0d60b65d | feat(payroll): A3-3 settlement shadow-run (read-only OLD vs NEW recovery comparison)
#933 | 2026-06-14 | 06:23:53 | 7bb67827 | feat(accounting): driver ASSET sub-account auto-provision on hire (escrow gated)
#934 | 2026-06-14 | 08:29:18 | 894e3af9 | feat(accounting): driver ESCROW sub-account auto-provision on hire (decision #1 resolved)
#935 | 2026-06-14 | 08:58:23 | 9e58a93e | feat(accounting): driver sub-account bulk backfill — DRY-RUN only (STOP #2 gated)
#937 | 2026-06-14 | 14:33:46 | 378b3fe3 | docs(recon): reconcile master tracker vs live code + driver-escrow research spec
#938 | 2026-06-14 | 15:22:18 | 45c4bdd4 | docs(recon): 5 recon resolutions + multi-tab md→xlsx tracker exporter (v26 format)
#939 | 2026-06-14 | 16:24:29 | 93b60c5f | fix(export): multi-tab tracker exporter matching v26 format (follow-up to #938)
#940 | 2026-06-14 | 16:45:56 | 0baf8afc | feat(tasks): Block B — Create-Task UI on Task Board
#941 | 2026-06-14 | 17:08:53 | d4c85abe | feat(export): Exporter-C — GitHub tabs (02/03) for the tracker xlsx (all 10 tabs)
#942 | 2026-06-14 | 17:09:11 | a3e4fadf | feat(maintenance): Block F — reefer hours 15-minute poller cron
#943 | 2026-06-14 | 18:44:45 | 1190e44a | docs(mileage): mileage-model design + grounding spec (phased PC*Miler)
#944 | 2026-06-14 | 19:13:57 | 5ac8e9c1 | feat(dispatch): Block 1 (C-1) — Planners split-control nav
#945 | 2026-06-14 | 19:29:48 | fa0f57f1 | feat(nav): Block 8 — hide stub/placeholder pages from sidebar
#946 | 2026-06-14 | 19:44:27 | 465d3564 | docs(mileage): §6 answered — lock Jorge's 6 mileage decisions
#947 | 2026-06-14 | 19:50:06 | 74dcb8fe | docs(security): Block 9 — RLS coverage audit (inventory, no fixes)
#948 | 2026-06-14 | 19:58:20 | 3b69ce46 | docs(finance): B9 escrow-deduction design spec (gated build, locked rules)
#949 | 2026-06-14 | 20:17:10 | 5b876330 | feat(docs): Block 4 — docs-upload UI on the Documents page
#950 | 2026-06-14 | 21:36:34 | 80d09aef | feat(help): Block 5 — module-guide help stubs (structure only)
#951 | 2026-06-14 | 21:48:58 | d7c2b871 | feat(driver-finance): Block 6 (B7) — driver-inbox reporting (read-only)
#952 | 2026-06-14 | 22:16:18 | 5ac90ef9 | feat(catalogs): Block 7 — classes bulk-edit (batch-PATCH + multi-select)
#953 | 2026-06-14 | 22:16:31 | 7fa266d0 | docs(finance): Roles & Permissions design spec (foundational, VOID vs DELETE)
#954 | 2026-06-14 | 22:20:06 | 1301ff7b | docs(mileage): §1A lifecycle correction — short@assign-bill, practical@delivery-invoice
#955 | 2026-06-14 | 22:25:39 | c377e582 | docs(finance): B9 §9A — escrow management screen (UI, Jorge-approved)
#956 | 2026-06-14 | 22:37:33 | 00694203 | docs(finance): RELAY internal-bank + diesel-code design spec (Section D #2)
#957 | 2026-06-14 | 22:53:14 | 5dac3741 | docs(finance): FH-1 Fixed Assets + Depreciation design spec (Finance …
#958 | 2026-06-14 | 23:01:48 | f2218ed3 | docs(finance): FH-3 Amortization Schedule Engine design spec (Finance Hub)
#959 | 2026-06-14 | 23:31:36 | 62d43fd8 | docs(finance): FH-2 Loan Wizard design spec (Finance Hub centerpiece)
#960 | 2026-06-14 | 23:31:53 | c2ca4029 | docs(finance): FH-4 Finance Calculator design spec (Finance Hub)
#961 | 2026-06-14 | 23:28:01 | 2847cd5f | docs(finance): FH-6 Tax Manager + FH-6a rendition design spec (Finance Hub)
#962 | 2026-06-14 | 23:36:17 | 3ee3bbe1 | docs(finance): FH-7 shared Unit Allocation control design spec (Finance Hub)
#963 | 2026-06-14 | 23:41:13 | df5ecae6 | docs(finance): FH-5 Bankruptcy Modeler design spec (Finance Hub, build last)
#964 | 2026-06-14 | 23:56:36 | d9404f67 | docs(finance): VOID-EVERYWHERE cross-cutting design spec (build packa…
#965 | 2026-06-15 | 00:03:19 | 79dafe90 | docs(finance): FH-8 Lease Contract + Unit Picker design spec (Legal<-…
#966 | 2026-06-15 | 00:05:58 | a75d2d14 | docs(finance): FH-1 Fixed Assets + Depreciation design spec (Finance …
#967 | 2026-06-15 | 00:07:20 | aaa33424 | docs(finance): FH-1 follow-up — inter-company leasing (owner vs opera…
#968 | 2026-06-15 | 00:28:21 | ae66deed | docs(finance): apply answered questions to FH-2 (trade-in) + FH-6 (ta…
#969 | 2026-06-15 | 00:43:56 | c0d4bd67 | docs(finance): FH-5 — posting decision LOCKED (POST TO BOOKS)
#970 | 2026-06-15 | 00:45:56 | ae4135a0 | fix(tasks): task-create 400 — stop double-stringifying the request body
#971 | 2026-06-15 | 00:53:37 | ba3f1195 | fix(finance): stop double-stringifying money-path request bodies
#972 | 2026-06-15 | 01:16:08 | 14e4966b | docs(finance): VOID-EVERYWHERE — cash¦accrual basis for reversing-ent…
#973 | 2026-06-15 | 01:18:50 | 3ead2e83 | feat(accounting): VOID-EVERYWHERE PR-1 — gated void engine for invoices + journal entries
#974 | 2026-06-15 | 01:38:37 | fb6ea147 | fix(nav): remove left-sidebar hover fly-out dropdown (block 17)
#975 | 2026-06-15 | 01:53:42 | 499a3455 | fix(api): stop double-stringifying request bodies in the remaining no…
#976 | 2026-06-15 | 02:37:29 | 47b8d6b0 | feat(accounting): D5 Account Register — read-only per-account running-balance ledger + audit tab
#977 | 2026-06-15 | 04:34:51 | be3323ed | feat(accounting): VOID-EVERYWHERE PR-2 — gated void engine for bills (AP mirror)
#978 | 2026-06-15 | 04:35:08 | 68bb77fd | docs(finance): VOID-EVERYWHERE PR-3/PR-4 design — expenses + settlements void model
#979 | 2026-06-15 | 04:43:54 | 1ea68ee8 | fix(tasks): Create Task 500/42501 — RLS scope sets the wrong GUC name
#980 | 2026-06-15 | 04:44:00 | 287107aa | fix(tasks): planner 500/42P01 — join identity.users, not non-existent users.users
#981 | 2026-06-15 | 05:08:39 | c7fcd97a | fix(drivers): deactivate sets status='Inactive' (driver stayed Active after deactivate)
#982 | 2026-06-15 | 05:08:52 | 6c50ba8a | fix(driver-finance): mount orphaned escrow-deductions-pending routes (404)
#984 | 2026-06-15 | 05:18:44 | 0d1f408c | fix(customers): QBO customer-sync returned HTML (raw relative fetch -> wrong host)
#985 | 2026-06-15 | 05:19:49 | d65dddb6 | fix(units): deactivate sets status='OutOfService' (mirror of driver deactivate fix)
#986 | 2026-06-15 | 05:22:33 | e3022787 | fix(insurance): asset coverage 404'd for every unit (unit-id vs asset-id mismatch)
#987 | 2026-06-15 | 06:26:18 | ced807e0 | fix(maintenance): fleet-table KPIs 500 — non-existent unit_status enum values
#988 | 2026-06-15 | 06:26:29 | bdbd7449 | fix(dispatch): mount orphaned load settlement-summary route (404)
#989 | 2026-06-15 | 06:29:51 | 3fe701e4 | fix(maintenance): WO list shows unit_number, not raw unit UUID
#990 | 2026-06-15 | 06:45:59 | 6dd54c87 | fix(maintenance): dashboard KPIs 500 — second unit_status 'active' enum bug
#992 | 2026-06-15 | 07:02:40 | b3820999 | fix(routes): mount 7 orphaned non-financial routes the frontend calls (404s)
#993 | 2026-06-15 | 07:05:55 | 953f4444 | chore(ci): guard against orphaned routes (kills the 404-from-unmounted-route bug class)
#994 | 2026-06-15 | 07:06:20 | c8c69ab8 | fix(escrow): drop dead /driver-finance/escrow call (404 on every Escrow Record load)
#995 | 2026-06-15 | 11:16:41 | 9f476353 | fix(routes): mount 4 more orphaned non-financial routes (batch 2)
#996 | 2026-06-15 | 11:27:37 | cd33f921 | chore(ci): guard against invalid enum literals (22P02) + fix 2 it surfaced
#997 | 2026-06-15 | 11:24:53 | 487dad2b | fix(drivers): rehire validation walks the full chain (not just immediate prior)
#998 | 2026-06-15 | 11:47:53 | dd73ae0d | fix(maintenance): cap-12/cap-13 workers query mdata.units by non-existent operating_company_id
#999 | 2026-06-15 | 12:22:50 | 1a3293af | fix(migrations): repair safety.fines→civil_fines (#0050 ordering collision) [GATED]
#1001 | 2026-06-15 | 13:13:12 | 7f53d845 | chore(ci): bump actions/checkout from 4 to 6
#1002 | 2026-06-15 | 13:24:59 | a306559d | chore(ci): bump actions/setup-node from 4 to 6
#1005 | 2026-06-15 | 16:03:05 | 954f3fee | docs(accounting): GAP-EXPENSES-MODULE-COMPLETION design — verified, A1/A2 fork [DESIGN]
#1006 | 2026-06-15 | 15:01:37 | 184da5a6 | feat(accounting): GAP-EXPENSES Phase 1 — accounting.expenses header (A1-staged foundation) [GATED]
#1007 | 2026-06-15 | 15:34:44 | 46610e84 | docs(accounting): GAP-EXPENSES Phase 1.5 design — expense_lines cents…
#1008 | 2026-06-15 | 16:02:35 | c6c57b71 | feat(accounting): GAP-EXPENSES Phase 1.5 — cents reconciliation + hard total=sum invariant [GATED]
#1009 | 2026-06-15 | 17:16:17 | 846c5ff4 | test(maintenance): cover copyToAccountingLines bill branch (Phase 1.5 follow-up)
#1010 | 2026-06-15 | 18:52:35 | e2c76b65 | docs(accounting): GAP-EXPENSES Phase 2 design — expense → GL posting + reversing-JE void [DESIGN/GATED]
#1011 | 2026-06-15 | 18:36:08 | 5448ca26 | fix(insurance): policy_unit has no is_active column — use removed_at (42703 → 500 on create/units)
#1012 | 2026-06-15 | 19:27:26 | c2a545dc | chore(deps): bump form-data from 4.0.5 to 4.0.6
#1013 | 2026-06-15 | 19:27:41 | a980876b | chore(deps): bump js-yaml from 4.1.1 to 4.2.0
#1014 | 2026-06-16 | 00:26:53 | 24dd1a93 | docs(accounting): Phase 2 design reconciled to 6 locked decisions + seed SQL shown [DESIGN/GATED]
#1015 | 2026-06-15 | 20:09:44 | f41b2e25 | feat(accounting): GAP-EXPENSES Phase 2 Step 2 — Uncategorized-Expenses seed (account+role) [GATED]
#1016 | 2026-06-16 | 00:26:37 | 4d0d3226 | docs(accounting): GAP-EXPENSES Phase 2 Step 3 design — posting engine + reversing-JE void [DESIGN/GATED]
#1017 | 2026-06-15 | 20:55:26 | d2a7fc8d | feat(finance): FH-1 Fixed Assets — Step 1 data model (fixed_assets sc…
#1018 | 2026-06-15 | 21:35:34 | 863a9f10 | feat(accounting): GAP-EXPENSES Phase 2 Step 3 — expense → GL posting …
#1019 | 2026-06-15 | 21:55:34 | c6fd71e4 | fix(accounting): COA-UNCATEGORIZED-EXPENSE-QBO-RECONCILE — uncategorized_expense role → QBO #25; retire redundant #6999 seed
#1020 | 2026-06-15 | 22:20:04 | 0eba27c0 | docs(tracker): master tracker v28 — fold 87 merged PRs (#924→#1018) + dated export
#1021 | 2026-06-15 | 23:45:30 | cc9135b1 | fix(accounting): Step 3 posting — unmask markBatchFailed + prove balanced JE [TIER 1 · STOP before merge]
#1022 | 2026-06-15 | 23:46:37 | 6ea814c7 | docs(tracker): log 3 follow-up backlog rows (876-878)
#1023 | 2026-06-16 | 00:24:42 | d258bd59 | feat(finance): FH-2 Loan Wizard — preview/compute-only, gated OFF [Tier 3]
#1024 | 2026-06-16 | 00:27:04 | 4fe8cfd0 | docs(trackers): full reconciled pending inventory 2026-06-15
#1025 | 2026-06-16 | 00:29:30 | 053a3188 | docs(tracker): reconcile 30 DONE-DRIFT rows to DONE (code-on-main proof)
#1026 | 2026-06-16 | 01:18:42 | 38716788 | feat(finance): FH-3 Amortization engine — create loans + store schedules, gated OFF [Tier 3]
#1027 | 2026-06-16 | 00:47:39 | 9fb80bf6 | feat(finance): FH-4 Finance Calculator — pure modeling, gated OFF [Tier 3]
#1028 | 2026-06-16 | 01:18:56 | ad0e9fba | Docs/tracker followup rows 3
#1029 | 2026-06-16 | 02:13:13 | 72a34334 | feat(accounting): MULTI-ENTITY COA Path B Stage 1 — additive entity c…
#1030 | 2026-06-16 | 02:36:13 | ab9a0d79 | feat(accounting): MULTI-ENTITY COA Path B — STAGE 2 (backfill ownership → TRANSP)
#1031 | 2026-06-16 | 04:34:49 | 1034e61a | Docs/tracker followup rows 3
#1032 | 2026-06-16 | 04:35:54 | c1f58a3e | feat(accounting): MULTI-ENTITY COA Path B — STAGE 3 (decommingle TRK)
#1033 | 2026-06-16 | 04:56:58 | e54dbd7e | fix(frontend): route all raw /api fetches through resolveApiUrl + CI guard (cross-origin base-URL bug)
#1034 | 2026-06-16 | 05:36:12 | 908a25f2 | fix(mdata): GO-LIVE DATA-TRUTH — list-endpoint total counts + driver …
#1035 | 2026-06-16 | 05:59:19 | f5cd3f0b | fix(drivers): GO-LIVE Block 1A — Drivers roster full fetch + real-total pager
#1036 | 2026-06-16 | 06:25:37 | b993de22 | fix(fleet): GO-LIVE Block 2 — add missing mdata.units.vehicle_type (unbreak include=trailers 500)
#1037 | 2026-06-16 | 06:46:24 | f4eda89e | feat(drivers): driver entity default — never entity-less (auto-stamp TRANSP)
#1038 | 2026-06-16 | 06:58:46 | 0e4009e6 | fix(dispatch): Block 2 Bug #5 — Book Load truck/trailer dropdowns split by kind
#1039 | 2026-06-16 | 07:12:01 | 7b7aebd8 | fix(frontend): GO-LIVE #15 (429) — QueryClient defaults + friendly 429
#1040 | 2026-06-16 | 07:17:32 | ac823fa8 | feat(nav): surface FINANCE HUB in the left sidebar (was orphaned)
#1041 | 2026-06-16 | 07:25:21 | 599749f8 | fix(fleet): GO-LIVE 2E — sold units → Inactive (deactivated_at), status stays Sold
#1042 | 2026-06-16 | 12:52:57 | 2c9eca5d | feat(samsara): GO-LIVE Step 1 — HOS/ELD pull → hos.duty_status_events
#1043 | 2026-06-16 | 13:00:21 | 4ff32a56 | fix(dispatch): Book Load quick polish — template double-box, single-open dropdowns, debug copy
#1044 | 2026-06-16 | 13:20:35 | ad60ce96 | docs(fleet): log 2F Samsara trailer dual-write finding — deferred post-go-live (gated)
#1045 | 2026-06-16 | 14:10:39 | fab78ccf | docs(go-live): Block 6 demo-purge plan (show-first/gated) + park 2H/2J post-go-live
#1046 | 2026-06-16 | 14:28:37 | 4c705781 | docs(hos): log driver↔Samsara ID mapping gap (post-go-live, blocks 2J step-2)
#1047 | 2026-06-16 | 14:31:59 | e6832f09 | docs(go-live): Block 6 plan — GUARD pre-check corrections (3 Rivers is real)
#1048 | 2026-06-16 | 14:47:04 | 65a19bba | feat(go-live): Block 6 — soft-archive demo/test data (4 drivers, 5 loads, 4 units) [GATED]
#1049 | 2026-06-16 | 14:48:31 | 7053f111 | docs(go-live): Block 6 PASS 1 done (#1048) + paste-ready PASS 2 count queries
#1050 | 2026-06-16 | 15:04:07 | b3ec5433 | fix(nav): uniform app-controlled sidebar order — drop per-user + per-role override
#1051 | 2026-06-16 | 18:46:24 | 159c26ec | fix(auth): same-site api.ih35dispatch.com API base — OAuth lockout fix [GATED, coordinated]
#1052 | 2026-06-16 | 16:32:26 | ee54ee63 | docs(fleet): FLEET-ASSET-HOME — Units module gap audit + gated proposal
#1053 | 2026-06-16 | 18:46:23 | 58d75942 | feat(samsara): real-trailer sync /fleet/trailers → mdata.equipment (E2)
#1054 | 2026-06-16 | 18:46:51 | e31c839b | fix(fleet): hide demo/phantom (SAM-*/TEST/DEMO) from fleet dropdowns + roster (E1)
#1055 | 2026-06-16 | 19:13:34 | 3a3bf624 | feat(units): block Sold/Transferred when unit has an open work order (WF-064, Block B)
#1056 | 2026-06-16 | 19:50:56 | b210767e | feat(fleet): top-level FLEET nav + /fleet home (Units roster) — C1+C2
#1057 | 2026-06-16 | 21:13:31 | 487c87d5 | docs(cash-flow): Manual Daily Prediction tab spec (Block F, firewalled)
#1058 | 2026-06-16 | 21:23:18 | 8f4491f1 | fix(samsara): savepoint-isolate syncs so VIN collision can't skip trailers
#1059 | 2026-06-16 | 22:41:59 | 78ba990b | feat(forecast): firewalled Manual Daily Projections tab (Block F) — GATED at migration
#1060 | 2026-06-16 | 22:27:43 | 9db8eb50 | feat(forms): shared QuickBooks DatePicker / TimePicker / MoneyInput (Block P)
#1061 | 2026-06-16 | 22:27:39 | a7b786e4 | fix(tasks): grant ih35_app on tasks schema — Task Board 500 (bug #17) — GATED
#1062 | 2026-06-16 | 22:25:49 | c0cba3e7 | fix(dispatch): book load accepts real company units (invalid_unit_for_company, G) — GATED
#1063 | 2026-06-16 | 22:39:05 | a7d8e013 | feat(driver-hub): surface Driver Scheduler + Leave Requests (Block J)
#1064 | 2026-06-16 | 22:43:59 | f4655c61 | fix(dispatch): load board auto-fit, no horizontal scroll (Block L)
#1065 | 2026-06-16 | 22:59:14 | 87a32b25 | feat(forecast): enable CASH_FORECAST_ENABLED flag (Block F go-live)
#1066 | 2026-06-16 | 23:18:31 | 30ded3df | feat(dispatch): Load Wizard V5 compact density (Block H, incr 1) behind flag
#1067 | 2026-06-16 | 23:37:48 | 7e554676 | feat(forecast): QB DatePicker + MoneyInput on Manual Daily Projections (Block N)
#1068 | 2026-06-17 | 00:18:30 | 891866a8 | feat(accounting): PayBillModal QB DatePicker + MoneyInput (Block N) — GATED-LIGHT
#1069 | 2026-06-17 | 00:11:46 | a92f1204 | fix(fleet): Edit Vehicle/Trailer Save actually saves (BUG-FLEET-EDIT-SAVE)
#1070 | 2026-06-17 | 00:17:51 | 87e89ccd | feat(forecast): Manual Daily Projections mirrors Projected (Auto) (queue #1)
#1071 | 2026-06-17 | 00:20:38 | fcf3cdef | feat(forms): shared StateSelect + Load Wizard stop wiring (queue #2)
#1072 | 2026-06-17 | 00:36:37 | 2ac837b1 | fix(accounting): cash-forecast opening excludes credit accounts (CASH-ANOMALY #10)
#1073 | 2026-06-17 | 01:04:12 | 736b87e4 | fix(dispatch): booking driver dropdown shows real names (queue #9)
#1074 | 2026-06-17 | 00:48:01 | 3334871a | feat(drivers): driver profile QB density (queue #6)
#1075 | 2026-06-17 | 01:07:21 | 3284e03c | feat(fleet): QB DatePicker on fleet edit date fields (queue #5)
#1076 | 2026-06-17 | 01:11:28 | 7bafab36 | feat(ui): QB DatePicker on named surfaces — Tasks/Customers/Vendors/Drivers (queue #5)
#1077 | 2026-06-17 | 01:18:28 | ed762933 | feat(ui): Active/Inactive list filter — Customers + Vendors (queue #3 SOFT-DELETE)
#1078 | 2026-06-17 | 01:24:15 | f4cab851 | feat(ui): Inactivate/Reactivate on Customer + Vendor profiles (queue #3 SOFT-DELETE)
#1079 | 2026-06-17 | 01:30:01 | 45f60c12 | feat(ui): QB DatePicker on Safety surfaces (queue #5)
#1080 | 2026-06-17 | 01:33:27 | 7c779d93 | feat(ui): QB DatePicker on operational surfaces — dispatch/maint/planner/insurance/docs (queue #5)
#1081 | 2026-06-17 | 01:34:58 | 5f7133f7 | feat(ui): QB DatePicker on Reports filters (queue #5)
#1082 | 2026-06-17 | 01:45:59 | 89ab435f | feat(ui): QB DatePicker on accounting/banking list filters (queue #5)
#1083 | 2026-06-17 | 01:47:54 | 18187a8a | feat(ui): QB DatePicker on remaining non-financial surfaces (queue #5)
#1084 | 2026-06-17 | 04:24:14 | 17976624 | fix(cash-flow): Manual Daily Projections summing bug — integer-cents (MANUAL-PROJECTIONS-V2 Part A)
#1085 | 2026-06-17 | 04:50:08 | 4aadbdc2 | feat(ui): QB form density — driver profile show-first (DENSITY-SWEEP-QB)
#1086 | 2026-06-17 | 04:44:01 | 7c446bbf | feat(table): shared GLOBAL-TABLE-CONTROLS toolbar + Fleet (show-first)
#1087 | 2026-06-17 | 05:08:47 | 4be89b79 | fix(nav): sidebar FACT → /factoring (stop Accounting subnav bleed)
#1088 | 2026-06-17 | 05:12:09 | d59f393d | fix(cash-flow): exclude credit accounts from auto opening cash (CASH-ANOMALY −$5.5M)
#1089 | 2026-06-17 | 05:28:31 | 0c39d926 | feat(ui): standardize oversized form inputs to QuickBooks density (DENSITY-SWEEP-QB)
#1090 | 2026-06-17 | 05:15:31 | fe3ddd6d | feat(fleet): include_inactive param (view/reactivate soft-deleted units) — HELD for Jorge
#1091 | 2026-06-17 | 05:47:55 | fda420c0 | feat(fleet): Active/Inactive/All filter + bulk Reactivate (soft-delete)
#1092 | 2026-06-17 | 06:26:13 | 322ea055 | feat(table): global column sort + resize in shared TableControls (Fleet first)
#1093 | 2026-06-17 | 06:07:13 | eed646f1 | feat(home): global clickable KPIs (drill-down)
#1094 | 2026-06-17 | 06:07:15 | eb746771 | feat(ui): QB DatePicker on Insurance create wizards (CALENDAR finish)
#1095 | 2026-06-17 | 06:15:42 | 06dc8514 | docs(tracker): 2026-06-17 session update
#1096 | 2026-06-17 | 07:32:08 | 2bbb6735 | feat(forecast): Part B snapshot ref columns (MANUAL-PROJECTIONS-V2) — HELD for Jorge
#1097 | 2026-06-17 | 06:20:41 | 292ac2db | feat(home): clickable KPIs on Owner dashboard
#1098 | 2026-06-17 | 06:23:44 | bea5dfd9 | feat(insurance): Down Payment field on Create-Policy wizard
#1099 | 2026-06-17 | 06:28:58 | eb9de0a1 | feat(forms): DatePicker max/min + Safety calendar conversions
#1100 | 2026-06-17 | 07:59:52 | 12889fe6 | feat(customers,vendors): adopt shared GLOBAL-TABLE-CONTROLS (sort/resize/paging/search/gear)
#1101 | 2026-06-17 | 07:40:32 | 14f38bd8 | feat(reports): RunnerTable adopts shared TableHeaderCell + useTablePref
#1102 | 2026-06-17 | 07:35:15 | 894299e6 | feat(home): clickable dispatcher KPIs → loads board
#1103 | 2026-06-17 | 07:45:45 | b9ba77f0 | guard(insurance): lock policy_unit has no is_active (removed_at)
#1104 | 2026-06-17 | 08:06:43 | 7581542a | fix(insurance): /api/v1/insurance/summary aggregate (dashboard widgets 404)
#1105 | 2026-06-17 | 08:12:26 | f43a1a70 | feat(dispatch): Part A — filter→slim QuickBooks toolbar + Date double-outline fix
#1106 | 2026-06-17 | 12:09:49 | 70301d13 | Dispatch Part B/C — unified column model + 3-section List/Table grid (show-first)
#1107 | 2026-06-17 | 09:06:21 | 66761d25 | Dispatch Part D — Kanban 10 lanes + ~40px compact cards + Fleet-OOS strip (show-first)
#1108 | 2026-06-17 | 12:10:08 | 1be43030 | [DO NOT MERGE pending OK] ETA-MODEL BLOCK 1 — two-date load model (migration + design)
#1109 | 2026-06-17 | 12:22:59 | f7237884 | [needs OK to merge — backend] Wire dispatch HOS columns to in-app HOS store (no Samsara)
#1110 | 2026-06-17 | 12:25:09 | a796caa1 | [DESIGN — do not merge] BLOCK 2 PROJECTED-CASH-FOLLOWS-ETA design
#1111 | 2026-06-17 | 12:37:08 | dabe5800 | [dry-run only — needs authorization to commit] AW open-loads import (11 loads, TRANSP)
#1112 | 2026-06-17 | 12:49:07 | 896f17a2 | [needs OK — backend read path] ETA-MODEL BLOCK 1 consumer wiring (effective_delivery_date)
#1113 | 2026-06-17 | 13:06:16 | 618547c7 | [DO NOT MERGE pending OK — financial migration] BLOCK 2 foundation — predicted-delivery audit + receivable-lag
#1114 | 2026-06-17 | 12:54:57 | 61181d53 | fix(dispatch): correct Awaiting/Booked partition (GUARD live-verify fix)
#1115 | 2026-06-17 | 13:20:42 | 7338a5ea | MDP single-row redesign — one date + horizontal income/expense rows (show-first)
#1116 | 2026-06-17 | 14:38:47 | a87f1c72 | Feat/cash eta confirm endpoint
#1117 | 2026-06-17 | 14:51:25 | d2eee0e0 | Feat/cash eta forecast rebucket
#1118 | 2026-06-17 | 14:23:25 | 49c9313f | fix(dispatch): compress List/Table rows + rename 3rd section to In shop (defects #3/#4)
#1119 | 2026-06-17 | 14:23:30 | fa93ba42 | fix(dispatch): wire Live GPS to real last-known position (defect #2)
#1120 | 2026-06-17 | 14:39:11 | 45cb2504 | fix(dispatch): truck-centric Awaiting assignment (roster minus loaded trucks)
#1121 | 2026-06-17 | 14:40:31 | a508356d | fix(dispatch): wire Live GPS to real position (defect #2, re-PR — #1119 didn't land in main)
#1122 | 2026-06-17 | 14:55:21 | 877094af | fix(dispatch): Kanban lane-1 Awaiting assignment = truck-derived
#1123 | 2026-06-17 | 15:01:15 | dabc9f1d | fix(dispatch): populate Driver + HOS for awaiting (unloaded) trucks
#1124 | 2026-06-17 | 15:05:38 | c2df59b6 | feat(forecast): BLOCK 2 — re-bucket 7-day strip + Actual-vs-Projected by projected_cash_date
#1125 | 2026-06-17 | 15:13:22 | f2b0821b | hotfix(dispatch): currency formatter crash on no-load Awaiting rows — board DOWN
#1126 | 2026-06-17 | 15:56:47 | 2ea72fd4 | hotfix(dispatch): harden SettlementProfitabilityCard currency formatter (audit follow-up)
#1127 | 2026-06-17 | 16:03:07 | f797d793 | fix(dispatch): Awaiting = active trucks only + dedupe Booked (GUARD re-verify #2/#3)
#1128 | 2026-06-17 | 16:20:49 | d92d3375 | hotfix(fleet): bulk inactivate isolates failures + never hangs (STOP-THE-LINE)
#1129 | 2026-06-17 | 16:45:32 | 42fc88d6 | fix(mdata): set tenant RLS context before equipment/units soft-delete (inactivate 500)
#1130 | 2026-06-17 | 17:55:16 | a2f94ea3 | diag(mdata): runtime RLS probe + exact PG error on equipment/units deactivate 42501
#1131 | 2026-06-17 | 18:33:42 | 596e85cb | fix(mdata): drop RETURNING from equipment/units deactivate — RLS 42501 on soft-delete
#1132 | 2026-06-17 | 18:57:39 | 25c84d5c | docs(tracker): dated MASTER_TRACKER 2026-06-17 — reconciled done/pending

## 04 Pending Queue
PENDING QUEUE — live ground truth
# | Item | Section | True Status | Minimal summary (why pending) | What it needs
A1 | AI-4 periods init | Accounting/Periods | ✅ SEED SHIPPED (PR #927) | Seed extended to full coverage | DONE: TRANSP Jul–Dec 2026 + all 2025, TRK all 2025+2026 (portable code-resolved, generate_series, gated). Remaining ops step: enable PERIODS_INIT_ENABLED in prod (read-only prod flag check still pending)
A2 | BLOCK-01 depreciation | Accounting/Fixed Assets | NOT BUILT | No fixed-asset accounting | Asset register + schedule + monthly posting
A3 | Block-F settlement auto-deduct (capped ledger) | Driver-Finance | ✅ FULL SERIES MERGED + FLAG ON (PROD) | A3-1 DDL #925 · A3-2 engine #929 · wiring #930 · GL paired-JE #931 · A3-3 shadow #932 — all merged | ✅ Flag SETTLEMENT_CAPPED_RECOVERY_ENABLED flipped ON in prod 2026-06-14 (read-back confirmed); shadow-run had 0 unexplained. ⚠️ A3-CUTOVER pending (FINANCE-GATED): remove legacy blunt recovery path from driver-settlement.service.ts lines ~197-220 + reconcile first real recovered settlements
B1 | /inventory parts → 404 | Inventory | ✅ DONE (PR #926) | Page called a missing endpoint | FIXED: repointed Parts & Stock page + create drawer to the real /api/v1/maintenance/parts (single source of truth, frontend-only, field-mapped)
C1 | QBO prod credentials | QBO | ENV-BLOCKED | Intuit approval (P7-T4) | prod creds
C2 | Twilio/WhatsApp | Notifications | ENV-BLOCKED | Meta verification (P7-T3) | external approval
D2 | Bank reconcile-commit writes | Accounting | PARTIAL | Read done; commit gated | enable commit; confirm advance→bank-txn match
D5 | CA-05/CA-06 | QBO-Parity | PENDING | After CA-04 | per-account ledger + audit tab
E1 | /eld + 5 tabs | ELD | STUB | No integration | wire Samsara ELD or remove
E2 | /finance ×3 | Finance | STUB | Prose placeholders | build or hide
E5 | /admin/integrity | Admin | STUB | Backend unshipped | register checks endpoint

## 09 Next Blocks
NEXT BLOCKS — recommended build order
Money-risk first → books-safety → cheap P0 → trust cleanup → features
Order | Wave | Block / Item | Why now | Risk if skipped | Effort | Depends on | Status today
1 | A | A3-1 ledger DDL (remaining_balance_cents + status) | — | — | — | — | ✅ DONE — merged #925
1 | A | A3-2 capped recovery ENGINE + 6 locked tests (pure) | Only live path that can mishandle real money | HIGH | M | A3-1 (done) | ✅ ENGINE merged #929
1 | A | A3-2 live-path WIRING (flag-gated, cash-advance only) + override DDL | Wires engine into computeSettlement behind SETTLEMENT_CAPPED_RECOVERY_ENABLED (default OFF) | HIGH | M | #929 | ✅ WIRING merged #930 (flag OFF = byte-identical)
1 | A | A3-2 GL — FALLBACK paired JE at POST (Dr expense / Cr QBO-149) + post-time ledger | Asset draw-down so books reconcile; verify-first proved option-a (bill rewire) not clean | HIGH | M | #930 | ✅ merged #931 — recovery applied at POST (ledger + paired JE atomic); recovery=0→no JE; flag OFF until A3-3
1 | A | A3-3 shadow-run (old vs new compared, read-only) | Evidence Jorge flips the flag on | HIGH | M | A3-2 (#929/#930/#931) | 🟢 BUILT — PR #932 · GET /api/v1/payroll/settlement-shadow-run compares both paths per settlement, classifies (a)avoids-below-floor / (b)recovers-leaked / (c)unexplained-must-be-0. NO writes. Shadow-run executed (24 seeded drivers, 0 unexplained) → ✅ FLAG FLIPPED ON in prod 2026-06-14 (lib.feature_flags SETTLEMENT_CAPPED_RECOVERY_ENABLED default_enabled=true, read-back confirmed). ⚠️ A3-CUTOVER pending: legacy blunt path still present in driver-settlement.service.ts
2 | A | AI-4 — Periods init: TRK + 2025 + H2-2026 + confirm flag in prod | Books-safety foundation; close period gaps | MED | S | none | ✅ SEED SHIPPED — PR #927 (gated; ops must enable PERIODS_INIT_ENABLED in prod)
3 | A | AI-1b/AI-3b — CONFIRM closed-period lock + financial probes enforce | Already shipped; validate, don't rebuild | LOW | S | none | ✅ verify
4 | B | B1 — /inventory parts 404 (repoint to /api/v1/maintenance/parts) | Visibly broken live page; trivial; independent | LOW-MED | XS | none | ✅ DONE — PR #926
5 | B | UNVERIFIED reconcile pass (DIR-G/H, BLOCK-11, CA-04, GAP-76, F3) | Make tracker fully trustworthy | LOW | S | none | ✅ DONE — PR #928
6 | B | Commit tracker → this file (Markdown) + xlsx export | Living, version-controlled doc | LOW | S | step 5 | THIS PR
7 | C | Diesel-code request type (request→approve→inbox) | Highest ops value; reuses B4 timeline + B6 inbox | — | M | B4/B6 | ❌ empty tab
8 | C | B7 — Driver-inbox reporting (resume; paused) | Preflighted; cross-request analytics; pure read | — | M | B4/B6 | PAUSED
9 | C | Repair request type | Net-new; links to maintenance WO | — | M | B4/B6+WO | ❌ empty tab
10 | C | Expense request type | Net-new; links to expense-category map / GL | — | M | B4/B6+Block-21 | ❌ empty tab
11 | C | Load-update + Complaint request types | Net-new, no GL; finishes inbox tabs | — | S | B4/B6 | ❌ empty tabs
12 | D | CA-05 register + CA-06 account audit history | QBO-parity; CA-04 shipped | LOW | M | CA-04 | PENDING
13 | D | Bank reconcile-commit writes (D2) | Read+scoring exists; enable commit | MED | M | recon engine | 🟡 PARTIAL
14 | D | Opening-balance entries (owner-entered) | Gated financial write | MED | S | AI-4 | PENDING
15 | E | Stubs: ELD / Finance / Inventory pages — build or hide | UX honesty | LOW | varies | none | ❌ STUB
16 | E | BLOCK-24 annual 1099 generation | Year-end tax | MED | L | vendor pmts | PENDING
17 | E | BLOCK-25 multi-entity consolidation | Consolidated statements | MED | L | periods+entities | PENDING
18 | E | BLOCK-01 depreciation (register+schedule+posting) | Largest financial gap left | MED | L | CoA | ❌ NOT BUILT
19 | E | USMCA master-data writes / activation | Deferred until July 2026 | LOW | M | — | DEFERRED
— | F | DRIVER-ESCROW-LIABILITY-SUBACCOUNTS (research + design first) | Truth-in-leasing per-driver escrow accounting | MED | L | A3 series | ⏸ PARKED — auto-create a LIABILITY sub-account (driver's name) under the escrow control parent (verify exact parent name in LIVE QBO — 'Escrow' or 'Escrow 2026', do NOT guess). Escrow = driver's money (refundable on separation if no fines/damage). SEPARATE from A3 (liability vs QBO-149 asset). Preview-gated if it touches a locked page.
— | F | DRIVER-SUBACCOUNT-AUTO-PROVISION — ASSET side | Per-driver advance sub-account on hire | MED | M | A3 series | ✅ merged #933 · on driver create, auto-create "Driver Cash Advance- <Name>" under the canonical parent (resolved by NAME, never UUID); idempotent; best-effort. Live-CoA verified: catalogs.accounts is global=TRANSP chart; TRK has no parents; USMCA excluded.
— | F | DRIVER-SUBACCOUNT-AUTO-PROVISION — ESCROW side (STOP #1 resolved) | Per-driver escrow liability sub-account on hire | MED | M | #933 | ✅ merged #934 · DECISION #1 LOCKED: nest under UNPREFIXED "Damage Claim Escrow" (QBO-1150040187, Liability). Auto-create "Damage Claim Escrow- <Name>" in the SAME hire hook; resolved by NAME+Liability (never UUID); idempotent; best-effort; TRANSP-scoped.
— | F | DRIVER-SUBACCOUNT-BULK-BACKFILL — DRY-RUN | Preview existing-driver sub-account gaps | MED | M | #933/#934 | ✅ MERGED #935 (deployed live 9e58a93e, route 401-gated; #936 stale-dup CLOSED 6/14) · GET /api/v1/payroll/driver-subaccount-backfill/dry-run reports per driver {asset/escrow: CREATE¦SKIP-exists¦SKIP-no-parent} + totals, reusing the SHARED planDriverSubAccount (extracted; both provisioners now call it). ZERO writes in dry-run (tested). apply=true defaults OFF + not exposed via any endpoint. ⛔ STOP-DECISION #2 — real mass-create against prod is Jorge's explicit manual go with his spreadsheet after reviewing a dry-run.

## 05 Functional Audit
FUNCTIONAL-COMPLETENESS AUDIT
HAND-CURATED in v26 — does NOT refresh on export; not derived from markdown/GitHub. Do not read as live.
Area | State | Evidence / Gap
(hand-curated v26) | STATIC — not refreshed | This tab is NOT regenerated by export:tracker. It was hand-curated in v26 and does not reflect live state. Define a source to auto-populate, or treat as historical only.

## 06 Net-New Request Types
NET-NEW DRIVER-REQUEST TYPES
Candidate | Today | Reuses | Net-new needed | GL?
diesel-code | empty tab | B4 spine + B6 inbox + cascade-preview | table, submit endpoint, approve handler, PWA form | Yes
repair | empty tab | same | + links to maintenance WO | Yes
expense | empty tab | same | + expense-category map | Yes
load-update | empty tab | B4/B6 | table + approve | No
complaint | empty tab | B4/B6 | table + routing | No

## 07 Duplicates
DUPLICATE TASKS — same block, multiple rows
Cluster key | Row #s (sheet 01) | Task name | Note
A17 | #482, #484, #485, #492 |  | 4 occurrences — keep #482
B21 | #491, #496, #500 |  | 3 occurrences — keep #491
P5T11 | #118, #127 |  | 2 occurrences — keep #118
P5T13 | #119, #129 |  | 2 occurrences — keep #119
A15 | #477, #516 |  | 2 occurrences — keep #477
P8AUDITBACKENDVERSION | #343, #540 |  | 2 occurrences — keep #343
P8AUDITNESTEDMODALS | #337, #541 |  | 2 occurrences — keep #337
P8AUDITELDREDIRECT | #340, #543 |  | 2 occurrences — keep #340
P8AUDITDOCSREDIRECT | #341, #546 |  | 2 occurrences — keep #341
P8AUDITQBOARCHIVE | #342, #547 |  | 2 occurrences — keep #342
P8AUDITTESTDATA | #339, #548 |  | 2 occurrences — keep #339
P8AUDITUNDEFINEDLEGEND | #344, #549 |  | 2 occurrences — keep #344
P8AUDITPRODSTUBS | #338, #550 |  | 2 occurrences — keep #338
P8AUDITKPIDRIFTS | #345, #558 |  | 2 occurrences — keep #345
P5T5 | #122, #561 |  | 2 occurrences — keep #122
P5T8 | #125, #562 |  | 2 occurrences — keep #125
BLOCK09E2EPATHS | #585, #622 |  | 2 occurrences — keep #585
BLOCK05CIRCUITBREAKERS | #584, #623 |  | 2 occurrences — keep #584
BLOCK11AUDITCOVERAGE | #593, #626 |  | 2 occurrences — keep #593
BLOCK10RLSTESTGATE | #592, #627 |  | 2 occurrences — keep #592
CLOSURE13USMCAACTIVATION | #605, #628 |  | 2 occurrences — keep #605
GAP76DEADHEADOPTIMIZER | #615, #633 |  | 2 occurrences — keep #615
BLOCK01DEPRECIATION | #597, #634 |  | 2 occurrences — keep #597
BLOCK19AUDITHASH | #599, #635 |  | 2 occurrences — keep #599
BLOCK241099ANNUAL | #600, #636 |  | 2 occurrences — keep #600
BLOCK25CONSOLIDATION | #601, #637 |  | 2 occurrences — keep #601
AI4PERIODSINITJANJUN2026 | #610, #641 |  | 2 occurrences — keep #610
CA04NEWEDITDRAWER | #612, #643 |  | 2 occurrences — keep #612

## 08 Phase Summary
PHASE / STATUS SUMMARY (reconciled)
Reconciled Status | Count
DONE | 614
PENDING | 136
IN FLIGHT | 10
SUPERSEDED | 6
ON DECK | 4
NOT STARTED | 4
PARTIAL | 3
ONGOING | 3
CANCELLED | 1
DISPATCHED | 1
DRAFTED | 1
DROPPED | 1
MISSING | 1
NEEDS CONFIRM | 1
TOTAL | 787
DONE share | 78%
BLOCK-REGISTRY RECON 2026-06-17
Shipped (branch merged) | 224
PENDING (no merged branch) | 70

## 10 Pending Block Instr
PENDING WRITTEN BLOCKS — construction instructions (branch NOT merged) — 2026-06-17
70 pending of 294 written blocks. INSTRUCTION = verbatim .block-ready 'task'. Gate: db:True still hits §1.3 backend gate.
block_id | phase | classification | gate | db | migration | branch | INSTRUCTION (construction)
C6-HOME-DASHBOARD | Accounting | NON-FINANCIAL | TIER-1: STOP + Jorge OK | False |  |  | QBO-style home dashboard at /app/homepage. Read-only aggregation. Sidebar HOME item wired to /app/homepage. No financial writes.
C7-ACCT-SUBNAV-CHROME | Accounting | NON-FINANCIAL | TIER-1: STOP + Jorge OK | False |  |  | Accounting sub-nav 12 QBO items (exact live order) + global topbar + Create and Tasks buttons. Shell pages for missing routes. Additive only. No posting, no financial writes.
ITEM1-TWO-SIDED-ITEM | Accounting | NON-FINANCIAL | TIER-1: STOP + Jorge OK | False |  |  | Two-sided item model: sell side (income account, defaults to Service income) + buy side (expense account + preferred vendor). ItemEditorModal replaces generic metadata modal. No financial writes.
ACCT-QBOPAR-01-CATALOG-BACKEND | Accounting — QBO Parity |  | TIER-1: STOP + Jorge OK | True | 202606080010_account_type_detail_type_catalog.sql |  | QBO-parity account type & detail type catalog: migration + seed (15 types / 5 groups) + GET /api/v1/accounting/account-type-catalog route.
BLOCK7-DRIVER-HUB-REQUESTS | BLOCK | ADDITIVE | Tier-3: ship on green | False |  | feature/block7-driver-hub-requests | Driver Hub Requests — Manager/Owner approve/deny cash advance requests; approve creates a settlement deduction via createSettlementDeduction()
BLOCK-C-DEDUCTION-CAP | BLOCK-C | ADDITIVE | TIER-1: STOP + Jorge OK | True | db/migrations/20260607_191000_settlement_min_net_floor.sql | feature/block-c-deduction-cap | Settlement deduction cap — net floor (50% gross + absolute cents) with all-or-nothing roll-over of pending deductions at settlement close.
BLOCK-H-DETENTION-NOTIFY | BLOCK-H | ADDITIVE | Backend §1.3: STOP + OK | True |  | feature/block-h-detention-notify | Block H — On detention request approval (PATCH /api/v1/dispatch/detention/requests/:id/approve), after the billing bridge + invoice build, email the customer a detention-charge notice. Default OFF behind feature flag 'detention_customer_notify_email'; sent AFTER the approval tx commits; idempotent on dispatch.detention_requests.customer_notified_at; charge labeled 'derived from stop timestamps'.
FIX-CANARY-SMOKE-DURABLE | CI Infrastructure |  | Tier-3: ship on green | False |  |  | Simplify smoke.sh to health-only: drop SMOKE_TEST_TOKEN/EMAIL/PASSWORD/COMPANY_ID — auth is Google OAuth/Lucia, no service-token route exists. Update prod-postdeploy-verify.yml and pr-preview-smoke.yml to not pass removed secrets. Update verify-canary-replacement.mjs to assert health-only smoke (checks 8+9).
DISPATCH-LIVE-ETA | DISPATCH | ADDITIVE | Tier-3: ship on green | False |  | feature/dispatch-live-eta-columns | Dispatch live ETA columns — driver status, Samsara ETA, on-time prediction
DISP-PLANNERS | Dispatch |  | Tier-3: ship on green | False |  |  | DISP-PLANNERS
W1-EVENT-LOG-SPINE | Foundation | NON-FINANCIAL | TIER-1: STOP + Jorge OK | True |  |  | Immutable timestamped event spine — events.event_log table + logEvent() helper. All downstream Waves (2-5) write to this for accountability. NON-FINANCIAL.
BLOCK5-INSURANCE-FORWARD-FIX | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/insurance-bill-creator-forward-fix | Forward-fix for the #687 double-bill vulnerability: require Idempotency-Key on /insurance/policies, partial-UNIQUE bill_uuid, replay-skip pre-check, atomic hard-fail+rollback with bill void / CRITICAL Sentry on orphans, and bill the down payment so down + sum(installments) === total_premium. Additive-only; keeps bill_uuid + vendor_id from #687.
GAP-10-DELTA-CANCELLATIONS-REPORT | GAP-HIGH |  | Tier-3: ship on green | False |  | feature/gap-10-delta-cancellations-report | Load cancellations analytics report (group by reason, driver, customer, date)
GAP-11-DELTA-UPLOAD-EXPENSE | GAP-HIGH |  | Tier-3: ship on green | False |  | feature/gap-11-delta-upload-expense | Wire UploadZone into expense create form (match bill/invoice attachment pattern)
GAP-19-DETENTION-INVOICE | GAP-HIGH | ADDITIVE | Backend §1.3: STOP + OK | True |  | feature/gap-19-detention-invoice | GAP-19 Detention billable manager-approval gate — approve bridges detention into linehaul invoice (reuses bridgeDetentionToBilling + buildInvoiceFromLoad) and records dwell evidence (stop-timestamp derived + units→Samsara projection join).
GAP-34 | GAP-HIGH | OVERLAP | Backend §1.3: STOP + OK | True |  | feature/gap-34-driver-pwa-dispatch-view | G22 Driver PWA dispatch view (pickup/delivery cards + doc upload)
GAP-38-DAMAGE-INSURANCE-CONTINUITY | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-38-damage-continuity | Damage report continuity chain + WF-027 insurance auto-claim linkage (additive; UI on locked shared surface deferred for preview)
GAP-39 | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-39-geofence-state-machine | G17 Geofencing full backend state machine
GAP-40 | GAP-HIGH | ADDITIVE | Backend §1.3: STOP + OK | True |  | feature/gap-40 | Damage photo EXIF chain-of-custody (WF-058)
GAP-44 | GAP-HIGH | ADDITIVE | Tier-3: ship on green | False |  | feature/gap-44-form-425c-exhibits | Form 425C Exhibits A-F auto-build for TRANSP monthly DIP filings
GAP-48 | GAP-HIGH | ADDITIVE | Tier-3: ship on green | False |  | feature/gap-48-driver-operations-depth | GAP-48 Driver Operations Depth — 12 read-only operational sub-views on a new Operations tab
GAP-49 | GAP-HIGH | ADDITIVE | Backend §1.3: STOP + OK | True |  | feature/gap-49-dvir-severity-tagging | Maintenance Pre-Flight DVIR Severity Tagging (major vs minor vs observation) — WF-050 / 49 CFR §396.11
GAP-61 | GAP-HIGH | ADDITIVE | Backend §1.3: STOP + OK | True |  | feature/gap-61 | CAP-11 Fuel card real-time fraud alerts
GAP-62-CAP-12-TIRE-TREAD | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-62 | CAP-12 tire tread wear tracking and replacement projections
GAP-63 | GAP-HIGH | ADDITIVE | Backend §1.3: STOP + OK | True |  | feature/gap-63 | CAP-13 Brake Wear Predictive Maintenance — lining thickness tracking + replacement projections
GAP-67-ACCOUNTING-HOME | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-67-accounting-home | Accounting Home role-specific view (read-only display)
GAP-68-SAFETY-OFFICER-HOME | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-68-safety-home | Safety Officer home role-specific view
GAP-69-DRIVER-MANAGER-HOME | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-69-driver-manager-home | Driver Manager home role-specific view
GAP-70 | GAP-HIGH | ADDITIVE | Backend §1.3: STOP + OK | True |  | feature/gap-70 | EDI Integration Foundation (204/214/210/990)
GAP-76 | GAP-HIGH |  | Tier-3: ship on green | False |  | feature/gap-76-deadhead-optimizer | Deadhead mile optimizer — ranked next-load suggestions
GAP-76 | GAP-HIGH |  | Tier-3: ship on green | False |  | feature/gap-76-deadhead-optimizer | Deadhead mile optimizer — ranked next-load suggestions
GAP-8 | GAP-HIGH |  | Tier-3: ship on green | False |  | feature/gap-8-assignments-quicksave | G26 assignments inline quicksave (unit/trailer/driver)
GAP-82-MEDICAL-CARD-TRACKING | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-82-medical-card | Medical card + CDL expiry tracking and alerts
GAP-83-ELD-AUDIT-VIEWER | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-83-eld-audit | ELD audit trail read-only viewer
GAP-84-DOT-INSPECTION-GAP-CLOSE | GAP-HIGH |  | Tier-3: ship on green | False |  | feature/gap-84-dot-inspection-gap-close | DOT inspection clean-rate endpoint, score badge, and CI verify guard
GAP-85-PERMIT-TOLL-TRACKING | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-85-permit-toll | Permit + toll tag tracking per unit with expiry alerts
GAP-86-INSURANCE-BILL-CREATOR | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-86-insurance-bill-creator | Insurance multi-vehicle policy creator + bill schedule write via createBill()
GAP-89-UNIVERSAL-SEARCH-CMD-K | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-89-universal-search | Universal Cmd-K quick switcher search
GAP-89-UNIVERSAL-SEARCH-CMD-K | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-89-universal-search | Universal Cmd-K quick switcher search
GAP-91-MOBILE-RESPONSIVE-AUDIT | GAP-HIGH |  | Tier-3: ship on green | False |  | feature/gap-91-mobile-responsive-audit | Mobile responsive audit + PWA touch UI polish
GAP-91-MOBILE-RESPONSIVE-AUDIT | GAP-HIGH |  | Tier-3: ship on green | False |  | feature/gap-91-mobile-responsive-audit | Mobile responsive audit + PWA touch UI polish
GAP-92-FEATURE-FLAG-SYSTEM | GAP-HIGH |  | Backend §1.3: STOP + OK | True |  | feature/gap-92-feature-flags | Per-tenant and per-user feature flag system
GAP-23 | GAP-MEDIUM | ADDITIVE | Tier-3: ship on green | False |  | feature/gap-23-samsara-cache-tiers | 4-tier Samsara cache hierarchy with scheduled warmer
GAP-24-FRESHNESS-INDICATOR | GAP-MEDIUM | ADDITIVE | Tier-3: ship on green | False |  | feature/gap-24-freshness-indicator | Samsara freshness indicator pill (L1-L4, green/amber/red)
GAP-28 | GAP-MEDIUM |  | Backend §1.3: STOP + OK | True |  | feature/gap-28-layover-detection | Layover Time Computation (>8h Gap)
GAP-29 | GAP-MEDIUM |  | Tier-3: ship on green | False |  | feature/gap-29-booking-gap-analytics | Booking-Gap Time per Dispatcher Analytics
GAP-30 | GAP-MEDIUM |  | Backend §1.3: STOP + OK | True |  | feature/gap-30-late-arrival-analytics | Late-arrival rate analytics per driver/customer/lane
GAP-41 | GAP-MEDIUM | OVERLAP | Tier-3: ship on green | False |  | feature/gap-41 | 9 Reports Hub categories with hover-dropdown WF-061
GAP-50 | GAP-MEDIUM | ADDITIVE | Backend §1.3: STOP + OK | True |  | feature/gap-50 | AI Photo Comparison Pre/Post Trip Damage Detection
GAP-PREMERGE-GATES-EXPAND | GAP-STRUCTURAL |  | Tier-3: ship on green | False |  | feat/premerge-gates-expand | Promote three post-merge feedback checks to required pre-merge CI gates (GAP-81 failure class)
BLOCK-C-MIGRATION-RENAME | HOTFIX | ADDITIVE | TIER-1: STOP + Jorge OK | True | db/migrations/202606071910_settlement_min_net_floor.sql | fix/block-c-migration-rename | Rename Block C migration to 12-digit runner-compatible filename so db:migrate applies min_net_settlement columns in prod.
FIX-SAFETY-NAV-COUNT | HOTFIX |  | Tier-3: ship on green | False |  | fix/safety-nav-count-import | Restore SAFETY_CANONICAL_TAB_COUNT reference in HomePage after home router refactor
HOTFIX-0327-MIGRATION-ROLE | HOTFIX |  | Backend §1.3: STOP + OK | True |  | hotfix/0327-drug-alcohol-app-user | Fix migration 0327 GRANT role (app_user → ih35_app) + TS18048 guards (GAP-81)
GAP-66-DISPATCHER-HOME | P2-H | B | Backend §1.3: STOP + OK | True |  | feature/gap-66-dispatcher-home | Dispatcher Home role-specific view
PREREQ-B-SETTLEMENT-DEDUCTION-SVC | PREREQ | ADDITIVE | Tier-3: ship on green | False |  | feat/settlement-deduction-service | createSettlementDeduction() service — unblocks Driver Hub Requests approve→deduction (Block 7)
STRUCTURAL-MANIFEST-SPLIT | STRUCTURAL-FIX |  | Tier-3: ship on green | False |  | feat/manifest-per-block | Each block writes its own .block-ready/<block-id>.json; zero manifest merge conflicts in parallel lanes
STRUCTURAL-MIGRATION-TIMESTAMPS | STRUCTURAL-FIX |  | Tier-3: ship on green | False |  | feat/migration-timestamp-naming | New migrations use timestamp format (20260607_120000_name.sql) to eliminate parallel-lane sequence collisions
FOLLOWUP-SPECS-2026-06-07 | docs |  | Tier-3: ship on green | False |  | docs/followup-block-specs | Follow-up block specs from June 6-7 sprint: insurance renewals, deduction cap, detention notifications, CI fixes, and Driver Hub extensions.
CASH-FLOW-MODULE | feat/cash-flow-daily-prediction |  | TIER-1: STOP + Jorge OK | False | 202606080200_cash_flow_adjustments.sql |  | (no task text — see spec/branch/file)
BLOCK-G-COI-PDF | implementation |  | Backend §1.3: STOP + OK | True |  |  | Certificate of Insurance PDF — GET /api/v1/insurance/policies/:id/coi returns Puppeteer-rendered PDF; frontend Download COI button on PolicyDetail. Read-only, no schema changes, no financial writes.
BK7-INLINE-CREATE-DRAWERS | (unfiled) | MIXED | Tier-3: ship on green | False |  |  | (no task text — see spec/branch/file)
BLOCK-I-CI-DIST-FIX | (unfiled) |  | Tier-3: ship on green | False |  |  | (no task text — see spec/branch/file)
BLOCK-J-MASTER-DATA-GRANT | (unfiled) |  | Tier-3: ship on green | False |  |  | Systemic migration silent-skip fix + repair master_data schema USAGE grant on production
FIX-AUDIT-TRIGGER-DRIFT | (unfiled) |  | TIER-1: STOP + Jorge OK | False | 202606080030_audit_trigger_drift_remediation.sql |  | (no task text — see spec/branch/file)
FIX-REQUIRED-CHECKS-GATE | (unfiled) |  | TIER-1: STOP + Jorge OK | False | none |  | (no task text — see spec/branch/file)
GAP-14-PRE-DISPATCH-VALIDATION | (unfiled) | A | Tier-3: ship on green | False |  |  | Pre-Dispatch Validation Panel
GAP-18-DRIVER-COMM-TIMELINE | (unfiled) |  | Tier-3: ship on green | False |  | feature/gap-18-driver-comm-log | (no task text — see spec/branch/file)
GAP-7 | (unfiled) | OVERLAP | Tier-3: ship on green | False |  | feature/gap-7-severe-repair-oos | ['severe-repair-estimate.service/routes and SevereRepairOosTab rollup already exist — extend with fleet-restore-cost, per-unit-breakdown, PDF export, Owner home card.', 'GAP-6 dependency met: duration_minutes present in migration 0158_abandonment_and_wo_time_tracking.sql.']
PREREQ-A-SCHEMA-GRANT-GATE | (unfiled) |  | Tier-3: ship on green | False |  |  | 4th pre-merge CI gate: schema-level GRANT USAGE check
SIDEBAR-DRIVER-HUB | (unfiled) |  | Tier-3: ship on green | False |  | feature/sidebar-driver-hub | (no task text — see spec/branch/file)