## Register
IH35-TMS · USMCA · LEAD PENDING REGISTER · updated 10-24-2026 07:44 AM CT · CODE-COMPLETE MODE · deadline 10-24 10:00 AM CT
# | Section | Area | Item | Measured evidence | Root cause | Required fix | Seat | Round | Status | Proof / sha | Deadline
1 | A · Owner requests (last 24 h) | Design | All module designs, higher quality, shown inside the live app (V3) | 36 V3 boards approved 10-22 6:10 PM |  |  | LEAD | 443.248-250 | DONE-LIVE | canvas DuE4p2MZHjxXEtnboiuEBx
2 | A · Owner requests (last 24 h) | Accounting | Driver bill due date = load (projected) delivery date | driver_bills NULL due 143 -> 0 |  | backfill + engine | CC-1 | 443.264/265-E5 | DONE-LIVE | AUTH-456; 77fb8fc2
3 | A · Owner requests (last 24 h) | Dispatch | Kanban: truck cards drag to assign/book/availability | merged 49d1d51c, 4313ac46 | drag disabled on synthetic cards (DispatchKanban L87-108) |  | LEAD | 443.251 | MERGED-UNVERIFIED | 49d1d51c 4313ac46 | 10-24 02:00 UTC
4 | A · Owner requests (last 24 h) | Dispatch | Planners: range in filters, resizable columns, selected days fill width | live check 10-22 9:12 PM |  |  | LEAD | 443.251 | DONE-LIVE | 9420c223 3296405d
5 | A · Owner requests (last 24 h) | All | Names proper-case automatically (people), org casing kept (ACME) | DB still stores ALL CAPS for several drivers (EDUARDO AZAEL FLORES ORTIZ, HUGO GAYTAN…) | display-layer fix only | normalize at write + backfill names through the driver engine | CC-3 | 443.266-A | PARTIAL | acf2e901 #27308 | 10-24 02:00 UTC
6 | A · Owner requests (last 24 h) | Driver/Fleet | Driver photo from uploaded IDs; unit photos | CC-2 built backend (photo_file_id, unit_photos, guard 18679) — never pushed | push blocked by main reds then dropped | ship backend PR + Cursor UI on Driver Profile board | CC-2 | 443.252 | OPEN |  | 10-24 02:00 UTC
7 | A · Owner requests (last 24 h) | Settlements | Settlement number column opens the statement | #27337 merged |  |  | CURSOR | 443.252/274-C | DONE-LIVE | c94e69d9 | 10-24 02:00 UTC
8 | A · Owner requests (last 24 h) | Settlements | Navigation defects N1-N10 (tabs leave module, escrow dupes, $2575.96, initials) | Escrow still 45-row all-holder list with Safety —, Driver — Not Visible, Genaro twice, owner as driver_bond |  | see board rows B-Escrow | Cursor | 443.254 | PARTIAL |  | 10-24 02:00 UTC
9 | A · Owner requests (last 24 h) | Dispatch | Truck Line status opens searchable dropdown | #27241 merged | hand-built div list | Combobox | Cursor | 443.256 | MERGED-UNVERIFIED | 17467838 | 10-24 02:00 UTC
10 | A · Owner requests (last 24 h) | Dispatch | Book Load: NB/TR/SB, no driver pay rate, miles DB + Google | live-verified 10-23 5:50 AM |  |  | LEAD/CC-3 | 443.257/265-A | DONE-LIVE | 0584599a 1bfd56cc | 10-24 02:00 UTC
11 | A · Owner requests (last 24 h) | Dispatch | Truck Line "Assign a load" on every available truck (no driver) | live-verified |  |  | LEAD | 443.257-A | DONE-LIVE | #27235 | 10-24 02:00 UTC
12 | A · Owner requests (last 24 h) | Fuel | Fuel Questions Review crash (load_number undefined) | fixed | candidate without load | null-safe popup | CC-2 | 443.258 | MERGED-UNVERIFIED | bf7dadd3 | 10-24 02:00 UTC
13 | A · Owner requests (last 24 h) | Process | Fast-merge law (4-min) + ruling 443.261 | in force |  |  | ALL | 443.255/261 | DONE-LIVE | docs/bus/FAST-MERGE-4MIN-LAW.md
14 | A · Owner requests (last 24 h) | Dispatch | Stops 13541 s3 / 13576 s2,s3 completed via engine | 0 pending, TB 0 (7,081 postings) |  |  | LEAD | 443.248 | DONE-LIVE | docs 5796/5804
15 | A · Owner requests (last 24 h) | Settlements | Pre-Settlements: Load #, Entries, Ready-to-close, Close, clickable, responsive, miles DB+Google | #27345 merged; page still mounted inside old DriversPage; Unit/Ready/Waiting hard "—" | Rule 07 layering | rebuild to board (443.280-A item 1) | CC-3 | 443.269-A | MERGED-UNVERIFIED | #27364 d6e9d60b 5:07 PM | 10-24 02:00 UTC
16 | A · Owner requests (last 24 h) | Settlements | A miles change at settlement re-prices the bills everywhere | fork 13688 proven; not shipped |  | ship engine + guard | CC-2 | 443.269-B | CODED | 891305b339 #27414 (CC-2) | 10-24 02:00 UTC
17 | A · Owner requests (last 24 h) | Repo | Everything in the repo: 36 boards + PNGs + Lead register + rounds | branch claude/lead-443-270-design-boards-register pushing (hooks on) |  | merge | LEAD | 443.270 | DONE-LIVE | #27365 ee5b7359 | 10-24 02:00 UTC
18 | A · Owner requests (last 24 h) | Design | Every board implemented exactly (no layering) | code audit e8a9f02b: 8 rebuilt / 11 partial / 16 layered / 1 not started | Rule 07 "never delete" applied to layouts | RULING 443.280: board replaces page body | CC-3 | 443.280 | OPEN |  | 10-24 02:00 UTC
19 | A · Owner requests (last 24 h) | Data | One canonical source per entity across all views of the same type | blocked on settlement load-cost red |  |  | CC-3 | 443.270-B | BLOCKED |  | 10-24 02:00 UTC
20 | A · Owner requests (last 24 h) | Data | Merge all duplicate customers / vendors / drivers | prod duplicate groups 0/0/0 |  |  | LEAD/CC-2 | 443.270-C | DONE-LIVE | merge-all 10-23 3:20 PM
21 | A · Owner requests (last 24 h) | Accounting | QuickBooks unapplied credit: paid bill/invoice reduced below paid -> unapplied credit on payee | not built |  | engine + UI + guard | CC-2 | 443.270-C d | OPEN |  | 10-24 02:00 UTC
22 | A · Owner requests (last 24 h) | Banking | Relay: nothing stored under TRANSP; 10/09 fundings on TRANSP bank; deposit ingest stopped after 10-09; bank feed last 10-21 | not started |  | engine moves + restore ingests + backfill | CC-2 | 443.270-C e | OPEN |  | 10-24 02:00 UTC
23 | A · Owner requests (last 24 h) | Deploy | Render web build failures | fixed; web live cd148cdf | TS6133/TS2554 | tsc -b before merge (443.270-G) | CURSOR/CC-3 | 443.270-G | DONE-LIVE | dep-dbdmto942hec739cukkg | 10-24 02:00 UTC
24 | A · Owner requests (last 24 h) | Process | Lead codes, not only coordinates | #27329, #27342, #27353 merged and live |  |  | LEAD |  | DONE-LIVE | ea1591f5 a37a2712 a9f01fab
25 | A · Owner requests (last 24 h) | Cash Flow | Driver pay counted twice (settlement + per-load A/P inside it) | wk 10-19 254,182 -> 149,587 live | both rows read | shared predicate on 4 readers | LEAD | 443.276 | DONE-LIVE | #27353 a9f01fab, dep-dbdsrbaqqsrs73d7g1m0
26 | A · Owner requests (last 24 h) | Data | Find real root causes of loads/settlements data issues | traced 10-23 4:35 PM (rows in section E) |  |  | LEAD | 443.279 | DONE-LIVE | journal 4:35 PM
27 | A · Owner requests (last 24 h) | Data | Delete USMCA test records (18 legal matters, 5 policies, 7 claims, 1 accident…) | prod still: legal.matters 18, safety.accidents 1 | prod run never happened (fork-proven 344 rows) | run the engine delete on prod, TB 0 before/after | CC-2 | 443.247 | CODED | 0ee3451d41 #27457 (CC-2) — deployed 0ee3451 11:04 PM CT; prod purge run = Lead under AUTH-451 | 10-24 02:00 UTC
28 | A · Owner requests (last 24 h) | Reports | Load History tab + Settlement (driver/company), Loads, Customers, Vendors reports | designs approved 10-23 5:08 PM | pages LoadHistoryPage.tsx / LoadsReportPage.tsx exist unrouted; "Loads history" button is only a load-board filter | build to the 6 boards, routes, two-way links, export | CC-1 | 443.281 | OPEN |  | 10-24 02:00 UTC
29 | A · Owner requests (last 24 h) | All | LAW 5:08 PM: every selector is multi-select (units, loads, settlements, trucks, trailers, drivers, customers, vendors…) everywhere | single-select pickers across filters (e.g. Cash Advances Driver, Fuel History Driver/Unit/Load/Trailer) |  | one shared MultiSelect component + guard that fails on single-select entity filters | LEAD | 443.281 | OPEN |  | 10-24 02:00 UTC
30 | A · Owner requests (last 24 h) | All | Baseline screenshots of every page before the rebuild | 52 live screenshots 10-23 5:10 PM |  |  | LEAD | 443.281 | DONE-LIVE | #27369 9932b495
31 | B · Board implementation (code audit e8a9f02b) | Cash Flow | Cash Flow › Home — board verdict PARTIAL | TAB_CARDS L855-877 old tab cards; run-rate vs committed cell colors; cells not clickable; Monthly = every 4th week |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | CODED | #27453 (Home unchanged = board) | 10-24 02:00 UTC
32 | B · Board implementation (code audit e8a9f02b) | Cash Flow | Cash Flow › Projected (Auto) — board verdict PARTIAL | old "Add cash-flow adjustment" form inside Expenses (L603-646); 7-day outlook no cents (D042) |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | CODED | #27453 | 10-24 02:00 UTC
33 | B · Board implementation (code audit e8a9f02b) | Cash Flow | Cash Flow › Actual vs Projected — board verdict PARTIAL | old CollapsedListFilters + ParityTable; no total row; Actual income $0 every day (see F) |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | CODED | #27453 AvP board restored | 10-24 02:00 UTC
34 | B · Board implementation (code audit e8a9f02b) | Cash Flow | Cash Flow › Rolling Ledger — board verdict LAYERED | old 8-tile CashFlowKpiStrip, old income/expense tables; board two-sided Party/Doc/Due/Amount + day grid missing | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | CODED | #27453 | 10-24 02:00 UTC
35 | B · Board implementation (code audit e8a9f02b) | Cash Flow | Cash Flow › Manual — board verdict LAYERED | old Opening cash editor, Pull bills button, old columns; no day stepper / Save projection | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | CODED | #27453 Manual board + opening cash | 10-24 02:00 UTC
36 | B · Board implementation (code audit e8a9f02b) | Accounting | Accounting › Home — board verdict REBUILT | — |  | rebuild to the board, remove old sections from the page (443.280) | CURSOR | 443.280 | DONE-LIVE |  | 10-24 02:00 UTC
37 | B · Board implementation (code audit e8a9f02b) | Accounting | Accounting › Unexpected — board verdict REBUILT | possible duplicates shows 0 while 460.01 x2 and 155.86 x2 present (see F) |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | PARTIAL |  | 10-24 02:00 UTC
38 | B · Board implementation (code audit e8a9f02b) | Banking | Banking › Home — board verdict REBUILT | "Linked to" label guessed by regex (BankingHomeBoard L117-121) |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | PARTIAL |  | 10-24 02:00 UTC
39 | B · Board implementation (code audit e8a9f02b) | Factoring | Factoring › Home — board verdict LAYERED | FactoringKpiPanel + FactoringCashFlowPanel under board on every tab; raw "175650.000000000000" KPI; True cost 0.00% | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | OPEN |  | 10-24 02:00 UTC
40 | B · Board implementation (code audit e8a9f02b) | Reports | Reports › Home — board verdict LAYERED | old Management list, FrequentlyRun, Scheduled, IFTA card below board; ☆ inert | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | CC-3 | 443.280 | OPEN |  | 10-24 02:00 UTC
41 | B · Board implementation (code audit e8a9f02b) | Reports | Reports › Trial balance viewer — board verdict PARTIAL | hardcoded A/R "Measured" string (TrialBalanceBoard L35-37) |  | rebuild to the board, remove old sections from the page (443.280) | CC-3 | 443.280 | PARTIAL |  | 10-24 02:00 UTC
42 | B · Board implementation (code audit e8a9f02b) | Customers | Customers › Home — board verdict CHROME-ONLY | old CustomersListView columns; Collected = billed - open (not payments) | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | CC-3 | 443.280 | OPEN |  | 10-24 02:00 UTC
43 | B · Board implementation (code audit e8a9f02b) | Vendors | Vendors › Home — board verdict CHROME-ONLY | old VendorsListView 13 columns; no Spend by category / Pays through panels | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | CC-3 | 443.280 | OPEN |  | 10-24 02:00 UTC
44 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Home — board verdict LAYERED | Payments view + old Button tab row + SettlementsTable under board | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | OPEN |  | 10-24 02:00 UTC
45 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Open — board verdict PARTIAL | extra columns Date started/Margin %/Checks/Verify; stacked under home |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | PARTIAL |  | 10-24 02:00 UTC
46 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Closed — board verdict PARTIAL | "Settlement (Closed) —" toggle shows nothing on home; extra columns |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | PARTIAL |  | 10-24 02:00 UTC
47 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Statement — board verdict LAYERED | old TourSettlementTab, header, KPI grid, sections L1005-1023 under the 2x2 panels; "paid on short miles" hardcoded | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | MERGED-UNVERIFIED | #27368 0c5f5376 Cursor 5:26 PM | 10-24 02:00 UTC
48 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Pre-Settlements — board verdict LAYERED | whole DriversPage mounted (Drivers header, 7 KpiCards, 2nd tab bar) | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | MERGED-UNVERIFIED | #27364 d6e9d60b 5:07 PM | 10-24 02:00 UTC
49 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Close — board verdict LAYERED | 7-step strip static; old single-page form below; KPIs "—" | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | OPEN |  | 10-24 02:00 UTC
50 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Company — board verdict REBUILT | duplicate rows (13696 Jose Antonio, 13691 Carlos twice); in-page Company tab still old period grain |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | PARTIAL | #27354 e8a9f02b; duplicate rows still live | 10-24 02:00 UTC
51 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Deductions — board verdict CHROME-ONLY | DriversPage shell; by-type all "—" while total $470.00 | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | MERGED-UNVERIFIED | #27355 / #27364; live 5:37 PM: by-type rows still "—" while total $470.00 | 10-24 02:00 UTC
52 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Cash Advances — board verdict CHROME-ONLY | old PageHeader, filter bar, 3rd tab bar, table; single-select Driver | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | MERGED-UNVERIFIED | #27358 eb08254d; live 5:38 PM page stuck "Loading…" | 10-24 02:00 UTC
53 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Escrow — board verdict CHROME-ONLY | 45-row all-holder list (Safety —, Driver — Not Visible, Genaro twice, owner as bond) | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | OPEN |  | 10-24 02:00 UTC
54 | B · Board implementation (code audit e8a9f02b) | Settlements | Settlements › Escrow Register — board verdict PARTIAL | no Release button; Target/Release "—" |  | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | PARTIAL |  | 10-24 02:00 UTC
55 | B · Board implementation (code audit e8a9f02b) | Fuel | Fuel › Home — board verdict CHROME-ONLY | old KPIs (Active plans —, Fleet MPG —, Loves sync Never); no Diesel by truck table / 7-tab structure | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | OPEN |  | 10-24 02:00 UTC
56 | B · Board implementation (code audit e8a9f02b) | Fuel | Fuel › 10 sub-tabs — board verdict CHROME-ONLY | pagination tiles ("This page", "Page size"), duplicated tiles, old bodies | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | Cursor | 443.280 | OPEN |  | 10-24 02:00 UTC
57 | B · Board implementation (code audit e8a9f02b) | Safety | Safety › Driver Files — board verdict LAYERED | old DriverSafetyCards/DriversListPage/Training inside collapsed details still mount; DrillKpiCard | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | CODEX | 443.280 | DONE-LIVE | #27367 40daa907; live 5:37 PM board only | 10-24 02:00 UTC
58 | B · Board implementation (code audit e8a9f02b) | Maintenance | Maintenance › Home — board verdict PARTIAL | IntegrationsStrip, RMBucketsGrid, embedded pages, 2 nav bars; old tiles; all trucks "PM reading unavailable" |  | rebuild to the board, remove old sections from the page (443.280) | LEAD | 443.280 | CODED | 893cc58eba #27375 + Home board: 4 tiles, fleet health line, PM countdown/engines/alerts/in-transit/severe, Arriving soon, At risk (all design sections; legacy strips gated to Settings / non-Home); 'PM reading unavailable' = row 108 (CC-2 odometer) | 10-24 02:00 UTC
59 | B · Board implementation (code audit e8a9f02b) | Maintenance | Maintenance › In Shop — board verdict LAYERED | 6 old blocks around board; no bay cards | Rule 07 additive-only applied to layouts | rebuild to the board, remove old sections from the page (443.280) | LEAD | 443.280 | OPEN |  | 10-24 02:00 UTC
60 | B · Board implementation (code audit e8a9f02b) | Driver Profile | Driver Profile › Board — board verdict NOT STARTED | 10-12 page still mounted; Angel shows "No current truck assignment" while on T156/13697 |  | rebuild to the board, remove old sections from the page (443.280) | LEAD | 443.280 | CODED | 8027099748 #27357 board (4 panels) + 75f1ed41d2 443.280 board-only test; RE-INSPECT at end: owner saw old layout + ~15 s load at 5:38 PM (before 443.280); 'No current truck assignment' = row 110 (CC-2) | 10-24 02:00 UTC
61 | B · Board implementation (code audit e8a9f02b) | Dispatch | Dispatch › Truck Planner — board verdict PARTIAL | bars show load # only — lane and $ · mi · $/mi missing; Unit column drivers "—" |  | rebuild to the board, remove old sections from the page (443.280) | CC-3 | 443.280 | MERGED-UNVERIFIED | 4ff9f272 bars lane + $/mi; #27359 | 10-24 02:00 UTC
62 | B · Board implementation (code audit e8a9f02b) | Dispatch | Dispatch › Book Load modal/side/spec — board verdict PARTIAL | center 1120 / side 660 vs board 1260 / 760; Load # left-aligned |  | rebuild to the board, remove old sections from the page (443.280) | CC-3 | 443.280 | MERGED-UNVERIFIED | 4ff9f272 1260/760, Load # right | 10-24 02:00 UTC
63 | B · Board implementation (code audit e8a9f02b) | Dispatch | Dispatch › Book Load trip types — board verdict REBUILT | — |  | rebuild to the board, remove old sections from the page (443.280) | CC-3 | 443.280 | DONE-LIVE |  | 10-24 02:00 UTC
64 | B · Board implementation (code audit e8a9f02b) | Insurance | Insurance › Home — board verdict REBUILT | page renders inside the Safety shell/header; tab bar old; "Lawsuits" tab extra |  | rebuild to the board, remove old sections from the page (443.280) | LEAD | 443.280 | CODED | d7e5e14e54 #27323 board (all design sections) + 8cff827545 #27400 own module shell; Lawsuits tab kept (not on the board) — owner decides | 10-24 02:00 UTC
65 | B · Board implementation (code audit e8a9f02b) | Legal | Legal › Home — board verdict REBUILT | — |  | rebuild to the board, remove old sections from the page (443.280) | CURSOR | 443.280 | DONE-LIVE |  | 10-24 02:00 UTC
66 | C · New approved designs (10-23 5:08 PM) | Reports/Dispatch | Dispatch › Load history (198 loads, every cell opens its record, load detail panel with timeline + money + linked records) | board on canvas + docs/design/v3 |  | build exactly, routes, two-way links, PDF/XLSX export, multi-select filters | CC-1 | 443.281 | OPEN |  | 10-24 14:00 UTC
67 | C · New approved designs (10-23 5:08 PM) | Reports/Dispatch | Reports › Loads report (week/month/customer/driver/truck/lane/trip type) | board on canvas + docs/design/v3 |  | build exactly, routes, two-way links, PDF/XLSX export, multi-select filters | CC-1 | 443.281 | OPEN |  | 10-24 14:00 UTC
68 | C · New approved designs (10-23 5:08 PM) | Reports/Dispatch | Reports › Driver settlement report (by settlement / driver, paid state) | board on canvas + docs/design/v3 |  | build exactly, routes, two-way links, PDF/XLSX export, multi-select filters | CC-1 | 443.281 | OPEN |  | 10-24 14:00 UTC
69 | C · New approved designs (10-23 5:08 PM) | Reports/Dispatch | Reports › Company settlement report (profit per closed trip) | board on canvas + docs/design/v3 |  | build exactly, routes, two-way links, PDF/XLSX export, multi-select filters | CC-1 | 443.281 | OPEN |  | 10-24 14:00 UTC
70 | C · New approved designs (10-23 5:08 PM) | Reports/Dispatch | Reports › Customer report (sales, open, aging, statement) | board on canvas + docs/design/v3 |  | build exactly, routes, two-way links, PDF/XLSX export, multi-select filters | CC-1 | 443.281 | OPEN |  | 10-24 14:00 UTC
71 | C · New approved designs (10-23 5:08 PM) | Reports/Dispatch | Reports › Vendor report (spend, open bills, category, 1099) | board on canvas + docs/design/v3 |  | build exactly, routes, two-way links, PDF/XLSX export, multi-select filters | CC-1 | 443.281 | OPEN |  | 10-24 14:00 UTC
72 | C · New approved designs (10-23 5:08 PM) | Reports/Dispatch | Reports home: add the 5 reports to the catalog; remove unrouted duplicates LoadHistoryPage.tsx / LoadsReportPage.tsx by replacing them with the board pages | board on canvas + docs/design/v3 |  | build exactly, routes, two-way links, PDF/XLSX export, multi-select filters | CC-1 | 443.281 | OPEN |  | 10-24 14:00 UTC
73 | E · Data / engine root causes | Driver pay | 3 delivered loads never accrued to A/P: 13663, 13687, 13688 ($2,056.34) | measured prod 10-23 | accrual runs once inline on the delivery tap; failure swallowed to console.warn | idempotent sweep (boot + 15 min + every stop path) + exception row + guard | CC-1 | 443.279 | OPEN |  | 10-24 02:00 UTC
74 | E · Data / engine root causes | Dispatch | 4 loads delivered_pending_docs with no final-stop actual departure: 13691, 13694, 13696, 13697 | measured prod 10-23 | status advanced without stop evidence (two sources of truth) | status derived from final stop; repair via stop engine with real times; guard | CC-3 | 443.279 | MERGED-UNVERIFIED | #27360 528fd12c delivered only via final stop + history repair; 358b7c12 | 10-24 02:00 UTC
75 | E · Data / engine root causes | Settlements | Settlement load-cost totals 25-50% below recount; P-0119/P-0113 $0 costs; GPS real miles 4,855 vs 1,110 | measured prod 10-23 | not traced yet | fix rollup or recount; per-load before/after | CC-1 | 443.278 | OPEN |  | 10-24 02:00 UTC
76 | E · Data / engine root causes | Settlements | 0 of 85 closed settlements marked paid ($127,897.75) | measured prod 10-23 | driver payments never linked to settlements | payment link on bank match; owner matching tonight | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
77 | E · Data / engine root causes | A/R | 0 customer payments / Faro purchases applied: all $621,076.72 open incl. 57 advanced invoices | measured prod 10-23 | factoring purchase close never applied to invoices | owner closes factoring purchases tonight; verify engine applies | CC-2 | 443.279 | OPEN |  | 10-24 02:00 UTC
78 | E · Data / engine root causes | Banking | 1090 Undeposited $170,210.48 (33 Faro advances never deposited) -> GL bank -$88,433.89 | measured prod 10-23 | advances posted to 1090 without the deposit step | owner matches; CC-2 proves match path on fork first | CC-2 | 443.277-A/279 | OPEN |  | 10-24 02:00 UTC
79 | E · Data / engine root causes | Cash Flow | Card payables not in forecast: Dreamline 2510 $187,894.21, WEX 2520 $29,156.88 | measured prod 10-23 | diesel row is run-rate only | statements on due dates + run-rate only for unbilled fills; guard | CC-1 | 443.277-B | OPEN |  | 10-24 02:00 UTC
80 | E · Data / engine root causes | Dispatch | Load 13699 Bradley IL delivery stop city-only (no street/ZIP) | measured prod 10-23 | data entry | address from rate confirmation via stop engine; booking requires geocodable address | CC-3 | 443.278 | OPEN |  | 10-24 02:00 UTC
81 | E · Data / engine root causes | HOS | 222,587 duty events on merged driver shells | measured prod 10-23 | logs are write-once; reads filter single driver_id | shared read helper following merged_into + guard | CC-2 | 443.278 | OPEN |  | 10-24 02:00 UTC
82 | E · Data / engine root causes | Accounting | Rafael salary bill P-0069 / 13530 $300 unpaid since 08-21, due_date NULL | measured prod 10-23 | salary bill created without due date | set due date via engine; guard | CC-1 | 443.279 | OPEN |  | 10-24 02:00 UTC
83 | E · Data / engine root causes | Accounting | R2: 241 Dreamline statement discount JEs ($10,744.65) -> card-credit documents | measured prod 10-23 | statement engine wrote handwritten JEs | B writer 10x25 batches (column is_credit live e568b60f) | CC-2 | 443.260 | PARTIAL | afd3fd334e #27384 coded; prod 198/241 done TB 0; 43 left PAUSED (AUTH-453, owner renews) | 10-24 02:00 UTC
84 | E · Data / engine root causes | Settlements | 5 settlement headers re-derive (P-0105/0107/0108/0109/0115); P-0115 carries two NBs incl. 13663 | measured prod 10-23 | stale first_load_id | owner-step route | CC-2 | 443.260 | CODED | afd3fd334e #27384; prod AUTH-454 run done, TB 0 | 10-24 02:00 UTC
85 | E · Data / engine root causes | Vendors | All 30 vendors have no category | measured prod 10-23 | category never set | set categories (owner list) + required on create | CC-1 | 443.281 | OPEN |  | 10-24 02:00 UTC
86 | E · Data / engine root causes | Settlements | 3 recent closed settlements have no number / company settlement not opened (P-0119, P-0113, P-0117) | measured prod 10-23 | close flow does not assign number | assign at close; guard | CC-1 | 443.281 | OPEN |  | 10-24 02:00 UTC
87 | E · Data / engine root causes | Telematics | verify-no-dead-schema: telematics.vehicle_latest_position_cache has no reader | measured prod 10-23 | D074 cache added, reader not wired | positions/latest reads it or drop by migration | CC-1 | 443.278 | DONE-LIVE | LEAD #27383 d85ade3b: guard credits view-read tables; verify-no-dead-schema exit 0 on main | 10-24 02:00 UTC
88 | E · Data / engine root causes | Live gate | No-5xx live GET guard | measured prod 10-23 | merged #27346 |  | CC-3 | 443.268-A | DONE-LIVE | #27346 + be076e3d fastify.inject | 10-24 02:00 UTC
89 | F · Live screenshot findings 10-23 5:10 PM (new) | Cash Flow | Three different opening-cash figures: Home $25,533.37, Manual bank total $102,867.17, Manual opening $0.00 | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-1 | 443.281 | CODED | d86e35ce75 #27453 LEAD 443.283 opening cash = operating accounts $25,533.37 | 10-24 02:00 UTC
90 | F · Live screenshot findings 10-23 5:10 PM (new) | Cash Flow | Manual "bank balances" counts card payables and Faro as cash: Dreamline -$140,226.34 (GL 2510 -$187,894.21), WEX +$29,156.88 (a payable shown positive), Faro Factoring $175,650.00 | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-1 | 443.281 | CODED | d86e35ce75 #27453 LEAD 443.283 cards/Faro no longer counted as cash | 10-24 02:00 UTC
91 | F · Live screenshot findings 10-23 5:10 PM (new) | Cash Flow | Actual vs Projected: Actual income $0.00 every day 10-16..10-23 while BofA received deposits (Faro wire +$10,629.09 10-22) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-1 | 443.281 | DONE-LIVE | LEAD #27383 d85ade3b live: AvP Oct actual income $208,031.56 / expense $205,270.54 from operating bank; 283b is_credit form (exit 0 direction guard) | 10-24 02:00 UTC
92 | F · Live screenshot findings 10-23 5:10 PM (new) | Cash Flow | Rolling Ledger lists Faro advances FAC-2026-00009… as income 49-74 days overdue (advance money already received = double count with 1090) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-1 | 443.281 | DONE-LIVE | LEAD #27383: rolling ledger factoring advances matched by bt.matched_factoring_advance_id; no double count | 10-24 02:00 UTC
93 | F · Live screenshot findings 10-23 5:10 PM (new) | Accounting | Open bills $126,443.92 / 179 vs A/P subledger $126,437.22 / 177 (diff $6.70, 2 bills) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-1 | 443.281 | OPEN |  | 10-24 02:00 UTC
94 | F · Live screenshot findings 10-23 5:10 PM (new) | Accounting | Open invoices header $624,076.72 / 165 vs aging $621,076.72 / 164 (proforma 169-13690 $3,000 counted in header) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-1 | 443.281 | CODED | eef797220e #27452 LEAD 443.285 Open invoices = issued only = GL A/R $621,076.72 | 10-24 02:00 UTC
95 | F · Live screenshot findings 10-23 5:10 PM (new) | Accounting | Cash pulse Oct: IN $0.00 / OUT $1,590.00 while Banking shows money in $216,532.56 / out $239,059.03 | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-1 | 443.281 | OPEN |  | 10-24 02:00 UTC
96 | F · Live screenshot findings 10-23 5:10 PM (new) | Accounting | QBO sync "Not connected" | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | OWNER | 443.281 | OPEN |  | 10-24 02:00 UTC
97 | F · Live screenshot findings 10-23 5:10 PM (new) | Banking | Reconciliation drift: BofA bank $1,808.13 vs book -$88,433.89 (diff $90,242.02); Relay Fuel Wallet listed twice | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
98 | F · Live screenshot findings 10-23 5:10 PM (new) | Factoring | KPI renders raw "175650.000000000000" and "170210.480000000000"; True cost 0.00% with fees $2,634.76 | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | Cursor | 443.281 | PARTIAL | main: NUMERIC fixed (7349992008); one-source True cost = Lead branch claude/lead-row98-factoring-kpi-units, pushing | 10-24 02:00 UTC
99 | F · Live screenshot findings 10-23 5:10 PM (new) | Unexpected | Possible duplicates 0 while bank lines repeat (460.01 on 10-03 and 10-05; 155.86 twice on 10-07) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
100 | F · Live screenshot findings 10-23 5:10 PM (new) | Customers | 201 possible duplicate customers flagged; billed shows $624,076.72 (incl. proforma) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-3 | 443.281 | OPEN |  | 10-24 02:00 UTC
101 | F · Live screenshot findings 10-23 5:10 PM (new) | Vendors | 86 possible duplicate vendors; Open bills $126,443.92 includes driver bills; Spend YTD $351,241.23 vs expenses $353,241.23 | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-1 | 443.281 | OPEN |  | 10-24 02:00 UTC
102 | F · Live screenshot findings 10-23 5:10 PM (new) | Settlements | Home "Week of Oct 18" lists closed settlements (P-0108 etc.) with status Open; "Settlement (Closed)" toggle empty; Drivers w/ debt 0 | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | Cursor | 443.281 | OPEN |  | 10-24 02:00 UTC
103 | F · Live screenshot findings 10-23 5:10 PM (new) | Settlements | Company Settlements shows 0 / Loading for ~6 s before data (87 closed, 6 not opened) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | Cursor | 443.281 | PARTIAL | #27354 e8a9f02b; duplicate rows still live | 10-24 02:00 UTC
104 | F · Live screenshot findings 10-23 5:10 PM (new) | Fuel | Cards: 0 card assignments; Relay issuer blank | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
105 | F · Live screenshot findings 10-23 5:10 PM (new) | Fuel | Relay unmatched 257 fills (truck matched, driver never matched) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
106 | F · Live screenshot findings 10-23 5:10 PM (new) | Fuel | History & savings / Compliance: every value "Not available"; Loves prices never synced | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
107 | F · Live screenshot findings 10-23 5:10 PM (new) | Fuel | Home MTD spend $91,539 vs Fuel board figure; Avg $/gal $5.44 | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
108 | F · Live screenshot findings 10-23 5:10 PM (new) | Maintenance | All 43 trucks "PM reading unavailable"; 0 work orders; MTD cost $0.00 | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
109 | F · Live screenshot findings 10-23 5:10 PM (new) | Dispatch | Load board HOS columns blank for most trucks; Truck planner driver column "—" for trucks with drivers | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-3 | 443.281 | OPEN |  | 10-24 02:00 UTC
110 | F · Live screenshot findings 10-23 5:10 PM (new) | Driver Profile | Angel Sosa: "No current truck assignment" while on T156 (13697); documents all "Not recorded" | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
111 | F · Live screenshot findings 10-23 5:10 PM (new) | Insurance | Insurance page renders inside the Safety header/tab shell | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | CODED | 8cff827545 #27400 — already on main; CC-2 verified /insurance/* InsuranceModuleShell | 10-24 02:00 UTC
112 | F · Live screenshot findings 10-23 5:10 PM (new) | Legal | Open matters 0 on page while legal.matters holds 18 rows (test records) | live Chrome 10-23 5:10 PM, screenshot in baseline folder | to trace | root cause + fix + guard | CC-2 | 443.281 | OPEN |  | 10-24 02:00 UTC
113 | E · Data / engine root causes | Banking | 43 Plaid PENDING lines in October never replaced by their posted lines (e.g. SOUTH TX TRUCK CENTERS -460.01 pending 10-03 + posted 10-05) -> Banking Money in/out ($216,532.56 / $239,059.03) and Unexpected "possible duplicates" count them twice | prod 10-23 6:00 PM | ingest keeps pending rows after the posted row arrives (pending_transaction_id not reconciled) | on posted arrival, retire the pending row (merged_into or void with reason); backfill; guard: no pending row older than 10 days with a posted twin | CC-2 | 443.282 | OPEN |  | 10-24 02:00 UTC
114 | A · Owner requests (last 24 h) | Process | Cursor confirmation of 443.282 (owner-authorized build exactly as specified) | box posted 5:45 PM |  |  | Cursor | 443.282 | OPEN |  | 10-24 02:00 UTC
115 | G · Main reds / guards | Guards | verify-stops-are-geocoded red (13699) — live-data exception for CC-2 migration |  |  |  | CC-2 | 443.278/280/281 | OPEN |  | 10-24 02:00 UTC
116 | G · Main reds / guards | Guards | verify-resettlement-origin-load-dates — guard retarget to board labels |  |  |  | CC-3 | 443.278/280/281 | MERGED-UNVERIFIED | #27356 6b9b2dc0 | 10-24 02:00 UTC
117 | G · Main reds / guards | Guards | verify-entity-label-rejects-uuid-shaped-name — restore protection in accounting hub |  |  |  | CC-3 | 443.278/280/281 | MERGED-UNVERIFIED | #27356 6b9b2dc0 | 10-24 02:00 UTC
118 | G · Main reds / guards | Guards | verify-board-page-no-legacy-sections (new) — stops layering |  |  |  | Codex | 443.278/280/281 | CODED | 3409d7a383 #27379 (Codex) selftest 10/10, scan 0 | 10-24 02:00 UTC
119 | G · Main reds / guards | Guards | verify-entity-filters-multi-select (new) — fails on single-select entity filters |  |  |  | LEAD | 443.278/280/281 | OPEN |  | 10-24 02:00 UTC
120 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Fuel › Questions › Review | D001: Clicking Review throws undefined `load_number` in FuelAssignmentPopup; whole-app crash | inline: Fuel Questions crash | class E | Review opens a usable panel; missing data handled without crashing | CC-2 | 443.257-D | MERGED-UNVERIFIED | bf7dadd3 | 10-24 02:00 UTC
121 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Home › Overview › Money tiles | D002: Currency values omit cents | inline: Home | class M | Currency always two decimal places | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
122 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Home › Overview › Driver day summary | D003: Names render all-uppercase | inline: Home | class N | Full proper-case names, honoring exceptions | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
123 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Home › Overview › Weekly revenue | D004: Axis dates use DD/MM without year | inline: Home | class D | MM/DD/YYYY under this round's explicit rule | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
124 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Home › Overview › Driver summary request | D005: `/api/v1/telematics/driver-day-summary` 5,071 ms | pending: resource timing | class P | API at most 2,000 ms | CC-2 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
125 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Drivers | D006: Link targets `/drivers` outside module | pending: DOM | class B | Keep Settlements context | LEAD | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
126 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Profiles | D007: Link targets `/drivers/profiles` | pending: DOM | class B | Keep Settlements context | Cursor | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
127 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Pre-Settlements | D008: Link targets `/drivers/pre-settlements` | pending: DOM | class B | Keep Settlements context | Cursor | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
128 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Feed Gate | D009: Link targets `/feed-gate` | pending: DOM | class B | Keep Settlements context | Cursor | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
129 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Cash Advances | D010: Link targets `/cash-advances` | pending: DOM | class B | Keep Settlements context | Cursor | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
130 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Liabilities | D011: Link targets `/liabilities` | pending: DOM | class B | Keep Settlements context | Cursor | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
131 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Escrow | D012: Link targets `/accounting/escrow` | pending: DOM | class B | Keep Settlements context | Cursor | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
132 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Pay Rate Templates | D013: Link targets `/drivers/pay-rate-templates` | pending: DOM | class B | Keep Settlements context | Cursor | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
133 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Navigation › Deductions | D014: Link targets `/drivers/deductions` | pending: DOM | class B | Keep Settlements context | Cursor | 443.257-D | CODED | 0512ef14cd 443.258-B (tab -> /driver-finance/…, route mounted) + Lead guard verify-settlements-subnav-stays-in-module | 10-24 02:00 UTC
134 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › List › Driver names | D015: All-uppercase names displayed | pending: DOM | class N | Full proper-case names | CC-1 / Cursor | 443.257-D | DONE-LIVE | settlements home proper case 10-23 5:12 PM | 10-24 02:00 UTC
135 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Fuel › Questions › Table | D016: No column chooser in rendered DOM | pending: DOM | class T | Gear column chooser | Cursor | 443.257-D | MERGED-UNVERIFIED | 0512ef14 | 10-24 02:00 UTC
136 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Fuel › Questions › Table headers | D017: Headers have no sorting controls | pending: DOM | class T | Sortable columns | Cursor | 443.257-D | MERGED-UNVERIFIED | 0512ef14 | 10-24 02:00 UTC
137 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Fuel › Cards › Assign card drawer | D018: Six input controls measured 38px high | inline: Assign fuel card | class I | Inputs 32px | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
138 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Fuel › Cards › Driver options request | D019: `/api/v1/mdata/drivers` 4,522 ms in audit session | pending: resource timing | class P | API at most 2,000 ms | CC-2 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
139 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Fuel › Expense mapping › Mapping request | D020: `/api/v1/accounting/expense-category-map` 8,831 ms | pending: resource timing | class P | API at most 2,000 ms | CC-1 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
140 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Dispatch › Home › Round-trip exposure | D021: Driver names abbreviated to initials | pending: DOM | class N | Full proper-case names | Cursor | 443.257-D | RE-VERIFY | loads list shows full names 10-23 | 10-24 02:00 UTC
141 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Dispatch › Home › Return / idle / missing-bill tables | D022: Driver names all-uppercase | pending: DOM | class N | Full proper-case names | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
142 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Dispatch › Book Load › Stop fields | D023: Both ZIP controls measured 28px high × 381.33px wide | inline: Book Load | class I | ZIP 32px high × 88px wide | Cursor / CC-3 | 443.257-D | DONE-LIVE | #27294 ZIP 88px | 10-24 02:00 UTC
143 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Dispatch › Book Load › Presentation | D024: Long A–E form; no Side panel / Center toggle or five-step flow present | inline: Book Load | class V | Same component with side/center toggle and specified five-step layout | Cursor / CC-3 | 443.257-D | DONE-LIVE | Side panel ¦ Center toggle live 10-23 5:19 PM | 10-24 02:00 UTC
144 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Dispatch › Load Costs › Pickup / delivery cells | D025: Dates display M/D/YY | inline: Load Costs | class D | MM/DD/YYYY | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
145 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Dispatch › Load Costs › Driver names | D026: All-uppercase names | inline: Load Costs | class N | Full proper-case names | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
146 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Dispatch › Load Costs › Settlement/Tour link | D027: Several links have only an em dash as label despite a settlement destination | inline: Load Costs | class N | Resolve human-readable settlement/tour display identifier | CC-1 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
147 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Tasks › Create Task › Inputs | D028: Eleven single-line inputs measured 38px high; textarea excluded | inline: Create Task | class I | Single-line inputs 32px | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
148 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Tasks › Exceptions › Since column | D029: ISO YYYY-MM-DD rendered | pending: DOM | class D | MM/DD/YYYY | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
149 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Driver Hub › Driver Scheduler › Date range | D030: Subtitle uses YYYY-MM-DD; grid uses MON-DD | pending: DOM | class D | MM/DD/YYYY under explicit round requirement | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
150 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Driver Hub › Driver Scheduler › Driver cells | D031: All-uppercase and inconsistent surname casing | pending: DOM | class N | Full proper-case names | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
151 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Driver Hub › Driver Scheduler › Assign Temp Cover | D032: Five single-line inputs measured 38px high; pickers about 2,477px wide and dates about 1,203px | pending: screenshot timed out | class I | 32px inputs and content-appropriate form widths | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
152 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Maintenance › Home / Fleet Table › Money tiles | D033: MTD Cost, Open $ and severe-repair total omit cents | inline: Maintenance Home | class M | Currency always two decimal places | LEAD | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
153 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Maintenance › Create Work Order › Drawer inputs | D034: Visible single-line inputs measured 38px; customer picker about 2,408px wide, open-date input about 766px | pending: measured DOM | class I | 32px inputs; dates 150px; content-appropriate widths | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
154 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Maintenance › Active WOs › Table headers | D035: Load, Driver, Vendor, Bill, JE and Timing headers have no sorting button, unlike adjacent headers | pending: DOM | class T | Sortable data columns | LEAD | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
155 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Safety › Hours & Fatigue › Driver roster | D036: Mixed proper-case and all-uppercase driver names | pending: DOM | class N | Full proper-case display with exceptions | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
156 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Safety › Hours & Fatigue › Create HOS Violation | D037: Seven visible inputs measured 38px high | pending: measured DOM | class I | 32px single-line inputs | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
157 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Compliance › Filings / Overview › Driver labels | D038: Mixed proper-case and uppercase driver labels in populated tables | pending: DOM | class N | Full proper-case display with exceptions | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
158 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Driver Profile › Create Driver › Identity step | D039: Fifteen visible inputs measured 38px; CDL state about 199px wide | pending: measured DOM | class I | Inputs 32px; state 64px | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
159 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Fleet › Create Trailer › Identity drawer | D040: Seven visible inputs measured 38px high | pending: measured DOM | class I | Inputs 32px | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
160 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Insurance › Policies › Create policy step 1 | D041: Eight visible inputs measured 38px high | pending: measured DOM | class I | Inputs 32px | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
161 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Cash Flow › Projected Auto › Seven-day outlook | D042: Currency abbreviated with k suffix and zero shown without cents | pending: DOM | class M | Full currency with two decimals | Cursor | 443.257-D | OPEN | still +15,386 no cents 10-23 5:10 PM | 10-24 02:00 UTC
162 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Cash Flow › Projected / Rolling / Manual › Date labels and cells | D043: Day labels and invoice/due cells omit year and use month names | pending: DOM | class D | MM/DD/YYYY for business dates | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
163 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Accounting › Home › Settlement / transaction links | D044: Driver/vendor names still all-uppercase | pending: DOM | class N | Proper-case full names with exceptions | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
164 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Banking › Home › Drift alert as-of | D045: Raw ISO timestamp rendered, including T and Z | pending: DOM | class D | Local business date MM/DD/YYYY; readable time if needed | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
165 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Banking › Home › Drift account label | D046: Several alerts show only generic Account rather than the account display name | pending: DOM | class N | Resolve full account display name | CC-1 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
166 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Factoring › Home › Ready-to-factor customers | D047: All-uppercase customer names displayed | pending: DOM | class N | Proper-case names honoring acronym exceptions | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
167 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Customers › Create Customer › Billing address | D048: State and ZIP each measure 38px high and 209.33px wide | pending: measured DOM | class I | 32px high; state 64px and ZIP 88px wide | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
168 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Customers › Directory › Customer display names | D049: Mixed uppercase and proper-case customer labels | pending: DOM | class N | Proper-case display honoring acronym exceptions | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
169 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Inventory › Create part › Unit cost | D050: Money input measures 28px high | pending: measured DOM | class I | Single-line input 32px high | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
170 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | 425C › Profiles & Defaults › Company Name | D051: Input measures 30.67px high | pending: measured DOM | class I | Single-line input 32px | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
171 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | 425C › History › Filed timestamp | D052: Month/day rendered without zero padding | pending: DOM | class D | MM/DD/YYYY plus readable local time | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
172 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Lists › Names Master › Name column | D053: Mixed uppercase and proper-case customer names | pending: DOM | class N | Proper-case display honoring exceptions | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
173 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Reports › Custom report builder › Report name | D054: Input measures 26.67px high and 1156.38px wide | pending: measured DOM | class I | Single-line input 32px; content-appropriate width | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
174 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Docs › All Entities › Entity names | D055: Mixed uppercase and proper-case driver names | pending: DOM | class N | Full proper-case display | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
175 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Docs › Upload Document › Category/entity/date inputs | D056: Four visible inputs 38px; date fields about 1201px wide | pending: measured DOM | class I | Inputs 32px; date widths fit MM/DD/YYYY | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
176 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Users › Master-detail › User labels | D057: Repeated generic User labels and mixed name capitalization | pending: DOM | class N | Resolved full names with proper-case display | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
177 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Users › Create User › Name/email/role | D058: Three visible inputs 38px high | pending: measured DOM | class I | Single-line inputs 32px | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
178 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Program › Scenario tracker › Certification timestamp | D059: Raw database timestamp with fractional seconds and +00 timezone | pending: DOM | class D | MM/DD/YYYY and readable local time | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
179 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | System › Transaction Health › Generated/document dates | D060: Month-name timestamps instead of MM/DD/YYYY | pending: DOM | class D | MM/DD/YYYY with readable CT time | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
180 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | System › Transaction Health › Journal-entry and bill-payment labels | D061: Raw UUIDs are visible display labels | pending: DOM | class N | Human-readable display identifiers | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
181 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | System › Transaction Health › Wiring preview DR/CR | D062: Currency values lack dollar signs | pending: DOM | class M | Currency formatted $1,234.56 | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
182 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Reports › Scheduled subscriptions › Add subscription timezone | D063: Input measures 30.67px high | pending: measured DOM | class I | Single-line inputs 32px | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
183 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Accounting › Create Manual JE › Step 2 Lines | D064: Header summary renders `Date: 2026-10-22`, while Step 1 correctly shows `10/22/2026` | inline: Manual JE Step 2 | class D | Display dates consistently as MM/DD/YYYY | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
184 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Accounting › Create Manual JE › Step 2 Lines | D065: Class selector overlaps the adjacent Debit field; line controls overflow the drawer horizontally | inline: Manual JE Step 2 | class V | Distinct aligned non-overlapping fields contained in the drawer | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
185 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Banking › Home / Record Transfer › Drawer footer | D066: Persistent alert stack renders above the open transfer drawer and obscures its bottom action area | inline: Record Transfer drawer | class V | Alerts must not obscure drawer controls; close/cancel remains accessible | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
186 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Accounting › Bills / Bill detail › Payments on this bill | D067: Two linked payments render as `Payment — not visible` rather than distinct display identifiers | observed Chrome AX | class N | Readable distinct payment identifiers; no UUID fallback | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
187 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Accounting › Bill detail › Journal Entity column | D068: Five journal rows show raw UUID entity labels | observed Chrome AX | class N | Resolve human-readable entity names | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
188 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Accounting › Reclassify › Account balance heading | D069: Date displays `10/23/26` while date filters use `10/23/2026` | observed Chrome AX | class D | MM/DD/YYYY consistently | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
189 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Banking › Categorize / Match › Candidate dates | D070: Loaded candidate list displays YYYY-MM-DD dates while transaction header uses MM/DD/YYYY | observed Chrome AX | class D | MM/DD/YYYY consistently | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
190 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Banking › Categorize / Match › Candidate payee labels | D071: Candidate names mix ALL CAPS and proper case | observed Chrome AX | class N | Full names in proper case, respecting approved exceptions | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
191 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Banking › Relay card › Wallet balance tile | D072: Five-digit currency omits thousands separator | observed Chrome AX | class M | Currency formatted $1,234.56 | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
192 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Cash Flow › Projected Auto › Expected Expenses driver labels | D073: Driver Bill labels mix ALL CAPS and proper case | observed Chrome AX | class N | Full names in proper case, respecting approved exceptions | Cursor | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
193 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Dispatch › Truck Line › Initial data requests | D074: Network capture: truck-line 11,425 ms; units-without-load 4,810 / 8,819 ms; positions/latest 4,193 ms; detention/board 3,217 ms | Chrome Network timing; payloads not retained | class P | API responses within 2 seconds; responsive row rendering | CC-3 | 443.257-D | PARTIAL | positions 168 ms / detention 203 ms (#27252); truck-line fc0a287e unverified | 10-24 02:00 UTC
194 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Open Tours › PU / DEL dates | D075: Rendered dates use OCT-21 / OCT-23 rather than numeric month/day/four-digit year | observed Chrome AX | class D | MM/DD/YYYY dates | Cursor | 443.257-D | OPEN | still OCT-21 on open tours 10-23 5:12 PM | 10-24 02:00 UTC
195 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Escrow Accounts › Holder labels | D076: One visible holder link says Driver — Not Visible instead of a resolved full name | observed Chrome AX; names not retained | class N | Readable full holder name or explicit unavailable-record explanation | Cursor | 443.257-D | OPEN | still "Driver — Not Visible" 10-23 5:14 PM | 10-24 02:00 UTC
196 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Settlements › Escrow Accounts › Updated dates | D077: Date portion uses unpadded month/day before time | observed Chrome AX | class D | MM/DD/YYYY with consistently formatted time where needed | Cursor | 443.257-D | OPEN | still 9/28/2026 unpadded 10-23 5:14 PM | 10-24 02:00 UTC
197 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Maintenance › Road Service / Create Roadside WO › Ticket # and Location inputs | D078: Two single-line dialog text inputs measure 38 CSS px high | read-only DOM bounding rectangles; opened and cancelled | class I | 32 CSS px input height under V3 audit contract | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
198 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Customers › Per-Customer P&L › Classification labels | D079: Visible tags read high_margin and past_due | observed Chrome AX | class N | Human-readable labels, not snake_case internal codes | CC-3 | 443.257-D | OPEN | not re-verified since audit | 10-24 02:00 UTC
199 | H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | Coverage | Codex audit coverage is partial depth — remaining tabs, drawers and record pages of every module still to audit | coverage ledger lists pending areas |  | finish the audit module by module, append D080+ | LEAD | 443.281 | OPEN |  | 10-24 02:00 UTC
200 | F · Money tie-outs | Accounting | Accounting "Open invoices" KPI $624,076.72/165 vs GL A/R 1100 $621,076.72/164 | prod 7:22 PM: diff $3,000.00 = 1 proforma (169-13690) | KPI filtered only void; proforma counted | issuedInvoice predicate on all 4 KPI aggregates + guard test | LEAD | 443.285 | CODED | #27452 eef79722
201 | E · Main static reds | Platform | 443.284: 7 main static reds from 10-23 board merges block every push | 7:40 PM measured: 2 fixed (parity footer, factoring nav), 5 red | board merges changed contracts guards pin | retarget guards to board contract with failing plants; never baseline | CC-2 | 443.284 | CODED | 804f5f38c2 #27409 (CC-2)
202 | E · Main static reds | Fuel | verify-no-internal-payload-in-notes red: dreamline-statement-import memo interpolates input.expenseId | exit 1 on main 1c118712 | afd3fd334e memo template | human memo + spine link | CC-2 | 443.284 | CODED | 804f5f38c2 memo + 5892782b30 structural link (CC-2)
203 | F · Money tie-outs | Linkage | Linkage gate red (verify-every-load-born-posting-carries-its-load) blocks every money push | uncapped prod: 43 discount legs ($1,976.20) on old load + 12 settlement legs on 4 settlements | AUTH-453 / AUTH-454 repairs built (CC-2 #27384) but never run on prod | fork rehearsal then prod, TB 0 before/after | LEAD | 443.287 | PAUSED | AUTH-454 done; AUTH-453 198/241 on prod — owner: resume after all rows coded
204 | F · Money tie-outs | Fuel | Statement card discount / difference is a separate expense with NO link to its receipt; copies the load once, never follows a move | receipt id only in memo (also the no-internal-payload red) | child document not linked to parent; move paths select by fuel link | parent_expense_id + source link; one moveExpenseFamilyToLoad; guard child-follows-parent | CC-2 | 443.288-A | CODED | 5892782b30 #27432 443.288-A (CC-2); AUTH-457 ready for Lead
205 | A · Owner requests (last 24 h) | Expenses | OWNER: every expense-to-load assignment confirmed by dispatcher or closer — always | 10-23 7:59 PM CT | machine writers set the load as final today | load_confirmation proposed¦confirmed; confirm engine; settlement close refuses proposed | CC-2 | 443.288-B | CODED | e2048ed4b4 #27460 443.288-B (CC-2)
206 | A · Owner requests (last 24 h) | Dispatch / Settlements | Expense load confirmations queue (Dispatch + Settlements Close), multi-select, bulk confirm | — | — | V3 board, two-way links | Cursor | 443.288-C | CODED | 5f0c13e0af #27445 Cursor 443.288-C queue; bound to CC-2 engine e2048ed4b4 by Lead claude/lead-443-301-frontend-tsc
207 | E · Main static reds | Guards | Guards for 443.288 (child follows parent, no machine-final load, close refuses proposed, family moves) | — | — | failing plants; wired with each change | CC-2 | 443.288-D | OPEN
208 | E · Main static reds | Platform | Main CI red at verify:arch-design (/insurance, Fuel Planner settings + Expense mapping) | nothing removed: /insurance/* route; V3Panel titles | reader read literals + h3 only | reader credits splat bases + V3 panel titles, plants | LEAD | 443.289 | DONE | #27422 b1192f1e; plants red; CI re-run pending
209 | E · Main static reds | Guards | 107 main static reds outside baseline split by seat | full verify:static 8:35 PM | board merges + stale text guards | fix code or retarget with plants | Cursor | 443.290 | IN PROGRESS | #27407 list; CC-1 #27413/#27416/#27417; Lead 4 Cash Flow in 443.283c
210 | E · Guards | Platform | 6,266 guard scripts (488 live, ~5,700 source-text, 316 slate-color copies) | census 8:50 PM | one guard per bug, never merged | consolidate: one check per family; text never guards money | CC-2 | 443.291 | OPEN | after Codex filters PR
211 | F · Money tie-outs | Cash Flow | Actual vs Projected + Manual reverted to pre-board code by #27390 | AvP 626→380 lines; 4 KPIs + chart gone | #27390 replaced files with old versions | restore approved boards | LEAD | 443.283c | CODED | #27453 d86e35ce
212 | A · Owner requests (last 24 h) | Settlements | Settlement number: P-number shown; real series not assigned by our system | 82 numbered (max 5851), 12 not; 5 closed today without number | close engine never assigns | auto-assign at close, next in series, shown everywhere | CC-1 | 443.292-A | OPEN
213 | A · Owner requests (last 24 h) | Settlements | Tour dates wrong (P-0114 10/20→10/20; real 10/16→10/23) | open headers period = creation day; UTC midnight renders a day early | writer stamps creation date | first pickup → last delivery, DATE type, re-derive 12 | CC-1 | 443.292-B | CODED | 7349992008 443.292-B tour period dates in Central time (CC-1)
214 | A · Owner requests (last 24 h) | Settlements | Settlements tab week list: closed show Open; duplicate empty driver rows | P-0107 closed reads Open | wrong status field | status + payment status columns | CC-1 | 443.292-C | CODED | 7349992008 443.292-C Settlement + Payment status columns (CC-1)
215 | A · Owner requests (last 24 h) | Settlements | Escrow register: all same date/source, no load numbers; escrow is per load | escrow_ledger 58 rows: load 0, settlement 2 | close engine writes no load/settlement | per-load rows + backfill; Date·Settlement#·Load# | CC-1 | 443.292-D | OPEN
216 | A · Owner requests (last 24 h) | Accounting | Bill Payments shows driver escrows — not bill payments | 218 rows $7,303.21 all settlement deductions; 0 cash | deduction recorded as bill_payment | deduction application kind; Bill Payments = cash only; A/P still 126,443.92 | CC-1 | 443.292-E | OPEN
217 | A · Owner requests (last 24 h) | Settlements | Empty closed settlements P-0123, P-0124 ($0, 0 lines) | closed 10/23 | close engine allows empty | refuse empty; void both via engine | CC-1 | 443.292-F | OPEN
218 | A · Owner requests (last 24 h) | Settlements | Statement must match the owner settlement document (5753 format): loads+stops+dates, fuel, expenses, per-load deductions, P&L | P-0114 statement shows no dates, $0 deductions line, fuel — | summary page, not the document | 8 sections as Company/Driver_Settlement_5753 | Cursor | 443.293-A | OPEN
219 | A · Owner requests (last 24 h) | Dispatch / Settlements | Settlement Close: what it does; should be a button in Dispatch | it is the 7-step close wizard | only reachable in Settlements | Close settlement button in Dispatch opens the same wizard; tab = closer queue | Cursor | 443.293-B | OPEN
220 | A · Owner requests (last 24 h) | Accounting | Inspect every Accounting tab; only Bills first tab is right | owner 8:52 PM | tabs not on V3 board grammar | every tab to Bills-first-tab grammar, screenshots | Cursor | 443.293-C | OPEN
221 | A · Owner requests (last 24 h) | All modules | Override: one reasons catalog + one button app-wide; owner/accountant confirm only; others dropdown; no typing | 67 files with ad-hoc override reasons | no shared catalog/engine | catalogs.override_reasons + recordOverride + OverrideButton; replace 67 | CC-3 | 443.294 | OPEN
222 | A · Owner requests (last 24 h) | All modules | Popup standard app-wide + Fuel assignment popup redesign | Modal falls back to 85% width; 140 of 155 popup files pass no size | no width caps except xl | sm 480/md 720/lg 960/xl 1280; default md; sections; design V3-Modal-FuelAssignment | Cursor | 443.295 | OPEN | design PR #27439
223 | E · Data / engine root causes | Fuel | Fuel evidence: odometer blank, "no GPS truck" while truck parked at pump | 360 of 818 fills no station coords; 713 no GPS truck; T173 parked 3:09–4:05 PM odo 438,489.5 | station never geocoded; resolver needs breadcrumb at fill minute | geocode stations; parked-hold resolver; odometer at fill | CC-2 | 443.296 | OPEN
224 | A · Owner requests (last 24 h) | Process | CODE-COMPLETE MODE: code every row, verify at the end | owner 9:40 PM | — | rows assigned by seat; deadline 10-24 10:00 AM CT | ALL | 443.297 | IN PROGRESS | box in docs/bus/lead/boxes/2026-10-23

## Summary
Section | Total | DONE-LIVE | DONE | MERGED-UNVERIFIED | CODED | PARTIAL | IN PROGRESS | OPEN | BLOCKED | PAUSED | RE-VERIFY
A · Owner requests (last 24 h) | 45 | 15 | 0 | 4 | 6 | 2 | 1 | 16 | 1 | 0 | 0
B · Board implementation (code audit e8a9f02b) | 35 | 4 | 0 | 6 | 8 | 7 | 0 | 10 | 0 | 0 | 0
C · New approved designs (10-23 5:08 PM) | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
E · Data / engine root causes | 18 | 2 | 0 | 1 | 1 | 1 | 0 | 13 | 0 | 0 | 0
F · Live screenshot findings 10-23 5:10 PM (new) | 24 | 2 | 0 | 0 | 4 | 2 | 0 | 16 | 0 | 0 | 0
G · Main reds / guards | 5 | 0 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 0 | 0
H · Codex live Chrome audit D001-D079 (docs/bus/AUDIT-443.257-REGISTER.md) | 80 | 3 | 0 | 3 | 9 | 1 | 0 | 63 | 0 | 0 | 1
F · Money tie-outs | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0
E · Main static reds | 5 | 0 | 1 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0
E · Guards | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
ALL | 224 | 26 | 1 | 16 | 34 | 13 | 2 | 129 | 1 | 1 | 1