## UI + MECHANICAL FIXES
IH35-TMS — UI AND MECHANICAL FIX REGISTER
Box sizes, columns, auto-fit, sorting, filters, modals, uploads, formatting. Everything you told me across these conversations. Purge and accounting are excluded — you gave the purge to Cursor. 'VERIFIED FIXED' means I checked the file on main today. 'NOT VERIFIED' means I traced it once and have not re-checked. 'REPORTED DONE' means a seat said so and I have not swept it myself.
ID | Root | What you asked for | Where it shows | Status | Mechanism / file:line | Seat
LAY-01 | 3 Layout law | Everything must adjust to the page — every module, every modal | Systemwide | STILL OPEN — no layout law exists | There is no written layout law and no ratchet guard. Each screen re-decides its own sizing. This is the ONE root behind the six 'boxes out of proportion' complaints. | CURSOR
LAY-02 | 3 Layout law | 13-item dispatch subnav clipped, 8 of 13 tabs unreachable, no scrollbar | /dispatch | VERIFIED FIXED 2026-09-01 | HoverDropdownNav.css now has overflow-x:auto and min-width:max-content. Checked on main today. | CURSOR
LAY-03 | 3 Layout law | Second dispatch nav row does not wrap either | Dispatch.tsx:282 | NOT VERIFIED | flex gap-2 with no wrap and no overflow-x. Third row (SecondaryNavTabs) was already correct — proof the fix was known and not applied across. | CURSOR
LAY-04 | 3 Layout law | KPI tiles all identical width — width ignores content | components/layout/KpiCard.tsx | STILL OPEN | Line 26 still 'flex min-w-[150px] flex-1'. flex:1 1 0% makes every tile the same width no matter what is in it. Checked on main today. | CURSOR
LAY-05 | 3 Layout law | 'Expiry alerts' tile overflows its box | pages/drivers/DriverProfilePage.tsx:530 | STILL OPEN | A sentence ('0 red · 0 amber') is passed through KpiCard's `number` prop and rendered 14px bold in a 30px-tall box. | CURSOR
LAY-06 | 3 Layout law | DQF box has six different font sizes stacked in one card | pages/drivers/components/DriverDqfPanel.tsx | NOT VERIFIED | 14 / 12 / 12 / 12 / 11 / 10 px in a single card, plus three more in ParityTable. | CURSOR
LAY-07 | 3 Layout law | Customer sidebar is a hardcoded fixed height at every screen size | CustomerListSidebar.tsx | NOT VERIFIED | max-h-[760px] hardcoded in px, no breakpoint. File has moved since the audit — re-locate before fixing. | CURSOR
LAY-08 | 3 Layout law | Customers split stacks too late — sidebar full-width 768-1280px | pages/Customers.tsx:1017 | VERIFIED FIXED 2026-09-01 | Now 'flex flex-col gap-3 xl:flex-row'. Checked on main today. | CURSOR
LAY-09 | 3 Layout law | Vendors never stacks at all — detail pane gets crushed | pages/Vendors.tsx:593 | VERIFIED FIXED 2026-09-01 | Now 'flex flex-col gap-3 xl:flex-row'. The unconditional min-w-[300px] on the sidebar still needs re-checking — file moved. | CURSOR
LAY-10 | 3 Layout law | Four different control heights in one header row | pages/Customers.tsx:848-930 | NOT VERIFIED | popover text-xs, sidebar text-sm, ActionButton, toggle px-2 py-1. There is already an in-repo comment admitting this at Customers.tsx:1013. | CURSOR
CTL-01 | UI control law | All buttons the same size and text scale | Systemwide | REPORTED DONE — NOT INDEPENDENTLY VERIFIED | CC-3 reported h-9 standard. I have not swept every module to confirm. | CC-3
CTL-02 | UI control law | Checkboxes bigger — real hit target | Systemwide | REPORTED DONE — NOT INDEPENDENTLY VERIFIED | CC-3 reported >=24x24. Not swept. | CC-3
CTL-03 | UI control law | Gear icon bigger, a real icon not a glyph | Systemwide | REPORTED DONE — NOT INDEPENDENTLY VERIFIED | CC-3 reported h-4 w-4. Not swept. | CC-3
CTL-04 | UI control law | Duplicate Create buttons in accounting — consolidate to one | Accounting module | STILL OPEN | Owner requirement 3.4. Never started. | CURSOR
CTL-05 | UI control law | Receive Payments missing from the accounting nav | Accounting nav | STILL OPEN — REPORTED FOUR TIMES | Owner requirement 3.5. The page exists; the nav entry does not. | CURSOR
COL-01 | 2 Columns | Every column sortable ascending and descending, every module | Systemwide | PARTIAL | ParityTable has sort wired (23 references). Not every module uses ParityTable — the alert boards hardcode ORDER BY and sort client-side over one page only. | CC-3
COL-02 | 2 Columns | Columns MOVABLE — drag to reorder | Systemwide | STILL OPEN — DOES NOT EXIST | Zero matches for onDragStart / columnOrder in ParityTable.tsx on main today. Nothing has been built. | CC-3
COL-03 | 2 Columns | Column AUTO-FIT — payee, vendor, state must show fully, not truncate | Systemwide | STILL OPEN — DOES NOT EXIST | Zero matches for autoFit in ParityTable.tsx on main today. This is your 'auto-adjusting' item and nothing has been built. | CC-3
COL-04 | 2 Columns | Sort click target too small / limit-100 caps the sort | Invoice + list grids | STILL OPEN | The header sort only orders the 100 rows already fetched, so sorting a longer list gives the wrong answer. | CURSOR
COL-05 | 2 Columns | Three money columns everywhere: Total / Open / Variance, red when non-zero | Every money grid | STILL OPEN | Owner requirement 4.3. | CC-1
COL-06 | 2 Columns | Settlement # / Period Begin / Period End on EVERY surface | Settlements | PARTIAL | Main grid verified compliant. Other surfaces never swept. | CASCADE+CC-1
FLT-01 | 2 Filters | Filters must be COMBO BOXES in correct proportion | Systemwide | STILL OPEN | Owner requirement 2.4. | CC-3
FLT-02 | 2 Filters | Filter / gear must let you choose what to view, including posted only | Systemwide | STILL OPEN | Owner requirement 2.7. | CURSOR
FLT-03 | 2 Filters | Hide voided by default, with a toggle to show them | Systemwide | STILL OPEN | Owner requirement 2.8. | CURSOR
FLT-04 | 2 Filters | Date range must actually re-query, not filter rows already in memory | Dispatch alert boards | STILL OPEN | All three alert queries are now()-anchored snapshots. ParityTable's Range popover filters in memory and never re-queries — you cannot ask for 'late arrivals last Tuesday'. | CODEX
SRC-01 | 2 Search | Search must cover amount, load #, PO, BOL, date and status | Systemwide | STILL OPEN | Invoice search is only display_id + customer name (invoices.routes.ts:261-271). Needs one shared search builder. | CURSOR
SRC-02 | 2 Search | Search must render TRUE data | Systemwide | STILL OPEN | Owner requirement 2.6. | CURSOR
MOD-01 | Modal | Book Load wizard reopens forever — you are trapped until you reload | /dispatch | NOT VERIFIED | Dispatch.tsx:125 derives open state from the URL on EVERY mount, and the effect at 211-225 clears only the query string, not the path. Cancel + click any tab = it reopens. | CURSOR
MOD-02 | Modal | Escape inside a date picker closes the ENTIRE wizard and discards everything typed | Insurance policy wizard, any form with a date | STILL OPEN | Hit live 2026-09-01 — lost a fully completed policy form. Escape must close the picker only. | CURSOR
MOD-03 | Modal | Date fields accept no typing at all — 12 clicks to reach an expiry year | Everywhere a date is entered | STILL OPEN | components/forms/DateTimePicker.tsx renders the value in a <button>, not an <input>. No text entry, no month or year jump. A one-year policy takes twelve clicks on the arrow. | CURSOR
MOD-04 | Modal | 'Couldn't load unit list' shows in red on an empty search box | Insurance policy form | STILL OPEN | Fires a fetch on an empty query and renders the failure as an error even when selections are valid. | CURSOR
MOD-05 | Modal | Picker offers '+ Add new unit <VIN>' for a VIN that already exists | Unit pickers | STILL OPEN | Offered for VINs that exist under another entity — an invitation to duplicate real equipment. Should say the unit exists and offer to scope it. | CURSOR
SEL-01 | Selection | Select-all only selects the current page | Every bulk grid | STILL OPEN | useBulkSelection.ts: selectAll = selectPage, while the tests assert cross-page accumulation. Select-all then act = you act on 100 rows, not the whole list. | CURSOR
SEL-02 | Selection | Bulk actions lock out permanently after one failure | Bulk void / bulk ops | STILL OPEN | bulk-rate-limit.ts sets an inFlight flag with NO expiry. If a batch throws, releaseBulkInFlight() never runs and bulk is dead until restart. Plus a 5-second interval at 1 point. | CURSOR
SEL-03 | Selection | Bulk must pre-validate and show what cannot be voided BEFORE running | Bulk void | STILL OPEN | One unreversible row rolled back all 11 selected bills: '0 of 11 succeeded; 1 failed.' | CURSOR
SEL-04 | Selection | Multi-select void on EVERY accounting table | Settlements, loads | STILL OPEN | Present elsewhere, absent on settlements and loads. | CURSOR
VIS-01 | 4 Void visibility | VOID banner at the top of the detail view | Every document | STILL OPEN | A voided document does not announce itself when you open it. | CC-1
VIS-02 | 4 Void visibility | Void as a first-class status column + filter + gear option | Every grid | STILL OPEN | Owner requirement 4.2. | CURSOR
VIS-03 | 4 Void visibility | Void button inside the transaction, not only in the list | Every document | STILL OPEN | Owner requirement 4.4. | CC-1
VIS-04 | 4 Void visibility | Void reason must be a dropdown catalog, memo optional — no free typing | Void dialog | STILL OPEN | catalogs.void_reasons does not exist. | CURSOR
DSP-01 | 5 Dispatch board | Keep pickup city and delivery city columns | Dispatch board | NOT VERIFIED | Owner requirement 5.1. | CURSOR
DSP-02 | 5 Dispatch board | Add pickup DATE, pickup TIME, delivery DATE, delivery TIME | Dispatch board | STILL OPEN | The data already exists in mdata.load_stops. Four columns. | CURSOR
DSP-03 | 5 Dispatch board | Board shows LIVE loads only — completed and cancelled to a History tab | Dispatch board | STILL OPEN | 65 of 78 loads on the board are already finished. | CURSOR
DSP-04 | 5 Dispatch board | Each section gets its OWN headers, sort and filters | Dispatch board | STILL OPEN | Owner requirement 5.4. | CURSOR
DSP-05 | 5 Dispatch board | Dispatcher on-screen confirmation on assignment + owner override | Dispatch board | DROPPED — ASSIGNED TO NOBODY | Owner requirement 5.5. | NOBODY
DSP-06 | 5 Dispatch board | Detention board never clears — closed loads stay on it forever | /dispatch detention | STILL OPEN | detention.service.ts:220 filters on the detention event status, joins mdata.loads, selects l.status and never filters on it. | CODEX
DSP-07 | 5 Dispatch board | At-Risk board is narrower than its own label | /dispatch at-risk | STILL OPEN | arch-tabs.service.ts:61 filters l.status='in_transit' ONLY. A dispatched load already blowing its window is invisible here but visible on Late Arrivals. | CODEX
DSP-08 | 5 Dispatch board | KPI card double-counts and drills to half of what it counted | Dispatch overview | STILL OPEN | DispatchOverview.tsx:277 — atRiskLateTotal = atRisk + late, so a load that is both is counted twice, then the card links to /dispatch/at-risk. | CODEX
DSP-09 | 5 Dispatch board | Detention is not in the KPI row at all | Dispatch overview | STILL OPEN | It is a panel further down the page. | CODEX
PLN-01 | 6 Planner | The planner filter bar is dead code — the 18-preset picker changes nothing | Planners | STILL OPEN | DispatchPlannersLayout.tsx:19-44 — `filters` is set and never read again. Never passed to PlannerRangeProvider or any planner. | CODEX
PLN-02 | 6 Planner | Planners are forward-only — you cannot look at last week | Planners | STILL OPEN | buildPlannerRange always anchors start to companyToday(). Four buttons: 7/14/30/40 days forward. | CODEX
PLN-03 | 6 Planner | Dates must read Aug-21, not 08-21 | Planners, HOS tracker, driver scheduler | PARTIAL | Still `.slice(5)` in HosTrackerSection.tsx:366 and DriverSchedulerGridPage.tsx:243 on main today. The correct formatter exists 200 lines away in PlannerCalendarPage.tsx:266. | CURSOR
PLN-04 | 6 Planner | Columns need visible lines that line up with their headers | Planners | NOT VERIFIED | Body cells border-l border-gray-50 (lightest in the scale); header day cells have no vertical border at all. | CURSOR
PLN-05 | 6 Planner | Show only ACTIVE drivers and units | Planners | STILL OPEN | driver-scheduler.service.ts:1020 selects d.status and never filters on it. A terminated driver whose deactivated_at is NULL still renders. Same for units. Trip Pairing does gate correctly — the right code exists nearby. | CODEX
PLN-06 | 6 Planner | Book button in its own column | Planners | STILL OPEN | UnifiedTimelinePlanner.tsx:239 puts driver link + unit link + Book button in ONE cell under one header, and only when status='Available', so column width changes row to row. Absent entirely from the Driver, Truck and Loads planners. | CURSOR
UPL-01 | 1 Upload | Upload missing in 15 places — it is ONE architectural gap, not fifteen | Systemwide | STILL OPEN | Two competing upload stacks: docs.files (8 entity types) and documents.attachments (23 types). No shared UI component, so every new screen re-decides and most skip it. | CC-1+CURSOR
UPL-02 | 1 Upload | DOT medical card has nowhere to save a document | Safety / driver profile | STILL OPEN | safety.medical_cards has NO document column at all (migration 0248). A button would have nowhere to write. | CC-1
UPL-03 | 1 Upload | Background check has nowhere to save a document | Safety | STILL OPEN | safety.background_checks has no document column (migration 0249). | CC-1
UPL-04 | 1 Upload | No upload on: drug test, company violation, HOS violation, border credentials, office fuel transaction, banking categorize drawer, banking expense form | 7 surfaces | STILL OPEN | Verified file by file. Note the same object answers differently: expense create HAS upload from Accounting and NONE from Banking. | CURSOR
UPL-05 | 1 Upload | MVR check has no create surface at all | Safety | STILL OPEN | Not a missing button — the screen does not exist. | CURSOR
UPL-06 | 1 Upload | DOT inspection: row-action PDF only, the create form has none | Safety | STILL OPEN | Partial by design accident. | CURSOR
WIR-01 | 8 Wired? | Border crossing manifest PDF is never generated | Border crossing wizard | STILL OPEN | The endpoint and renderer both exist. WizardStep6.tsx:101 shows the reference string and never calls it. Not saved to the load either. | CURSOR
WIR-02 | 8 Wired? | Driver Export PDF downloads index.html renamed as a PDF | Drivers | STILL OPEN | ActionBar.tsx:31 builds a relative href and never calls resolveApiUrl. Production is split-hosted, so it hits the static host which answers index.html with HTTP 200. The backend route is fine. | CURSOR
WIR-03 | 8 Wired? | Dispatch Factoring tab leaves the Dispatch module | /dispatch | STILL OPEN | /dispatch/factoring-queue is routed and real but has no tab, while the Dispatch 'Factoring' tab points at /accounting/factoring. Factoring appears in Dispatch three times pointing two places. | CURSOR
WIR-04 | 8 Wired? | A complete e-signature pipeline exists and W-8BEN does not use it | Legal / onboarding | STILL OPEN | Working OTP + drawn-signature canvas + signed PDF pipeline in LegalSignPage, and a second one in the driver PWA. W-8BEN captures a typed name in a text box and stores no artifact at all. | CURSOR
CUS-01 | 7 Customers | Two competing customer pages with different tab sets | Customers | STILL OPEN | Customers.tsx has 12 tabs, CustomerDetail.tsx has a different 13. Each has sections the other lacks. | CC-3
CUS-02 | 7 Customers | Three dead stub tabs — Projects, Opportunities, Conversations | Customers.tsx:334 | STILL OPEN | Dashed box, no query behind any of them. | CC-3
CUS-03 | 7 Customers | Cannot sort by balance in the view you actually use | Customers + Vendors sidebar | STILL OPEN | Sidebar comparator is name-only and the select offers two options. Balance sort exists only in the opt-in List view. Identical gap on vendors. | CC-3
CUS-04 | 7 Customers | A brand-new customer renders '0.0/100 At Risk' in red | Relationship health | STILL OPEN | With every subscore null the weighted score returns 0, which maps to tier at_risk. There is no 'not enough data' state. That is a false accusation printed on screen. | CC-3
CUS-05 | 7 Customers | Vendor W-9 tab does not check whether a W-9 exists | VendorDetail.tsx:1334 | STILL OPEN | A static chip reading 'Managed in Documents'. It queries nothing. | CC-3
CUS-06 | 7 Customers | Two hardcoded em-dashes where fields should be | Customers.tsx:1039,1041 | STILL OPEN | Shipping address and custom fields are literal em-dashes. | CC-3
CUS-07 | 7 Customers | Eleven reverse sections in one unbroken column above the tab strip, all vanish silently with no operating company selected | CustomerDetail.tsx:1260 | STILL OPEN | No empty state, no message saying why. | CC-3
DQF-01 | 2 DQF | '+ Create checklist item' looks dead | Driver DQF panel | STILL OPEN | It is disabled={!itemName.trim()} — disabled because the text box is empty. It looks dead because there is no wizard behind it. DQF items are free text with no catalog and no FK. | CC-1+CURSOR

## BY ROOT
THE ROOTS — fix these and the symptoms close together
Your list is ~70 symptoms of a small number of roots. Patch the symptoms and they come back.
BY ROOT CAUSE
Items
3 Layout law | 10
5 Dispatch board | 9
7 Customers | 7
2 Columns | 6
6 Planner | 6
1 Upload | 6
UI control law | 5
Modal | 5
2 Filters | 4
Selection | 4
4 Void visibility | 4
8 Wired? | 4
2 Search | 2
2 DQF | 1
BY STATUS
Items
STILL OPEN | 56
NOT VERIFIED | 7
VERIFIED FIXED 2026-09-01 | 3
REPORTED DONE | 3
PARTIAL | 3
DROPPED | 1
TOTAL NOT CONFIRMED FIXED | 70